## E 9TH STREET
Revision Date:
2009-11-19
EAST 9TH STREET STORM SEWER OUTFALL AREA
Along Broadway Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Railroad Crossing | Active | Across | 102 + 50 | NS | PRIVATE | Private | NS | NO | CONTRACT | NEUTRAL | NO |  | Unknown | 0 months | 2010-01-01
Along East 9th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Railroad Crossing | Active | Across | 109 + 40 | GCRTA | PRIVATE | Private | GCRTA | NO | CONTRACT | NEUTRAL | NO |  | Unknown | 0 months | 2010-01-01
Railroad Crossing | Active | Across | 109 + 60 | GCRTA | PRIVATE | Private | GCRTA | NO | CONTRACT | NEUTRAL | NO |  | Unknown | 0 months | 2010-01-01
8” Water | Active | Across | 112 + 40 | CWD | PUBLIC | Private | City | YES | CONTRACT | HIGH | YES | DBT | Unknown | 0 months | 2010-01-01
Communications | Abandoned | Across | 115 + 30 | SPRINT | PRIVATE | Private | City | YES | YES | LOW | YES | SPRINT | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 118 + 45 | CEI | PRIVATE | City | City | YES | NO | HIGH | YES | CEI | Unknown | 0 months | 2010-01-01
12" Water | Active | Across | 118 + 70 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
8" Gas | Active | Across | 122 + 50 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
6” Gas | Active | Across | 122 + 55 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 122 + 75 | ATT | PRIVATE | City | City | YES | NO | HIGH | YES | ATT | Unknown | 0 months | 2010-01-01
Unidentified Facility | Active | Across | 122 + 75 | UNKNOWN | PRIVATE | City | City | YES | NO | HIGH | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
24" Combined Sewer | Active | Across | 122 + 80 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
6” Water | Active | Across | 122 + 95 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Along Commercial Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station** | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Unidentified Facility | Active | Parallel | North | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
Unidentified Facility | Active | Parallel | North | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
8" Gas*** | Active | Parallel | North | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
6" Gas*** | Active | Parallel | North | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Parallel | North | CPP | PUBLIC | City | City | NO | YES | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
128 KV Conductor**** | Active | Parallel | North | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
128 KV Conductor**** | Active | Parallel | North | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
Communications*** | Active | Parallel | North | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
12" Water*** | Active | CL |  | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Communications*** | Active | Across | 17 + 75 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
128 KV Conductor**** | Active | Across | 16 + 45 | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
Communications*** | Active | Across | 16 + 45 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
128 KV Conductor**** | Active | Across | 16 + 10 | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
12" Water*** | Active | Across | 15 + 00 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Communications*** | Active | Across | 14 + 60 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
36" Combined Sewer*** | Active | Across | 14 + 60 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Unidentified Facility*** | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
8" Gas*** | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
6” Gas*** | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Horizon Tunnel**** | Active | Across | 13 + 40 | CEI | PRIVATE | Easement | Easement | NO | YES | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
Unidentified Facility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
6” Water | Active | Parallel | West | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Along Canal Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
6” Water | Active | Across | 123 + 40 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 123 + 50 | ATT | PRIVATE | City | City | YES | NO | HIGH | YES | ATT | Unknown | 0 months | 2010-01-01
24" Combined Sewer | Active | Across | 123 + 60 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
8" Gas | Active | Across | 124 + 05 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
6” Gas | Active | Across | 124 + 10 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
12" Combined Sewer | Active | Across | 125 + 40 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
10” Water | Active | Across | 125 + 55 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Along 40' Storm Easement
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station* | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Communications | Abandoned | Across | 126 + 15 | SPRINT | PRIVATE | City | City | NO | YES | LOW | YES | SPRINT | Unknown | 0 months | 2010-01-01
Railroad Crossing | Active | Across | 126 + 25 | NS | PRIVATE | Private | NS | NO | CONTRACT | NEUTRAL | NO |  | Unknown | 0 months | 2010-01-01
Railroad Crossing | Active | Across | 126 + 40 | NS | PRIVATE | Private | NS | NO | CONTRACT | NEUTRAL | NO |  | Unknown | 0 months | 2010-01-01
Railroad Crossing | Active | Across | 127 + 00 | CSX | PRIVATE | Private | CSX | NO | CONTRACT | NEUTRAL | NO |  | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 127 + 05 | ATT | PRIVATE | City | City | MAYBE | NO | HIGH | YES | ATT | Unknown | 0 months | 2010-01-01
* Stationing is taken from the Storm Sewer alignment.
** Stationing is taken from proposed Commercial Road alignment.
*** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road.
**** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road. This facility may not be relocated or impacted in any way. Load constraints are defined in existing easement documents.

## EAST BANK
Revision Date:
2009-11-17
EAST BANK STORM SEWER OUTFALL AREA
Central Viaduct Way
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Electric conduit* | Active | Across | 100 + 95 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Communications* | Active | Across | 101 + 00 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
128 KV Conductor** | Active | Across | 101 + 25 | CEI | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
128 KV Conductor** | Active | Across | 101 + 60 | CEI | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
4" Gas* | Active | Across | 101 + 20 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Communications* | Active | Across | 103 + 05 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
12" Water* | Active | Across | 103 + 20 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Canal Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Horizon Tunnel** | Active | Across | 106 + 40 | CEI | PRIVATE | Easement | Easement | NO | YES | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
6” Water*** | Active | Across | 106 + 10 | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Communications*** | Active | Across | 106 + 15 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
24" Combined Sewer*** | Active | Across | 106 + 25 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
8" Gas*** | Active | Across | 107 + 45 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
4” Gas*** | Active | Across | 107 + 50 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
Railroad Crossing | Active | Across | 109 + 00 | CSX | PRIVATE | Private | CSX | YES | CONTRACT | HIGH |  |  | Unknown | 0 months | 2010-01-01
Railroad Crossing | Active | Across | 109 + 20 | CSX | PRIVATE | Private | CSX | YES | CONTRACT | HIGH |  |  | Unknown | 0 months | 2010-01-01
Communications*** | Active | Across | 109 + 40 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
West 3rd Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
15" Combined Sewer | Active | Across | 111 + 45 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
6” Water | Active | Across | 111 + 55 | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
10” Water | Active | Across | 111 + 70 | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
4” Gas | Active | Across | 111 + 90 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
Industrial Flats Driveway
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
2” Water | Active | Across | 115 + 00 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
2” Water | Active | Across | 117 + 50 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 122 + 45 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Railroad Crossing | Active | Across | 123 + 60 | NS | PRIVATE | Private | NS | YES | CONTRACT | HIGH |  |  | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 123 + 70 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Railroad Crossing | Active | Across | 123 +85 | NS | PRIVATE | Private | NS | YES | CONTRACT | HIGH |  |  | Unknown | 0 months | 2010-01-01
*Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road.
** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road. This facility may not be relocated or impacted in any way. Load constraints are defined in existing easement documents.
***Utility facilities located under existing Canal Road. Facility position varies with actual location on Canal Road.

## WEST BANK - EAST of I90
Revision Date:
2009-11-17
WEST BANK STORM SEWER OUTFALL AREA
West 15th Street (old ROW)
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Unidentified Facility | Active | Across | 100 + 25 | UNKNOWN | PRIVATE | City | City | YES | NO | HIGH | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
1.5" Water* | Active | Across | 100 + 60 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
15" Combined Sewer*** | Active | Across | 101 + 45 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Fairfield Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
8” Gas | Active | Across | 102 + 25 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
12" Combined Sewer | Active | Across | 102 + 30 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
10" Water | Active | Across | 102 + 40 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
24" Combined Sewer | Active | Across | 102 + 55 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 102 + 60 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
8” Gas | Active | Across | 102 + 70 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Canal Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Electric conduit | Active | Across | 110+ 00 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 110 + 35 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
6” Water | Active | Across | 110 + 60 | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
16” Water | Active | Across | 111 + 10 | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
12" Combined Sewer | Active | Across | 111 + 40 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
University Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
60" Combined Sewer | Active | Across | 112 + 90 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
2” Gas | Active | Across | 113 + 00 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 114 + 60 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 114 + 75 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 114 + 75 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
21" Combined Sewer | Active | Across | 114 + 75 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
24" Combined Sewer | Active | Across | 114 + 35 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
6” Gas | Active | Across | 114 + 40 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
24" Combined Sewer | Active | Across | 115 + 10 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01

## WEST BANK - WEST of I90
Revision Date:
2009-11-17
WEST BANK STORM SEWER OUTFALL AREA
West 15th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
15" Combined Sewer | Active | Across | 100 + 20 | CWPC | PUBLIC | City | ODOT | MAYBE | CONTRACT | HIGH | YES | DBT | Advance | 0 months | 2010-01-01
6” Water | Active | Across | 100 + 30 | CWD | PUBLIC | City | ODOT | MAYBE | CONTRACT | HIGH | YES | DBT | Unknown | 0 months | 2010-01-01
8” Gas | Active | Across | 100 + 45 | DEOG | PRIVATE | City | ODOT | MAYBE | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
Abbey Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Electric conduit | Active | Across | 103 + 40 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Unidentified Facility | Active | Across | 103 + 50 | UNKNOWN | PRIVATE | City | City | YES | NO | HIGH | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
6” Water | Active | Across | 103 + 60 | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
6" Gas | Active | Across | 103 + 95 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
Crown Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
6" Water | Active | Across | 104 + 70 | CWD | PUBLIC | City | ODOT | YES | CONTRACT | HIGH | YES | DBT | Unknown | 0 months | 2010-01-01
18" Combined Sewer | Active | Across | 104 + 80 | CWPC | PUBLIC | City | ODOT | YES | YES | HIGH | YES | NEORSD | Unknown | 0 months | 2010-01-01
Cold Storage Drive
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Electric conduit | Active | Across | 107 + 25 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 107 + 25 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
University Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
16” Water | Active | Across | 107 + 90 | CWD | PUBLIC | City | ODOT | YES | CONTRACT | HIGH | YES | DBT | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 107 + 95 | CPP | PUBLIC | City | ODOT | YES | YES | HIGH | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
24" Combined Sewer | Active | Across | 108 + 05 | NEORSD | PUBLIC | City | ODOT | YES | YES | HIGH | YES | NEORSD | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 108 + 10 | CPP | PUBLIC | City | ODOT | YES | YES | HIGH | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 108 + 20 | ATT | PRIVATE | City | ODOT | YES | NO | HIGH | YES | ATT | Unknown | 0 months | 2010-01-01
6” Gas | Active | Across | 108 + 25 | DEOG | PRIVATE | City | ODOT | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01

## LISTS
Location | Utility | Schedule | Duration | Property |  |  | Status
North | ATT | Advance | 0 months | ODOT | YES | HIGH | Active
South | DEOG | DB Contract | 3 months | City | NO | LOW | Abandoned
East | CEI | Unknown | 6 months | Private | MAYBE | NEUTRAL
West | CWD | Not Required | 9 months | Easement | CONTRACT
CL | NEORSD |  | 12 months |  | ABANDON
Across | ODOT |  | 15 months
Parallel | UNKNOWN |  | 18 months
| DBT |  | 21 months
| NOT REQ'D |  | 24 months
CPP
ADELPHIA
DOMINION
MCI
CWPC
DOMTEL
VERIZON
SPRINT
NOT ALLOW
The facilities tabulated below are located inside the proposed Commercial Road ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Central Viaduct Way ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed E 14th Street ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Broadway Avenue ROW. Construction of the new roadway may or may not impact these facilities.