## E 9TH
Revision Date:
2009-10-30
EAST 9TH STREET
The facilities tabulated below are located inside the proposed E 9th Street aerial ROW. Construction of the new roadway may impact these facilities.
Roadway from Canal Road to Commercial Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Aerial Utility | Active | Across | 11 + 75 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 11 + 75 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 12 + 50 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
High Volt Tension | Active | Across | 13 + 50 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
High Volt Tension | Active | Across | 13 + 50 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Roadway from Commercial Road to GCRTA Crossing
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Aerial Utility | Active | Across | 16 + 25 | UNKNOWN | PRIVATE | City | City | YES |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 16 + 25 | UNKNOWN | PRIVATE | City | City | YES |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
GCRTA Crossing (to Broadway Avenue)*
No immediately identified potential conflicts.
Other potential aerial conflicts may include overhead power and lighting lines not identified here.
*Railroad drainage, signal, communication and cantenary facilities are located within the GCRTA corridor.

## COMMERCIAL
Revision Date:
2009-10-30
COMMERCIAL ROAD
The facilities tabulated below are located inside the proposed E 9th Street aerial ROW. Construction of the new roadway may impact these facilities.
Roadway from E 9th Street to Existing Commercial Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
High Volt Tension | Active | Across | 10 + 50 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
High Volt Tension | Active | Across | 10 + 50 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 12 + 75 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
High Volt Tension | Active | Parallel | North | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
High Volt Tension | Active | Parallel | North | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Roadway from Proposed Commercial Road to Central Viaduct Way
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Guidewire | Active | Across | 13 + 00 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 13 + 25 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 13 + 25 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 15 + 50 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 15 + 50 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Guidewire | Active | Across | 14 + 75 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Guidewire | Active | Across | 16 + 00 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Other potential aerial conflicts may include overhead power and lighting lines not identified here.

## CENTRAL VIADUCT WAY
Revision Date:
2009-10-30
CENTRAL VIADUCT WAY
The facilities tabulated below are located inside the proposed E 9th Street aerial ROW. Construction of the new roadway may impact these facilities.
Commercial Road to Carnegie Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 102 + 00 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 102 + 25 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 102 + 50 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 103 + 50 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Guidewire | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Guidewire | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 105 + 00 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 105 + 00 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Other potential aerial conflicts may include overhead power and lighting lines not identified here.

## E 14TH
Revision Date:
2009-10-30
EAST 14TH STREET
The facilities tabulated below are located inside the proposed E 9th Street aerial ROW. Construction of the new roadway may impact these facilities.
Broadway Avenue to Orange Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Aerial Utility | Active | Across | 11 + 00 | UNKNOWN | PRIVATE | City | City | YES |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Parallel | West | UNKNOWN | PRIVATE | City | City | YES |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | YES |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 13 + 50 | UNKNOWN | PRIVATE | City | City | YES |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 14 + 25 | UNKNOWN | PRIVATE | City | City | YES |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Post Office Lights | Active | Parallel | East | CPP | PUBLIC | Private | Private | YES |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Other potential aerial conflicts may include overhead power and lighting lines not identified here.

## BROADWAY
Revision Date:
2009-10-30
BROADWAY AVENUE
The facilities tabulated below are located inside the proposed E 9th Street aerial ROW. Construction of the new roadway may impact these facilities.
Roadway from E 9th Street to E 14th Street
No immediately identified potential conflicts.
Roadway from E 14th Street to existing Broadway Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Aerial Utility | Active | Across | 15 + 00 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | ADELPHIA | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Parallel | North | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Parallel | South | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | ADELPHIA | Unknown | 0 months | 2010-01-01
Guidewire | Active | Across | 14 + 00 | UNKNOWN | PRIVATE | City | City | YES |  | NEUTRAL | YES | ADELPHIA | Unknown | 0 months | 2010-01-01
Aerial Utility | Active | Across | 11 + 00 | UNKNOWN | PRIVATE | City | City | YES |  | NEUTRAL | YES | ADELPHIA | Unknown | 0 months | 2010-01-01
Other potential aerial conflicts may include overhead power and lighting lines not identified here.

## BROADWAY WALL
Revision Date:
2009-10-30
BROADWAY AVENUE RETAINING WALL
The facilities tabulated below are located inside the proposed E 9th Street aerial ROW. Construction of the new roadway may impact these facilities.
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Guidewire | Active | Across | 14 + 00 | UNKNOWN | PRIVATE | City | City | YES |  | NEUTRAL | YES | ADELPHIA | Unknown | 0 months | 2010-01-01
Other potential aerial conflicts may include overhead power and lighting lines not identified here.

## DRIVES
Revision Date:
2009-10-30
COMMERCIAL ROAD HILL DRIVEWAYS
Drive "A"
No immediately identified potential conflicts.
Drive "B"
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted |  | Priority | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Aerial Utility | Active | Across | 41 + 75 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Drive "C"
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Aerial Utility | Active | Across | 61 + 00 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Guidewire | Active | Across | 61 + 00 | UNKNOWN | PRIVATE | City | City | MAYBE |  | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Drive "D"
No immediately identified potential conflicts.
Drive "E"
No immediately identified potential conflicts.
Other potential aerial conflicts may include overhead power and lighting lines not identified here.

## LISTS
Location | Utility | Schedule | Duration | Property |  |  | Status
North | ATT | Advance | 0 months | ODOT | YES | HIGH | Active
South | DEOG | DB Contract | 3 months | City | NO | LOW | Abandoned
East | CEI | Unknown | 6 months | Private | MAYBE | NEUTRAL
West | CWD | Not Required | 9 months | Easement | CONTRACT
CL | NEORSD |  | 12 months |  | ABANDON
Across | ODOT |  | 15 months
Parallel | UNKNOWN |  | 18 months
| DBT |  | 21 months
| NOT REQ'D |  | 24 months
CPP
ADELPHIA
DOMINION
MCI
CWPC
DOMTEL
The facilities tabulated below are located inside the proposed Commercial Road ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Central Viaduct Way ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed E 14th Street ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Broadway Avenue ROW. Construction of the new roadway may or may not impact these facilities.