## WEST APP ROAD
Revision Date:
2009-11-23
WB MAINLINE WEST APPROACH ROADWAY FROM I-71 / I-90 SPLIT TO KENILWORTH
No immediately identified underground utility conflicts, however, potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.

## WEST APP WALL
Revision Date:
2009-11-23
WB MAINLINE WEST APPROACH RETAINING WALLS BETWEEN KENILWORTH AND FAIRFIELD
No immediately identified underground utility conflicts, however, potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.

## KENILWORTH
Revision Date:
2009-11-23
WB MAINLINE OVER KENILWORTH BRIDGE WIDENING
The facilities tabulated below are located inside the existing Kenilworth Avenue ROW.
Construction of substructure unit foundations outside of NBZ should minimize possible underground utility conflicts.
Kenilworth Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
20” Gas | Active | Across | 109+34 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
45" Combined Sewer | Active | Across | 109+43 | NEORSD | PUBLIC | City | City | NO | CONTRACT | HIGH | YES | NOT REQ'D | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 109+69 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 109+69 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
6" Water | Active | Across | 109+80 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
48" Combined Sewer | Active | Across | 109+86 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 109+96 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
16" Water | Active | Across | 110+11 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
Underbridge lighting circuits (overhead) belongs to CPP

## FAIRFIELD
Revision Date:
2009-11-23
WB MAINLINE OVER FAIRFIELD BRIDGE
The facilities tabulated below are located inside the existing Fairfield Avenue ROW.
Construction of substructure unit foundations outside of NBZ should minimize possible underground utility conflicts.
Fairfield Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
8” Gas | Active | Across | 119+44 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
12" Combined Sewer | Active | Across | 119+47 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
10" Water | Active | Across | 119+62 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
24" Combined Sewer | Active | Across | 119+68 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 119+76 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
8” Gas | Active | Across | 119+88 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
4" Gas | Active | Parallel | West | DEOG | PRIVATE | Private | ODOT | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
6" Water | Active | Parallel | West | CWD | PUBLIC | Private | ODOT | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.

## RAMP A6
Revision Date:
2009-11-23
RAMP A6 CONSTRUCTION (WB MAINLINE TO ABBEY / W 14TH)
W 15th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
6” Water | Active | Parallel | East | CWD | PUBLIC | City | ODOT | MAYBE | CONTRACT | HIGH | YES | DBT | Unknown | 0 months | 2010-01-01
8” Gas | Active | Parallel | East | DEOG | PRIVATE | City | ODOT | MAYBE | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
15" Combined Sewer | Active | Parallel | East | CWPC | PUBLIC | City | ODOT | MAYBE | CONTRACT | HIGH | YES | DBT | Advance | 0 months | 2010-01-01
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
Identified conflicts also include service disconnections for buildings to be demolished although they are not listed separately.

## WEST BANK
Revision Date:
2009-11-23
WEST BANK SLOPE UNLOADING
University Road - West
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
16” Water | Active | Across | 130 + 84 | CWD | PUBLIC | City | ODOT | YES | CONTRACT | HIGH | YES | DBT | Unknown | 0 months | 2010-01-01
6” Gas | Active | Across | 130 + 86 | DEOG | PRIVATE | City | ODOT | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 130 + xx | CPP | PUBLIC | City | ODOT | YES | YES | HIGH | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 130 + 95 | CEI | PRIVATE | City | ODOT | YES | NO | HIGH | YES | CEI | Unknown | 0 months | 2010-01-01
24" Combined Sewer | Active | Across | 131 + 14 | NEORSD | PUBLIC | City | ODOT | YES | YES | HIGH | YES | NEORSD | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 131 + 16 | ATT | PRIVATE | City | ODOT | YES | NO | HIGH | YES | ATT | Unknown | 0 months | 2010-01-01
6” Gas | Active | Across | 131 + 19 | DEOG | PRIVATE | City | ODOT | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
University Road - East
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
60" Combined Sewer | Active | Across | 129 + 98 | NEORSD | PUBLIC | City | ODOT | YES | YES | HIGH | YES | NEORSD | Advance | 0 months | 2010-01-01
2” Gas | Active | Across | 130 + 17 | DEOG | PRIVATE | City | ODOT | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 130 + 79 | CPP | PUBLIC | City | ODOT | YES | YES | HIGH | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 130 + 92 | CEI | PRIVATE | City | ODOT | YES | NO | HIGH | YES | CEI | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 130 + 94 | ATT | PRIVATE | City | ODOT | YES | NO | HIGH | YES | ATT | Unknown | 0 months | 2010-01-01
24" Storm Sewer | Active | Across | 130 + 98 | NEORSD | PUBLIC | City | ODOT | YES | YES | HIGH | YES | NEORSD | Advance | 0 months | 2010-01-01
8” Gas | Active | Parallel | East | DEOG | PRIVATE | City | ODOT | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
Crown Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
3” Gas | Active | Across | 128 + 56 | DEOG | PRIVATE | City | ODOT | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
6" Water | Active | Across | 128 + 74 | CWD | PUBLIC | City | ODOT | YES | CONTRACT | HIGH | YES | DBT | Unknown | 0 months | 2010-01-01
18" Combined Sewer | Active | Across | 128 + 84 | CWPC | PUBLIC | City | ODOT | YES | YES | HIGH | YES | NEORSD | Unknown | 0 months | 2010-01-01
W 15th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
12" Combined Sewer | Active | Parallel | West | CWPC | PUBLIC | City | ODOT | YES | CONTRACT | HIGH | YES | DBT | Advance | 0 months | 2010-01-01
3” Gas | Active | Parallel | West | DEOG | PRIVATE | City | ODOT | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
6” Water | Active | Parallel | West | CWD | PUBLIC | City | ODOT | YES | CONTRACT | HIGH | YES | DBT | Unknown | 0 months | 2010-01-01
W 14th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
4" Gas | Active | Parallel | East | DEOG | PRIVATE | City | ODOT | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
60" Combined Sewer | Active | Parallel | East | NEORSD | PUBLIC | City | ODOT | YES | CONTRACT | HIGH | YES | NEORSD | Advance | 0 months | 2010-01-01
16” Water | Active | Parallel | East | CWD | PUBLIC | City | ODOT | YES | CONTRACT | HIGH | YES | DBT | Unknown | 0 months | 2010-01-01
12" Gas | Active | Parallel | East | DEOG | PRIVATE | City | ODOT | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
36" Combined Sewer | Active | Across | 128 + 80 | NEORSD | PUBLIC | City | ODOT | YES | CONTRACT | HIGH | YES | NEORSD | Advance | 0 months | 2010-01-01
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
Identified conflicts also include service disconnections for buildings to be demolished although they are not listed separately.

## SUBSTRUCTURE
Revision Date:
2009-11-23
I-90 VIADUCT SUBSTRUCTURE UNITS (W 14TH STREET EXTENSION TO ONTARIO STREET)
DBT TO PROVIDE SUBSTRUCTURE UNIT LOCATIONS AND COMPLETE TABLES
DBT to add tables as necessary for each additional substructure unit. DBT to add rows to tables as necessary to account for each identified impact.
REAR ABUTMENT STATION XX + XX
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
| Active |  | YY + YY | UNKNOWN | PRIVATE |  |  | MAYBE | NO | LOW | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
PIER "N" STATION XX + XX
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing
| Active |  | YY + YY | UNKNOWN | PRIVATE |  |  | MAYBE | NO | LOW | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
FORWARD ABUTMENT STATION XX + XX
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
| Active |  | YY + YY | UNKNOWN | PRIVATE |  |  | MAYBE | NO | LOW | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
Utility facilities being abandoned or relocated as part of West Bank Slope Unloading within the proposed Right of Way from Abbey Avenue to the Cuyahoga River.
Identified conflicts also include service disconnections for buildings to be demolished although they are not listed separately.

## ONTARIO
Revision Date:
2009-11-23
RAMP A4 AND WB MAINLINE OVER ONTARIO BRIDGE
The facilities tabulated below are located inside the existing Ontario Street ROW.
Construction of substructure unit foundations outside of NBZ should minimize possible underground utility conflicts.
Ontario Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Communications | Active | Across | 168 + 37 | VERIZON | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | VERIZON | Unknown | 0 months | 2010-01-01
8" Gas | Active | Across | 168 + 40 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
20” Gas | Active | Across | 168 + 42 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
10" Water | Active | Across | 168 + 78 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
24" Combined Sewer | Active | Across | 168 + 86 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 169 + 09 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 169 + 15 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 169 + 96 | CPP | PUBLIC | City | City | MAYBE | YES | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.

## EAST APP ROAD
Revision Date:
2009-11-23
WB MAINLINE EAST APPROACH ROADWAY
No immediately identified underground utility conflicts, however, potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.

## RAMP A4 WALL
Revision Date:
2009-11-23
RAMP A4 RETAINING WALL (Adjacent to CCC)
Facility Crossing under Proposed Wall
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Communications | Abandoned | CL | 604 + 73 | ATT | PRIVATE | Private | ODOT | MAYBE | NO | LOW | YES | NOT REQ'D | Unknown | 0 months | 2010-01-01 | Abandoned
Communications | Abandoned | CL | 604 + 77 | ATT | PRIVATE | Private | ODOT | MAYBE | NO | LOW | YES | NOT REQ'D | Unknown | 0 months | 2010-01-01 | Abandoned
48" Combined Sewer | Active | Across | 605 + 09 | CWPC | PUBLIC | Private | ODOT | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
RAMP A4 RETAINING WALL (Between mainline and ramp)
Facility Crossing under Proposed Wall
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Electric conduit | Active | Across | 600 + 50 | CEI | PRIVATE | City | ODOT | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 601 + 75 | CEI | PRIVATE | City | ODOT | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 602 + 50 | CEI | PRIVATE | City | ODOT | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 603 + 20 | CEI | PRIVATE | City | ODOT | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Communications | Abandoned | Across | 604 + 75 | ATT | PRIVATE | City | ODOT | MAYBE | NO | LOW | YES | NOT REQ'D | Unknown | 0 months | 2010-01-01 | Abandoned
Combined Sewer | Active | Across | 605 + 00 | CWPC | PUBLIC | City | ODOT | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
Several underground electric and communications lines are located under the proposed walls.

## E 9TH
Revision Date:
2009-11-23
RAMP A3 OVER E 9TH BRIDGE
The facilities tabulated below are located inside the existing E 9th Street ROW.
Construction of substructure unit foundations outside of NBZ should minimize possible underground utility conflicts.
E 9th Street
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Electric conduit | Active | Parallel | CL | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Parallel | North | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 175 + 73 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 175 + 83 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 176 + 11 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 176 + 17 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 176 + 29 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 176 + 33 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 176 + 39 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 176 + 42 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
85" Combined Sewer | Active | Across | 176 + 65 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 176 + 70 | CPP | PUBLIC | City | City | MAYBE | YES | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 176 + 99 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.

## RAMP A3 ROAD
Revision Date:
2009-11-23
RAMP A3 ROADWAY (Adjacent to Hilton)
No immediately identified underground utility conflicts, however, potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.

## RAMP A3 WALL
Revision Date:
2009-11-23
RAMP A3 RETAINING WALL (Adjacent to Hilton Hotel)
No immediately identified underground utility conflicts, however, potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.

## LISTS
Location | Utility | Schedule | Duration | Property |  |  | Status
North | ATT | Advance | 0 months | ODOT | YES | HIGH | Active
South | DEOG | DB Contract | 3 months | City | NO | LOW | Abandoned
East | CEI | Unknown | 6 months | Private | MAYBE | NEUTRAL
West | CWD | Not Required | 9 months | Easement | CONTRACT
CL | NEORSD |  | 12 months |  | ABANDON
Across | ODOT |  | 15 months
Parallel | UNKNOWN |  | 18 months
| DBT |  | 21 months
| NOT REQ'D |  | 24 months
CPP
ADELPHIA
DOMINION
MCI
CWPC
DOMTEL
VERIZON
SPRINT
NOT ALLOW
The facilities tabulated below are located inside the proposed Commercial Road ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Central Viaduct Way ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed E 14th Street ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Broadway Avenue ROW. Construction of the new roadway may or may not impact these facilities.