## PID 107286
[9 empty] | REPAIR/REPLACE | [22 empty] | GA |  | TTS |  |  | COMMENT
PID | SFN | C-R-S |  | DECK REPLACEMENT | TIMBER SUB-DECK | WEARING SURFACE | PATCH WS/DECK | REPAIR CURB/WALK | RAILING | DRAINAGE | EXPAN JTS | FENCE | STRUCTURAL STEEL | CROSS FRAMES | RESET/REPAIR BEARINGS | PAINT | SEAL CONCRETE | REPAIR ABUTMENT | PATCH/REPAIR BACKWALLS | PATCH/REPAIR PIERS | FIBER WRAP | SCOUR REPAIR | REPAIR/REPLACE SLOPE PROTECTION | REPAIR/REPLACE CULVERT | CHANNEL WORK | REPAIR/REPLACE APPROACH SLAB | APPROACH GUARDRAIL | UTILITY SUPPORTS/ SEAL UTILITIES | SIGN SUPPORTS | CAPACITY ENHANCE | RAILROAD LEGIS | RATING | DATE | ? | DATE | DATE ADDED TO LIST
107286 | 1807749 | CUY-090-0607 |  |  |  |  | X | X |  |  | X | X |  |  | X |  |  | X | X | X | X |  |  |  |  | X | X |  |  |  |  | 5 | 2020-07-20 | Y | 2020-07-22 | 2020-07-22 | Single column piers need work. Need expansion joint repairs. Patching work needed throughout. Repair top of backwall and aproach slab. Replace cover plates and replace tar sealer.
107286 | 1807781 | CUY-090-0667 | [8 empty] | x |  |  | X | [5 empty] | X | X | [10 empty] | 6 | 2019-05-03 |  |  | 2020-06-03 | 130% LEGAL. Expansion joint cover plates need replacement on sidewalks.
107286 | 1808125 | CUY-090-0909 |  |  |  |  | X | X |  |  | X | [5 empty] | X | [14 empty] | 7 | 2020-03-09 | Y | 2021-01-19 | 2021-01-19 | Expansion joints need replacement (both rear and forward). Seal wearing surface.
107286 | 1808346 | CUY-090-2069 | [10 empty] | X | X | [17 empty] | 6 | 2019-04-09 |  |  | 2019-09-19 | Some x-frames need repair. Rusted thru holes to web of fascia beams.
107286 | 2801655 | GEA-422-0986 | L | [7 empty] | X |  |  |  | X |  |  | X | [13 empty] | 6 | 2018-06-08 |  |  | 2018-09-13 | Expansion joints rated 3. Could use work at the abutments.
107286 | 2801744 | GEA-422-0986 | R | [7 empty] | X |  |  |  | X |  |  | X | [13 empty] | 6 | 2018-06-09 |  |  | 2018-09-13 | Expansion joints rated 3. Could use work at the abutments.
107286 | 4301056 | LAK-002-1029 | [10 empty] | X | X | X |  |  | X | X | X | X | [10 empty] | 6 | 2017-11-07 | Y | 2018-10-09 | 2018-10-10 | Substructure needs repairs. Heat straighten steel beams.
Note on B2: Youssef Seif: Check both sheets Avoid duplication
Note on C2: Youssef Seif: 3 digit route 4 digit section