## Slide 1: 23-3008, PID 117955, FAY-435-1.52 Dispute No. 06-233008-02 Step 2
Ramp D Pavement Performance Review
Notes: Introduce purpose and panel acknowledgement.

## Slide 2: 23-3008, PID 117955, FAY-435-1.52 Dispute No. 06-233008-02 Step 2
Ramp D Pavement Performance Review
Notes: Introduce purpose and panel acknowledgement.

## Slide 3: Purpose
Evaluate Ramp D cracking
Confirm construction compliance
Review acceptance and opening process
Present engineering explanation
Notes: Set objective: explanation not accusation.

## Slide 4: Project Context
Single-lane ramp
Heavy truck channelization
High braking/turning stress
Notes: Use site photos to explain loading environment.

## Slide 5: Prescribed Pavement Section
Section prescribed and Buildable Units approved by ODOT
Notes: Emphasize contractor followed design.

## Slide 6: Construction Compliance
Approved mix
Approved placement
Approved curing
Passed acceptance testing
Opened under ODOT direction
Notes: Establish Spearin without naming it.

## Slide 7: Construction Compliance
Approved mix
Approved placement
Approved curing
Passed acceptance testing
Opened under ODOT direction
Notes: Establish Spearin without naming it.

## Slide 8: Department Causation Theory
Batch tolerances
Placement method
Workmanship
Notes: Neutral framing.

## Slide 9: Observed Distress
Mid‑panel cracking
Patterned
Post‑acceptance
Notes: Show photos only — minimal text.

## Slide 10: Concrete Variability
Variability occurred project‑wide
No spatial correlation with distress
Notes: Reference CA‑C‑1 data.

## Slide 11: Replacement Panels
Similar cracking observed
Notes: Weakens batching theory.

## Slide 12: Acceptance & Opening
Flexural strength governed opening
Opening controlled by Department
Documentation inconsistencies
Notes: Introduce early loading concept.

## Slide 13: Beam Documentation Questions
Beams cast vs break results
Break ages vs opening timing
Maturity expectations
Requested ODOT testing records
Notes: Raise uncertainty calmly.

## Slide 14: Structural Sensitivity
Thicker sections performing
10" ramp showing distress
State-wide 1L cement seminar
Notes: Use 71 ramp comparison.

## Slide 15: Engineering Mechanism
Early loading
Channelized truck stress
Mid‑panel cracking
Notes: Explain physics.

## Slide 16: System Interaction Summary
Design margin
Traffic concentration
Acceptance timing
Material behavior
Notes: Tie narrative together.

## Slide 17: Requested Path Forward
Collaborative evaluation
Targeted repair
Avoid unnecessary removal
Shared technical review
Please consider causes for next steps
What is the purpose:
  Determine Cause?
  Assign $$$ fault?
Notes: Signal reasonableness.