## Ticket Breakdown
233008 FAY Ramp D
PLACEMENT DATE: 8/15/2024
Cracking Locations | *According to Cracked Panels Legend
None
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag | % Slag | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag | Cumulative Cementitious
2024-08-15 | C750291P1A | 459478 | 1299 | 405 | 1196 | 395 | 169 |  | 13879 | 4271 | 12576 | 3950 | 1690 | 232 | 10 | 13780 | 0.5 | 4220 | 0.5 | 12510 | 3 | 3920 | 1705 | 30.31% | 233 | -0.7133% | -1.194% | -0.5248% | 99.3% | -0.7595% | 0.8876% | -0.266%
2024-08-15 | C750291P1A | 459482 | 1299 | 405 | 1196 | 395 | 169 |  | 13879 | 4271 | 12576 | 3950 | 1690 | 232 | 10 | 13760 | 0.5 | 4250 | 0.5 | 12530 | 3 | 3930 | 1815 | 31.59% | 233 | -0.8574% | -0.4917% | -0.3658% | 99.39% | -0.5063% | 7.396% | 1.862%
2024-08-15 | C750291P1A | 459485 | 1299 | 405 | 1196 | 395 | 169 |  | 13879 | 4271 | 12576 | 3950 | 1690 | 232 | 10 | 13840 | 0.5 | 4210 | 0.5 | 12520 | 3 | 3920 | 1720 | 30.5% | 234 | -0.281% | -1.428% | -0.4453% | 99.49% | -0.7595% | 1.775% | 0%
2024-08-15 | C750291P1A | 459488 | 1299 | 405 | 1196 | 395 | 169 |  | 13879 | 4271 | 12576 | 3950 | 1690 | 232 | 10 | 13750 | 0.5 | 4270 | 0.5 | 12540 | 3 | 3915 | 1805 | 31.56% | 234 | -0.9295% | -0.02341% | -0.2863% | 99.46% | -0.8861% | 6.805% | 1.418%
2024-08-15 | C750291P1A | 459489 | 1299 | 405 | 1196 | 395 | 169 |  | 13879 | 4271 | 12576 | 3950 | 1690 | 232 | 10 | 13770 | 0.5 | 4230 | 0.5 | 12470 | 3 | 3925 | 1810 | 31.56% | 233 | -0.7854% | -0.96% | -0.8429% | 99.17% | -0.6329% | 7.101% | 1.684%
2024-08-15 | C750291P1A | 459490 | 1299 | 405 | 1196 | 395 | 169 |  | 13879 | 4271 | 12576 | 3950 | 1690 | 232 | 10 | 13770 | 0.5 | 4210 | 0.5 | 12500 | 3 | 3935 | 1785 | 31.21% | 234 | -0.7854% | -1.428% | -0.6043% | 99.2% | -0.3797% | 5.621% | 1.418%
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag | % Slag | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag | Cumulative Cementitious
2024-08-20 | C750291P1A | 459520 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12576 | 3950 | 1690 | 238 | 10 | 13830 | 0.5 | 4210 | 0.5 | 12530 | 3 | 3915 | 1740 | 30.77% | 239 | -0.3531% | -1.428% | -0.3658% | 99.49% | -0.8861% | 2.959% | 0.266%
2024-08-20 | C750291P1A | 459522 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 230 | 10 | 13850 | 0.5 | 4260 | 0.5 | 12550 | 3.5 | 3940 | 1670 | 29.77% | 233 | -0.2089% | -0.2576% | -0.6885% | 99.59% | -0.2532% | -1.183% | -0.5319%
2024-08-20 | C750291P1A | 459523 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 245 | 10 | 13840 | 0.5 | 4220 | 0.5 | 12570 | 3.5 | 3920 | 1745 | 30.8% | 247 | -0.281% | -1.194% | -0.5302% | 99.49% | -0.7595% | 3.254% | 0.4433%
2024-08-20 | C750291P1A | 459524 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 241 | 10 | 13800 | 0.5 | 4210 | 0.5 | 12620 | 3.5 | 3935 | 1740 | 30.66% | 244 | -0.5692% | -1.428% | -0.1345% | 99.49% | -0.3797% | 2.959% | 0.6206%
2024-08-20 | C750291P1A | 459526 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 241 | 10 | 13770 | 0.5 | 4250 | 0.5 | 12600 | 3.5 | 3925 | 1760 | 30.96% | 244 | -0.7854% | -0.4917% | -0.2928% | 99.46% | -0.6329% | 4.142% | 0.7979%
2024-08-20 | C750291P1A | 459527 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 241 | 10 | 13760 | 0.5 | 4260 | 0.5 | 12580 | 3.5 | 3945 | 1720 | 30.36% | 244 | -0.8574% | -0.2576% | -0.4511% | 99.39% | -0.1266% | 1.775% | 0.4433%
2024-08-20 | C750291P1A | 459528 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 252 | 10 | 13750 | 0.5 | 4260 | 0.5 | 12460 | 3.5 | 3920 | 1685 | 30.06% | 254 | -0.9295% | -0.2576% | -1.401% | 98.97% | -0.7595% | -0.2959% | -0.6206%
2024-08-20 | C750291P1A | 459529 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 247 | 10 | 13780 | 0.5 | 4250 | 0.5 | 12590 | 3.5 | 3925 | 1770 | 31.08% | 249 | -0.7133% | -0.4917% | -0.3719% | 99.46% | -0.6329% | 4.734% | 0.9752%
2024-08-20 | C750291P1A | 459531 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 247 | 10 | 13770 | 0.5 | 4250 | 0.5 | 12610 | 3.5 | 3920 | 1775 | 31.17% | 249 | -0.7854% | -0.4917% | -0.2137% | 99.49% | -0.7595% | 5.03% | 0.9752%
2024-08-20 | C750291P1A | 459532 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 241 | 10 | 13920 | 0.5 | 4240 | 0.5 | 12590 | 3.5 | 3925 | 1750 | 30.84% | 244 | 0.2954% | -0.7258% | -0.3719% | 99.88% | -0.6329% | 3.55% | 0.6206%
2024-08-20 | C750291P1A | 459534 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 241 | 10 | 13760 | 0.5 | 4210 | 0.5 | 12470 | 3.5 | 3940 | 1710 | 30.27% | 244 | -0.8574% | -1.428% | -1.322% | 98.87% | -0.2532% | 1.183% | 0.1773%
2024-08-20 | C750291P1A | 459535 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 241 | 10 | 13870 | 0.5 | 4220 | 0.5 | 12640 | 3.5 | 3950 | 1815 | 31.48% | 244 | -0.06485% | -1.194% | 0.02374% | 99.81% | 0% | 7.396% | 2.216%
2024-08-20 | C750291P1A | 459536 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 236 | 10 | 13820 | 0.5 | 4250 | 0.5 | 12650 | 3.5 | 3925 | 1685 | 30.04% | 238 | -0.4251% | -0.4917% | 0.1029% | 99.78% | -0.6329% | -0.2959% | -0.5319%
2024-08-20 | C750291P1A | 459537 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 241 | 10 | 13770 | 0.5 | 4260 | 0.5 | 12610 | 3.5 | 3965 | 1670 | 29.64% | 244 | -0.7854% | -0.2576% | -0.2137% | 99.52% | 0.3797% | -1.183% | -0.08865%
2024-08-20 | C750291P1A | 459538 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 239 | 10 | 13770 | 0.5 | 4270 | 0.5 | 12600 | 3.5 | 3930 | 1775 | 31.11% | 242 | -0.7854% | -0.02341% | -0.2928% | 99.52% | -0.5063% | 5.03% | 1.152%
2024-08-20 | C750291P1A | 459541 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 239 | 10 | 13780 | 0.5 | 4230 | 0.5 | 12570 | 3.5 | 3935 | 1825 | 31.68% | 242 | -0.7133% | -0.96% | -0.5302% | 99.33% | -0.3797% | 7.988% | 2.128%
2024-08-20 | C750291P1A | 459542 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 239 | 10 | 13760 | 0.5 | 4210 | 0.5 | 12580 | 3.5 | 3925 | 1780 | 31.2% | 242 | -0.8574% | -1.428% | -0.4511% | 99.23% | -0.6329% | 5.325% | 1.152%
2024-08-20 | C750291P1A | 459543 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 239 | 10 | 13750 | 0.5 | 4220 | 0.5 | 12620 | 3.5 | 3935 | 1640 | 29.42% | 242 | -0.9295% | -1.194% | -0.1345% | 99.36% | -0.3797% | -2.959% | -1.152%
2024-08-20 | C750291P1A | 459544 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 241 | 10 | 13750 | 0.5 | 4250 | 0.5 | 12610 | 3.5 | 3920 | 1650 | 29.62% | 244 | -0.9295% | -0.4917% | -0.2137% | 99.43% | -0.7595% | -2.367% | -1.241%
2024-08-20 | C750291P1A | 459545 | 1299 | 405 | 1196 | 395 | 169 | Water | 13879 | 4271 | 12637 | 3950 | 1690 | 241 | 10 | 13820 | 0.5 | 4250 | 0.5 | 12600 | 3.5 | 3930 | 1805 | 31.47% | 244 | -0.4251% | -0.4917% | -0.2928% | 99.62% | -0.5063% | 6.805% | 1.684%
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag | % Slag | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag | Cumulative Cementitious
2024-09-09 | C750291P1A | 450162 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 226 | 10 | 13780 | 0.3 | 4250 | 0.3 | 12670 | 3.5 | 3925 | 1780 | 31.2% | 228 | -0.5126% | -0.3049% | 0.2611% | 99.83% | -0.6329% | 5.325% | 1.152%
2024-09-09 | C750291P1A | 450164 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 220 | 10 | 13720 | 0.3 | 4290 | 0.3 | 12540 | 3.5 | 3940 | 1805 | 31.42% | 223 | -0.9458% | 0.6334% | -0.7676% | 99.35% | -0.2532% | 6.805% | 1.862%
2024-09-09 | C750291P1A | 450170 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 220 | 10 | 13770 | 0.3 | 4310 | 0.3 | 12570 | 3.5 | 3915 | 1805 | 31.56% | 223 | -0.5848% | 1.103% | -0.5302% | 99.67% | -0.8861% | 6.805% | 1.418%
2024-09-09 | C750291P1A | 450173 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 220 | 10 | 13740 | 0.3 | 4310 | 0.3 | 12590 | 3.5 | 3920 | 1765 | 31.05% | 223 | -0.8014% | 1.103% | -0.3719% | 99.64% | -0.7595% | 4.438% | 0.7979%
2024-09-09 | C750291P1A | 450174 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 220 | 10 | 13750 | 0.3 | 4370 | 0.3 | 12570 | 3.5 | 3985 | 1775 | 30.82% | 223 | -0.7292% | 2.51% | -0.5302% | 99.8% | 0.8861% | 5.03% | 2.128%
2024-09-09 | C750291P1A | 450178 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 220 | 10 | 13770 | 0.3 | 4240 | 0.3 | 12570 | 3.5 | 3915 | 1645 | 29.59% | 223 | -0.5848% | -0.5395% | -0.5302% | 99.44% | -0.8861% | -2.663% | -1.418%
2024-09-09 | C750291P1A | 450180 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 220 | 10 | 13730 | 0.3 | 4310 | 0.3 | 12590 | 3.5 | 3915 | 1810 | 31.62% | 223 | -0.8736% | 1.103% | -0.3719% | 99.61% | -0.8861% | 7.101% | 1.507%
2024-09-09 | C750291P1A | 450183 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 209 | 10 | [13 empty] | 0% |  |  |  | No Information on Ticket
2024-09-09 | C750291P1A | 450185 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 209 | 10 | 13740 | 0.3 | 4210 | 0.3 | 12610 | 3.5 | 3940 | 1670 | 29.77% | 212 | -0.8014% | -1.243% | -0.2137% | 99.38% | -0.2532% | -1.183% | -0.5319%
2024-09-09 | C750291P1A | 450188 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13740 | 0.3 | 4220 | 0.3 | 12560 | 3.5 | 3950 | 1680 | 29.84% | 203 | -0.8014% | -1.009% | -0.6093% | 99.25% | 0% | -0.5917% | -0.1773%
2024-09-09 | C750291P1A | 450190 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13800 | 0.3 | 4270 | 0.3 | 12460 | 3.5 | 3915 | 1800 | 31.5% | 203 | -0.3682% | 0.1642% | -1.401% | 99.28% | -0.8861% | 6.509% | 1.33%
2024-09-09 | C750291P1A | 450192 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13720 | 0.3 | 4220 | 0.3 | 12610 | 3.5 | 3950 | 1815 | 31.48% | 202 | -0.9458% | -1.009% | -0.2137% | 99.35% | 0% | 7.396% | 2.216%
2024-09-09 | C750291P1A | 450193 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13770 | 0.3 | 4230 | 0.3 | 12640 | 3.5 | 3960 | 1660 | 29.54% | 203 | -0.5848% | -0.7741% | 0.02374% | 99.64% | 0.2532% | -1.775% | -0.3546%
2024-09-09 | C750291P1A | 450197 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13830 | 0.3 | 4250 | 0.3 | 12610 | 3.5 | 3920 | 1735 | 30.68% | 203 | -0.1516% | -0.3049% | -0.2137% | 99.8% | -0.7595% | 2.663% | 0.266%
2024-09-09 | C750291P1A | 450200 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13720 | 0.3 | 4240 | 0.3 | 12570 | 3.5 | 3935 | 1775 | 31.09% | 203 | -0.9458% | -0.5395% | -0.5302% | 99.28% | -0.3797% | 5.03% | 1.241%
2024-09-09 | C750291P1A | 450202 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13790 | 0.3 | 4210 | 0.3 | 12630 | 3.5 | 3970 | 1755 | 30.66% | 203 | -0.4404% | -1.243% | -0.05539% | 99.61% | 0.5063% | 3.846% | 1.507%
2024-09-09 | C750291P1A | 450204 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13740 | 0.3 | 4240 | 0.3 | 12630 | 3.5 | 3950 | 1775 | 31% | 203 | -0.8014% | -0.5395% | -0.05539% | 99.54% | 0% | 5.03% | 1.507%
2024-09-09 | C750291P1A | 450206 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13750 | 0.3 | 4240 | 0.3 | 12560 | 3.5 | 3965 | 1770 | 30.86% | 203 | -0.7292% | -0.5395% | -0.6093% | 99.35% | 0.3797% | 4.734% | 1.684%
2024-09-09 | C750291P1A | 450208 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 193 | 10 | 13790 | 0.3 | 4230 | 0.3 | 12600 | 3.5 | 3970 | 1750 | 30.59% | 195 | -0.4404% | -0.7741% | -0.2928% | 99.57% | 0.5063% | 3.55% | 1.418%
2024-09-09 | C750291P1A | 450212 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13800 | 0.3 | 4220 | 0.3 | 12630 | 3.5 | 3925 | 1755 | 30.9% | 201 | -0.3682% | -1.009% | -0.05539% | 99.67% | -0.6329% | 3.846% | 0.7092%
2024-09-09 | C750291P1A | 450217 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 193 | 10 | 13800 | 0.3 | 4250 | 0.3 | 12600 | 3.5 | 3935 | 1650 | 29.54% | 194 | -0.3682% | -0.3049% | -0.2928% | 99.67% | -0.3797% | -2.367% | -0.9752%
2024-09-09 | C750291P1A | 450220 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13750 | 0.3 | 4240 | 0.3 | 12530 | 3.5 | 3945 | 1795 | 31.27% | 200 | -0.7292% | -0.5395% | -0.8467% | 99.25% | -0.1266% | 6.213% | 1.773%
2024-09-09 | C750291P1A | 450223 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13730 | 0.3 | 4240 | 0.3 | 12590 | 3.5 | 3915 | 1765 | 31.07% | 201 | -0.8736% | -0.5395% | -0.3719% | 99.38% | -0.8861% | 4.438% | 0.7092%
2024-09-09 | C750291P1A | 450225 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13820 | 0.3 | 4220 | 0.3 | 12590 | 3.5 | 3915 | 1795 | 31.44% | 201 | -0.2238% | -1.009% | -0.3719% | 99.61% | -0.8861% | 6.213% | 1.241%
2024-09-09 | C750291P1A | 450228 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13750 | 0.3 | 4250 | 0.3 | 12620 | 3.5 | 3935 | 1790 | 31.27% | 201 | -0.7292% | -0.3049% | -0.1345% | 99.57% | -0.3797% | 5.917% | 1.507%
2024-09-09 | C750291P1A | 450230 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13760 | 0.3 | 4200 | 0.3 | 12610 | 3.5 | 3915 | 1615 | 29.2% | 201 | -0.657% | -1.478% | -0.2137% | 99.41% | -0.8861% | -4.438% | -1.95%
2024-09-09 | C750291P1A | 450231 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13730 | 0.3 | 4210 | 0.3 | 12460 | 3.5 | 3940 | 1750 | 30.76% | 200 | -0.8736% | -1.243% | -1.401% | 98.86% | -0.2532% | 3.55% | 0.8865%
2024-09-09 | C750291P1A | 450233 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 193 | 10 | 13720 | 0.3 | 4210 | 0.3 | 12580 | 3.5 | 3965 | 1630 | 29.13% | 194 | -0.9458% | -1.243% | -0.4511% | 99.22% | 0.3797% | -3.55% | -0.7979%
2024-09-09 | C750291P1A | 450238 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 198 | 10 | 13790 | 0.3 | 4530 | 0.3 | 12590 | 3.5 | 3925 | 1805 | 31.5% | 201 | -0.4404% | 6.263% | -0.3719% | 100.5% | -0.6329% | 6.805% | 1.596%
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag | % Slag | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag | Cumulative Cementitious
2024-09-10 | C750291P1A | 450253 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 251 | 10 | 13850 | 0.2 | 4240 | 0.3 | 12540 | 3.25 | 3930 | 1725 | 30.5% | 254 | 0.08672% | -0.5395% | -0.5315% | 99.75% | -0.5063% | 2.071% | 0.266%
2024-09-10 | C750291P1A | 450256 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 251 | 10 | 13710 | 0.2 | 4250 | 0.3 | 12570 | 3.25 | 3925 | 1790 | 31.32% | 254 | -0.925% | -0.3049% | -0.2935% | 99.42% | -0.6329% | 5.917% | 1.33%
2024-09-10 | C750291P1A | 450259 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 251 | 10 | 13810 | 0.2 | 4260 | 0.3 | 12500 | 3.25 | 3915 | 1780 | 31.26% | 254 | -0.2023% | -0.07037% | -0.8487% | 99.55% | -0.8861% | 5.325% | 0.9752%
2024-09-10 | C750291P1A | 450261 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 251 | 10 | 13700 | 0.2 | 4200 | 0.3 | 12570 | 3.25 | 3925 | 1815 | 31.62% | 254 | -0.9973% | -1.478% | -0.2935% | 99.22% | -0.6329% | 7.396% | 1.773%
2024-09-10 | C750291P1A | 450264 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 251 | 10 | 13740 | 0.2 | 4230 | 0.3 | 12450 | 3.25 | 3945 | 1620 | 29.11% | 254 | -0.7082% | -0.7741% | -1.245% | 99.06% | -0.1266% | -4.142% | -1.33%
2024-09-10 | C750291P1A | 450265 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 251 | 10 | 13740 | 0.2 | 4200 | 0.3 | 12640 | 3.25 | 3930 | 1625 | 29.25% | 254 | -0.7082% | -1.478% | 0.2618% | 99.58% | -0.5063% | -3.846% | -1.507%
2024-09-10 | C750291P1A | 450267 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 251 | 10 | 13720 | 0.2 | 4210 | 0.3 | 12610 | 3.25 | 3915 | 1780 | 31.26% | 254 | -0.8527% | -1.243% | 0.0238% | 99.45% | -0.8861% | 5.325% | 0.9752%
2024-09-10 | C750291P1A | 450277 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 246 | 10 | 13700 | 0.2 | 4220 | 0.3 | 12520 | 3.25 | 3925 | 1775 | 31.14% | 248 | -0.9973% | -1.009% | -0.6901% | 99.13% | -0.6329% | 5.03% | 1.064%
2024-09-10 | C750291P1A | 450280 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 240 | 10 | 13790 | 0.2 | 4260 | 0.3 | 12510 | 3.25 | 3935 | 1765 | 30.96% | 243 | -0.3469% | -0.07037% | -0.7694% | 99.52% | -0.3797% | 4.438% | 1.064%
2024-09-10 | C750291P1A | 450284 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 251 | 10 | 13700 | 0.2 | 4220 | 0.3 | 12530 | 3.25 | 3915 | 1760 | 31.01% | 254 | -0.9973% | -1.009% | -0.6108% | 99.16% | -0.8861% | 4.142% | 0.6206%
2024-09-10 | C750291P1A | 450286 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 240 | 10 | 13730 | 0.2 | 4310 | 3.25 | 12580 | 3.25 | 3930 | 1780 | 31.17% | 243 | -0.7805% | 1.103% | -0.2142% | 99.71% | -0.5063% | 5.325% | 1.241%
2024-09-10 | C750291P1A | 450290 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 240 | 10 | 13790 | 0.2 | 4230 | 0.3 | 12630 | 3.25 | 3935 | 1775 | 31.09% | 243 | -0.3469% | -0.7741% | 0.1824% | 99.81% | -0.3797% | 5.03% | 1.241%
2024-09-10 | C750291P1A | 450292 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 240 | 10 | 13900 | 0.2 | 4250 | 0.3 | 12640 | 3.25 | 3925 | 1765 | 31.02% | 243 | 0.448% | -0.3049% | 0.2618% | 100.3% | -0.6329% | 4.438% | 0.8865%
2024-09-10 | C750291P1A | 450294 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 240 | 10 | 13700 | 0.2 | 4230 | 0.3 | 12530 | 3.25 | 3935 | 1790 | 31.27% | 243 | -0.9973% | -0.7741% | -0.6108% | 99.19% | -0.3797% | 5.917% | 1.507%
2024-09-10 | C750291P1A | 450296 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 235 | 10 | 13700 | 0.2 | 4200 | 0.3 | 12530 | 3.25 | 3945 | 1820 | 31.57% | 237 | -0.9973% | -1.478% | -0.6108% | 99.09% | -0.1266% | 7.692% | 2.216%
2024-09-10 | C750291P1A | 450298 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 235 | 10 | 13770 | 0.2 | 4320 | 0.3 | 12460 | 3.25 | 3930 | 1765 | 30.99% | 237 | -0.4914% | 1.337% | -1.166% | 99.49% | -0.5063% | 4.438% | 0.9752%
2024-09-10 | C750291P1A | 450302 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 229 | 10 | 13850 | 0.2 | 4450 | 0.3 | 12650 | 3.25 | 3920 | 1730 | 30.62% | 232 | 0.08672% | 4.387% | 0.3411% | 100.8% | -0.7595% | 2.367% | 0.1773%
2024-09-10 | C750291P1A | 450304 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 229 | 10 | 13740 | 0.2 | 4430 | 0.3 | 12540 | 3.25 | 3950 | 1815 | 31.48% | 232 | -0.7082% | 3.917% | -0.5315% | 100% | 0% | 7.396% | 2.216%
2024-09-10 | C750291P1A | 450306 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 225 | 10 | 13760 | 0.2 | 4220 | 0.3 | 12560 | 3.25 | 3980 | 1640 | 29.18% | 227 | -0.5637% | -1.009% | -0.3728% | 99.45% | 0.7595% | -2.959% | -0.3546%
2024-09-10 | C750291P1A | 450308 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 229 | 10 | 13740 | 0.2 | 4230 | 0.3 | 12530 | 3.25 | 3935 | 1755 | 30.84% | 231 | -0.7082% | -0.7741% | -0.6108% | 99.32% | -0.3797% | 3.846% | 0.8865%
2024-09-10 | C750291P1A | 450309 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 229 | 10 | 13760 | 0.2 | 4270 | 0.3 | 12510 | 3.25 | 3935 | 1655 | 29.61% | 231 | -0.5637% | 0.1642% | -0.7694% | 99.45% | -0.3797% | -2.071% | -0.8865%
2024-09-10 | C750291P1A | 450311 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 229 | 10 | 13710 | 0.2 | 4230 | 0.3 | 12640 | 3.25 | 3940 | 1685 | 29.96% | 231 | -0.925% | -0.7741% | 0.2618% | 99.58% | -0.2532% | -0.2959% | -0.266%
2024-09-10 | C750291P1A | 450320 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 235 | 10 | 13780 | 0.2 | 4210 | 0.3 | 12500 | 3.25 | 3915 | 1660 | 29.78% | 237 | -0.4191% | -1.243% | -0.8487% | 99.29% | -0.8861% | -1.775% | -1.152%
2024-09-10 | C750291P1A | 450323 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4263 | 12607 | 3950 | 1690 | 229 | 10 | 13800 | 0.2 | 4220 | 0.3 | 12560 | 3.25 | 3945 | 1680 | 29.87% | 231 | -0.2746% | -1.009% | -0.3728% | 99.58% | -0.1266% | -0.5917% | -0.266%
PLACEMENT DATE: 9/11/2024
Cracking Locations | *According to Cracked Panels Legend
None
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag | % Slag | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag
2025-09-11 | C75029MS1B | 8972 | 1606 |  | 1082 | 800 | Slag |  | 16350 |  | 11171 | 8000 |  | 346 | 10 | 16310 | -0.75 |  |  | 11100 | 1 | 7935 |  |  | 346 | -0.2446% |  | -0.6356% | 99.6% | -0.8125% |  |  | No ticket display # used ticket ID
2025-09-11 | C75029MS1B | 969324 | 1606 |  | 1082 | 800 | Slag |  | 16350 |  | 11171 | 8000 |  | 346 | 10 | 16290 | -0.75 |  |  | 11010 | 1 | 7980 |  |  | 347 | -0.367% |  | -1.441% | 99.2% | -0.25%
2025-09-11 | C75029MS1B | 8974 | 1606 |  | 1082 | 800 | Slag |  | 16350 |  | 11143 | 8000 |  | 355 | 10 | 16280 | -1 |  |  | 11140 | 0.75 | 7945 |  |  | 354 | -0.4281% |  | -0.02692% | 99.73% | -0.6875% |  |  | No ticket display # used ticket ID
PLACEMENT DATE: 9/12/2024
Cracking Locations | *According to Cracked Panels Legend
None
No section on Placement Dates Map with 9/12
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag | % Slag | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag | Cumulative Cementitious
2024-09-12 | C750291P1A | 450450 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4259 | 12637 | 3950 | 1690 | 253 | 10 | 13730 | 0.2 | 4230 | 0.2 | 12550 | 3.5 | 3935 | 1785 | 31.21% | 256 | -0.7805% | -0.6809% | -0.6885% | 99.27% | -0.3797% | 5.621% | 1.418%
2024-09-12 | C750291P1A | 450453 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4259 | 12637 | 3950 | 1690 | 248 | 10 | 13780 | 0.2 | 4230 | 0.2 | 12640 | 3.5 | 3930 | 1770 | 31.05% | 250 | -0.4191% | -0.6809% | 0.02374% | 99.73% | -0.5063% | 4.734% | 1.064%
2024-09-12 | C750291P1A | 450460 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4259 | 12637 | 3950 | 1690 | 264 | 10 | 13740 | 0.2 | 4230 | 0.2 | 12590 | 3.5 | 3925 | 1690 | 30.1% | 266 | -0.7082% | -0.6809% | -0.3719% | 99.43% | -0.6329% | 0% | -0.4433%
2024-09-12 | C750291P1A | 450463 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4259 | 12637 | 3950 | 1690 | 242 | 10 | 13720 | 0.2 | 4240 | 0.2 | 12560 | 3.5 | 3920 | 1660 | 29.75% | 244 | -0.8527% | -0.4461% | -0.6093% | 99.3% | -0.7595% | -1.775% | -1.064%
2024-09-12 | C750291P1A | 450471 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4259 | 12637 | 3950 | 1690 | 242 | 10 | 13720 | 0.2 | 4200 | 0.2 | 12490 | 3.5 | 3935 | 1755 | 30.84% | 244 | -0.8527% | -1.385% | -1.163% | 98.95% | -0.3797% | 3.846% | 0.8865%
2024-09-12 | C750291P1A | 450474 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4259 | 12637 | 3950 | 1690 | 242 | 10 | 13770 | 0.2 | 4200 | 0.2 | 12630 | 3.5 | 3925 | 1635 | 29.41% | 244 | -0.4914% | -1.385% | -0.05539% | 99.56% | -0.6329% | -3.254% | -1.418%
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag |  | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag
2025-09-12 | C75029MS1B | 969327 | 1299 | 405 | 1196 | 395 | 169 |  | 16350 |  | 11143 | 8000 |  | 355 | 10 | 16280 | -1 |  |  | 11140 | 0.75 | 8055 |  |  | 355 | -0.4281% |  | -0.02692% | 99.73% | 0.6875%
2025-09-12 | C75029MS1B | 969330 | 1299 | 405 | 1196 | 395 | 169 |  | 16350 |  | 11143 | 8000 |  | 355 | 10 | 16280 | -1 |  |  | 11150 | 0.75 | 7945 |  |  | 354 | -0.4281% |  | 0.06282% | 99.77% | -0.6875%
2025-09-12 | C75029MS1B | 969331 | 1299 | 405 | 1196 | 395 | 169 |  | 11445 |  | 7800 | 5600 |  | 248 | 7 | 11390 | -1 |  |  | 7690 | 0.75 | 5565 |  |  | 248 | -0.4806% |  | -1.41% | 99.14% | -0.625%
PLACEMENT DATE: 9/15/2024
Cracking Locations | *According to Cracked Panels Legend
None
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag |  | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag
2025-09-15 | C75029MS1B | 969411 | 1606 |  | 1082 | 800 | Slag |  | 16350 |  | 11143 | 8000 |  | 335 | 10 | 16280 | -1 |  |  | 11050 | 0.75 | 7985 |  |  | 335 | -0.4281% |  | -0.8346% | 99.41% | -0.1875%
2025-09-15 | C75029MS1B | 969417 | 1606 |  | 1082 | 800 | Slag |  | 6540 |  | 4457 | 3200 |  | 135 | 4 | 6560 | -1 |  |  | 4460 | 0.75 | 3215 |  |  | 135 | 0.3058% |  | 0.06731% | 100.2% | 0.4688%
PLACEMENT DATE: 9/16/2024
Cracking Locations | *According to Cracked Panels Legend
Location | Group #
Left Shoulder | 3
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag |  | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag
2024-09-16 | C75029MS1B | 450582 | 1606 |  | 1082 | 800 |  |  | 16743 |  | 11447 | 8000 |  | 264 | 10 | 16650 | 0.2 |  |  | 11410 | 3.5 | 7975 |  |  | 265 | -0.5555% |  | -0.3232% | 99.54% | -0.3125%
2024-09-16 | C75029MS1B | 450584 | 1606 |  | 1082 | 800 |  |  | 16743 |  | 11447 | 8000 |  | 264 | 10 | 16600 | 0.2 |  |  | 11370 | 3.5 | 7965 |  |  | 265 | -0.8541% |  | -0.6727% | 99.22% | -0.4375%
2024-09-16 | C75029MS1B | 450587 | 1606 |  | 1082 | 800 |  |  | 16743 |  | 11447 | 8000 |  | 275 | 10 | 16590 | 0.2 |  |  | 11350 | 3.5 | 7920 |  |  | 276 | -0.9138% |  | -0.8474% | 99.11% | -1%
2024-09-16 | C75029MS1B | 450590 | 1606 |  | 1082 | 800 |  |  | 16743 |  | 11447 | 8000 |  | 264 | 10 | 16670 | 0.2 |  |  | 11380 | 3.5 | 7975 |  |  | 265 | -0.436% |  | -0.5853% | 99.5% | -0.3125%
2024-09-16 | C75029MS1B | 450592 | 1606 |  | 1082 | 800 |  |  | 16743 |  | 11447 | 8000 |  | 264 | 10 | 16700 | 0.2 |  |  | 11310 | 3.5 | 7965 |  |  | 265 | -0.2568% |  | -1.197% | 99.36% | -0.4375%
2024-09-16 | C75029MS1B | 450600 | 1606 |  | 1082 | 800 |  |  | 11720 |  | 8013 | 5600 |  | 181 | 7 | 11650 | 0.2 |  |  | 7930 | 3.5 | 5585 |  |  | 182 | -0.5973% |  | -1.036% | 99.22% | -0.2679%
PLACEMENT DATE: 9/17/2024
Cracking Locations | *According to Cracked Panels Legend
None
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag |  | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag | Cumulative Cementitious
2024-09-17 | C750291P1A | 450611 | 1299 | 405 | 1196 | 395 | 169 | Water | 13838 | 4259 | 12637 | 3950 | 1690 | 222 | 10 | 13740 | 0.2 | 4200 | 0.2 | 12640 | 3.5 | 3970 | 1705 | 30.04% | 223 | -0.7082% | -1.385% | 0.02374% | 99.5% | 0.5063% | 0.8876% | 0.6206%
2024-09-17 | C750291P1A | 450613 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 210 | 10 | 13760 | 0.3 | 4220 | 0.3 | 12610 | 3.5 | 3980 | 1670 | 29.56% | 211 | -0.657% | -1.009% | -0.2137% | 99.48% | 0.7595% | -1.183% | 0.1773%
2024-09-17 | C750291P1A | 450618 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 210 | 10 | 13770 | 0.3 | 4210 | 0.3 | 12640 | 3.5 | 3965 | 1690 | 29.89% | 212 | -0.5848% | -1.243% | 0.02374% | 99.57% | 0.3797% | 0% | 0.266%
2024-09-17 | C750291P1A | 450620 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 210 | 10 | 13790 | 0.3 | 4260 | 0.3 | 12580 | 3.5 | 3955 | 1680 | 29.81% | 211 | -0.4404% | -0.07037% | -0.4511% | 99.61% | 0.1266% | -0.5917% | -0.08865%
2024-09-17 | C750291P1A | 450625 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 208 | 10 | 13920 | 0.3 | 4250 | 0.3 | 12610 | 3.5 | 3950 | 1795 | 31.24% | 210 | 0.4982% | -0.3049% | -0.2137% | 100.1% | 0% | 6.213% | 1.862%
2024-09-17 | C750291P1A | 450627 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 210 | 10 | 13750 | 0.3 | 4200 | 0.3 | 12650 | 3.5 | 3935 | 1740 | 30.66% | 212 | -0.7292% | -1.478% | 0.1029% | 99.51% | -0.3797% | 2.959% | 0.6206%
2024-09-17 | C750291P1A | 450633 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 210 | 10 | 13750 | 0.3 | 4230 | 0.3 | 12600 | 3.5 | 3935 | 1795 | 31.33% | 213 | -0.7292% | -0.7741% | -0.2928% | 99.44% | -0.3797% | 6.213% | 1.596%
2024-09-17 | C750291P1A | 450635 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 210 | 10 | 13730 | 0.3 | 4230 | 0.3 | 12630 | 3.5 | 3940 | 1820 | 31.6% | 211 | -0.8736% | -0.7741% | -0.05539% | 99.48% | -0.2532% | 7.692% | 2.128%
2024-09-17 | C750291P1A | 450640 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 210 | 10 | 13750 | 0.3 | 4200 | 0.3 | 12640 | 3.5 | 3995 | 1815 | 31.24% | 212 | -0.7292% | -1.478% | 0.02374% | 99.48% | 1.139% | 7.396% | 3.014%
2024-09-17 | C750291P1A | 450642 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 199 | 10 | 13720 | 0.3 | 4240 | 0.3 | 12590 | 3.5 | 3965 | 1765 | 30.8% | 201 | -0.9458% | -0.5395% | -0.3719% | 99.35% | 0.3797% | 4.438% | 1.596%
2024-09-17 | C750291P1A | 450645 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 199 | 10 | 13750 | 0.3 | 4230 | 0.3 | 12590 | 3.5 | 3925 | 1770 | 31.08% | 201 | -0.7292% | -0.7741% | -0.3719% | 99.41% | -0.6329% | 4.734% | 0.9752%
2024-09-17 | C750291P1A | 450648 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 193 | 10 | 13790 | 0.3 | 4240 | 0.3 | 12540 | 3.5 | 3935 | 1660 | 29.67% | 196 | -0.4404% | -0.5395% | -0.7676% | 99.41% | -0.3797% | -1.775% | -0.7979%
2024-09-17 | C750291P1A | 450651 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 193 | 10 | 13740 | 0.3 | 4200 | 0.3 | 12600 | 3.5 | 3955 | 1665 | 29.63% | 196 | -0.8014% | -1.478% | -0.2928% | 99.31% | 0.1266% | -1.479% | -0.3546%
2024-09-17 | C750291P1A | 450655 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 193 | 10 | 13730 | 0.3 | 4240 | 0.3 | 12630 | 3.5 | 3940 | 1710 | 30.27% | 189 | -0.8736% | -0.5395% | -0.05539% | 99.51% | -0.2532% | 1.183% | 0.1773%
2024-09-17 | C750291P1A | 450659 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 193 | 10 | 13720 | 0.3 | 4250 | 0.3 | 12620 | 3.5 | 3950 | 1695 | 30.03% | 196 | -0.9458% | -0.3049% | -0.1345% | 99.48% | 0% | 0.2959% | 0.08865%
2024-09-17 | C750291P1A | 450661 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 199 | 10 | 13760 | 0.3 | 4230 | 0.3 | 12620 | 3.5 | 3955 | 1670 | 29.69% | 200 | -0.657% | -0.7741% | -0.1345% | 99.54% | 0.1266% | -1.183% | -0.266%
2024-09-17 | C750291P1A | 450667 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 204 | 10 | 13800 | 0.3 | 4240 | 0.3 | 12560 | 3.5 | 3915 | 1695 | 30.21% | 206 | -0.3682% | -0.5395% | -0.6093% | 99.51% | -0.8861% | 0.2959% | -0.5319%
2024-09-17 | C750291P1A | 450671 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 204 | 10 | 13740 | 0.3 | 4230 | 0.3 | 12600 | 3.5 | 3935 | 1785 | 31.21% | 211 | -0.8014% | -0.7741% | -0.2928% | 99.41% | -0.3797% | 5.621% | 1.418%
PLACEMENT DATE: 9/19/2024
Cracking Locations | *According to Cracked Panels Legend
None
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag |  | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag | Cumulative Cementitious
2024-09-19 | C750291P1A | 450752 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 248 | 10 | 13770 | 0.3 | 4260 | 0.3 | 12630 | 3.5 | 3950 | 1775 | 31% | 249 | -0.5848% | -0.07037% | -0.05539% | 99.7% | 0% | 5.03% | 1.507%
2024-09-19 | C750291P1A | 450758 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4263 | 12637 | 3950 | 1690 | 257 | 10 | 13720 | 0.3 | 4250 | 0.3 | 12570 | 3.5 | 3940 | 1635 | 29.33% | 260 | -0.9458% | -0.3049% | -0.5302% | 99.31% | -0.2532% | -3.254% | -1.152%
2024-09-19 | C750291P1A | 450771 | 1299 | 405 | 1196 | 395 | 169 | Water | 4155 | 1279 | 3791 | 1185 | 507 | 57 | 3 | 4230 | 0.3 | 1300 | 0.3 | 3760 | 3.5 | 1220 | 530 | 30.29% | 60 | 1.805% | 1.642% | -0.8177% | 100.7% | 2.954% | 4.536% | 3.428%
PLACEMENT DATE: 9/20/2024
Cracking Locations | *According to Cracked Panels Legend
Location | Group #
Right Shoulder | 1
Right Shoulder | 2
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag |  | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag | Cumulative Cementitious
2024-09-20 | C750291P1A | 450811 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4284 | 12637 | 3950 | 1690 | 238 | 10 | 13730 | 0.3 | 4290 | 0.8 | 12620 | 3.5 | 3935 | 1795 | 31.33% | 239 | -0.8736% | 0.1401% | -0.1345% | 99.57% | -0.3797% | 6.213% | 1.596%
2024-09-20 | C750291P1A | 450813 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4284 | 12637 | 3950 | 1690 | 238 | 10 | 13730 | 0.3 | 4230 | 0.8 | 12610 | 3.5 | 3920 | 1635 | 29.43% | 239 | -0.8736% | -1.261% | -0.2137% | 99.34% | -0.7595% | -3.254% | -1.507%
2024-09-20 | C750291P1A | 450814 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4284 | 12637 | 3950 | 1690 | 238 | 10 | 13790 | 0.3 | 4240 | 0.8 | 12610 | 3.5 | 3935 | 1640 | 29.42% | 239 | -0.4404% | -1.027% | -0.2137% | 99.57% | -0.3797% | -2.959% | -1.152%
2024-09-20 | C750291P1A | 450818 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4284 | 12637 | 3950 | 1690 | 238 | 10 | 13780 | 0.3 | 4280 | 0.8 | 12590 | 3.5 | 3925 | 1810 | 31.56% | 239 | -0.5126% | -0.09337% | -0.3719% | 99.6% | -0.6329% | 7.101% | 1.684%
2024-09-20 | C750291P1A | 450820 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4284 | 12637 | 3950 | 1690 | 260 | 10 | 13750 | 0.3 | 4240 | 0.8 | 12610 | 3.5 | 3915 | 1800 | 31.5% | 240 | -0.7292% | -1.027% | -0.2137% | 99.44% | -0.8861% | 6.509% | 1.33%
2024-09-20 | C750291P1A | 450824 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4284 | 12637 | 3950 | 1690 | 260 | 10 | 13720 | 0.3 | 4220 | 0.8 | 12620 | 3.5 | 4015 | 1645 | 29.06% | 241 | -0.9458% | -1.494% | -0.1345% | 99.31% | 1.646% | -2.663% | 0.3546%
2024-09-20 | C750291P1A | 450827 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4284 | 12637 | 3950 | 1690 | 238 | 10 | 13760 | 0.3 | 4220 | 0.8 | 12590 | 3.5 | 3945 | 1670 | 29.74% | 239 | -0.657% | -1.494% | -0.3719% | 99.34% | -0.1266% | -1.183% | -0.4433%
2024-09-20 | C750291P1A | 450830 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4284 | 12637 | 3950 | 1690 | 238 | 10 | 13730 | 0.3 | 4230 | 0.8 | 12590 | 3.5 | 3945 | 1755 | 30.79% | 240 | -0.8736% | -1.261% | -0.3719% | 99.28% | -0.1266% | 3.846% | 1.064%
2024-09-20 | C750291P1A | 450834 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4284 | 12637 | 3950 | 1690 | 238 | 10 | 13750 | 0.3 | 4250 | 0.8 | 12590 | 3.5 | 3955 | 1680 | 29.81% | 239 | -0.7292% | -0.7937% | -0.3719% | 99.41% | 0.1266% | -0.5917% | -0.08865%
2024-09-20 | C750291P1A | 450836 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4284 | 12637 | 3950 | 1690 | 238 | 10 | 13760 | 0.3 | 4260 | 0.8 | 12600 | 3.5 | 3905 | 1760 | 31.07% | 239 | -0.657% | -0.5602% | -0.2928% | 99.51% | -1.139% | 4.142% | 0.4433%
2024-09-20 | C750291P1A | 450837 | 1299 | 405 | 1196 | 395 | 169 | Water | 13851 | 4284 | 12637 | 3950 | 1690 | 238 | 10 | 13760 | 0.3 | 4270 | 0.8 | 12550 | 3.5 | 3930 | 1810 | 31.53% | 239 | -0.657% | -0.3268% | -0.6885% | 99.38% | -0.5063% | 7.101% | 1.773%
PLACEMENT DATE: 9/23/2024
Cracking Locations | *According to Cracked Panels Legend
None
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag |  | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag
2024-09-23 | C75029MS1B | 450877 | 1606 |  | 1082 | 800 | Slag |  | 16727 |  | 11447 | 8000 |  | 255 | 10 | 16650 | 0.1 |  |  | 11490 | 3.5 | 7985 |  |  | 256 | -0.4603% |  | 0.3756% | 99.88% | -0.1875%
2024-09-23 | C75029MS1B | 450880 | 1606 |  | 1082 | 800 | Slag |  | 16727 |  | 11447 | 8000 |  | 260 | 10 | 16660 | 0.1 |  |  | 11450 | 3.5 | 7995 |  |  | 263 | -0.4006% |  | 0.02621% | 99.77% | -0.0625%
2024-09-23 | C75029MS1B | 450884 | 1606 |  | 1082 | 800 | Slag |  | 16727 |  | 11447 | 8000 |  | 277 | 10 | 16690 | 0.1 |  |  | 11370 | 3.5 | 7975 |  |  | 278 | -0.2212% |  | -0.6727% | 99.6% | -0.3125%
PLACEMENT DATE: 9/25/2024
Cracking Locations | *According to Cracked Panels Legend
None
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag |  | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag
2024-09-25 | C75029MS1B | 450925 | 1606 |  | 1082 | 800 | Slag |  | 16794 |  | 11447 | 8000 |  | 247 | 10 | 16794 | 0.5 |  |  | 11370 | 3.5 | 7985 |  |  | 248 | 0% |  | -0.6727% | 99.73% | -0.1875%
2024-09-25 | C75029MS1B | 450927 | 1606 |  | 1082 | 800 | Slag |  | 16794 |  | 11447 | 8000 |  | 269 | 10 | 16720 | 0.5 |  |  | 11400 | 3.5 | 7995 |  |  | 270 | -0.4406% |  | -0.4106% | 99.57% | -0.0625%
PLACEMENT DATE: 10/1/2024
Cracking Locations | *According to Cracked Panels Legend
None
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag |  | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag
2024-10-01 | C75029MS1B | 451026 | 1606 |  | 1082 | 800 | Slag |  | 11755 |  | 8090 | 5600 |  | 148 | 7 | 11650 | 0.5 |  |  | 8010 | 4.5 | 5570 |  |  | 150 | -0.8932% |  | -0.9889% | 99.07% | -0.5357%
2024-10-01 | C75029MS1B | 451035 | 1606 |  | 1082 | 800 | Slag |  | 11755 |  | 8090 | 5600 |  | 165 | 7 | 11690 | 0.5 |  |  | 8060 | 4.5 | 5560 |  |  | 168 | -0.553% |  | -0.3708% | 99.52% | -0.7143%
2024-10-01 | C75029MS1B | 451032 | 1606 |  | 1082 | 800 | Slag |  | 11755 |  | 8090 | 5600 |  | 154 | 7 | 11640 | 0.5 |  |  | 8020 | 4.5 | 5555 |  |  | 156 | -0.9783% |  | -0.8653% | 99.07% | -0.8036%
2024-10-01 | C75029MS1B | 451029 | 1606 |  | 1082 | 800 | Slag |  | 11755 |  | 8090 | 5600 |  | 154 | 7 | 11650 | 0.5 |  |  | 7980 | 4.5 | 5590 |  |  | 156 | -0.8932% |  | -1.36% | 98.92% | -0.1786%
PLACEMENT DATE: 10/3/2024
Cracking Locations | *According to Cracked Panels Legend
None
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag |  | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag
2024-10-03 | C75029MS1B | 451109 | 1606 |  | 1082 | 800 | Slag |  | 16794 |  | 11558 | 8000 |  | 238 | 10 | 16720 | 0.5 |  |  | 11480 | 4.5 | 7990 |  |  | 241 | -0.4406% |  | -0.6749% | 99.46% | -0.125%
2024-10-03 | C75029MS1B | 451112 | 1606 |  | 1082 | 800 | Slag |  | 16794 |  | 11558 | 8000 |  | 238 | 10 | 16760 | 0.5 |  |  | 11480 | 4.5 | 7990 |  |  | 241 | -0.2025% |  | -0.6749% | 99.6% | -0.125%
2024-10-03 | C75029MS1B | 451117 | 1606 |  | 1082 | 800 | Slag |  | 16794 |  | 11558 | 8000 |  | 238 | 10 | 16710 | 0.5 |  |  | 11510 | 4.5 | 7980 |  |  | 241 | -0.5002% |  | -0.4153% | 99.53% | -0.25%
2024-10-03 | C75029MS1B | 451126 | 1606 |  | 1082 | 800 | Slag |  | 16794 |  | 11558 | 8000 |  | 244 | 10 | 16740 | 0.5 |  |  | 11510 | 4.5 | 7965 |  |  | 245 | -0.3215% |  | -0.4153% | 99.64% | -0.4375%
PLACEMENT DATE: 10/4/2024
Cracking Locations | *According to Cracked Panels Legend
None
Batch Ticket Tolerances
Information |  |  | Original JMF | [5 empty] | "Required" Adjusted for Water | [5 empty] | Batched | [10 empty] | Tolerances based on "Required"
Date | JMF | Ticket # | 57 | 8 | Sand | Cement | Slag | Water | 57 | 8 | Sand | Cement | Slag | Water | Qty | 57 | Moisture | 8 | Moisture | Sand | Moisture | Cement | Slag |  | Water (gal) | 57 | 8 | Sand | Agg | Cement | Slag
2024-10-04 | C75029MS1B | 451169 | 1606 |  | 1082 | 800 | Slag |  | 16794 |  | 11558 | 8000 |  | 227 | 10 | 16740 | 0.5 |  |  | 11500 | 4.5 | 7990 |  |  | 230 | -0.3215% |  | -0.5018% | 99.6% | -0.125%
2024-10-04 | C75029MS1B | 451171 | 1606 |  | 1082 | 800 | Slag |  | 16794 |  | 11558 | 8000 |  | 227 | 10 | 16760 | 0.5 |  |  | 11510 | 4.5 | 7980 |  |  | 230 | -0.2025% |  | -0.4153% | 99.71% | -0.25%

## Summary - Cracks & Non-Spec
| Placement Date | PCJMF | # of Tickets | Total Number of Cracks | Current Cracks after Repairs |  | Tickets Out of Spec 499.06-1 Agg. | Tickets Out of Spec 499.06-1 Cement | Tickets Out of Spec 499.06-1 Pozzolan (cumulative)
DAY 1 | 2024-08-15 | C750291P1A | 6 | 1 | 0 |  | 0 | 0 | 4
DAY 2 | 2024-08-20 | C750291P1A | 20 | 27 | 11 |  | 0 | 0 | 7
DAY 3 | 2024-09-09 | C750291P1A | 29 | 3 | 3 |  | 0 | 0 | 18
DAY 4 | 2024-09-10 | C750291P1A | 24 | 25 | 23 |  | 0 | 0 | 12
DAY 5 | 2024-09-12 | C750291P1A | 6 | 0 | 0 |  | 0 | 0 | 4
DAY 6 | 2024-09-15 | C75029MS1B | 2 | 0 | 0 |  | 0 | 0 | 0
DAY 7 | 2024-09-16 | C75029MS1B | 6 | 1 | 1 |  | 0 | 0 | 0
DAY 8 | 2024-09-17 | C750291P1A | 18 | 1 | 1 |  | 0 | 1 | 6
DAY 9 | 2024-09-19 | C750291P1A | 3 | 0 | 0 |  | 0 | 1 | 3
DAY 10 | 2024-09-20 | C750291P1A | 11 | 2 | 2 |  | 0 | 2 | 7
DAY 11 | 2024-09-23 | C75029MS1B | 3 | 0 | 0 |  | 0 | 0 | 0
DAY 12 | 2024-09-25 | C75029MS1B | 2 | 0 | 0 |  | 0 | 0 | 0
DAY 13 | 2024-10-01 | C75029MS1B | 4 | 0 | 3 |  | 0 | 0 | 0
DAY 14 | 2024-10-03 | C75029MS1B | 4 | 0 | 3 |  | 0 | 0 | 0
DAY 15 | 2024-10-04 | C75029MS1B | 2 | 0 | 0 |  | 0 | 0 | 0
DAY 16 | 2025-09-11 | C75029MS1B | 3 | 0 | 0 |  | 0 | 0 | 0
DAY 17 | 2025-09-12 | C75029MS1B | 3 | 0 | 0 |  | 0 | 0 | 0
C750291P1A | Number of Tickets | 117 | Number of cracks | 59 | 40 | Out of Spec | 0 | 4 | 61
C75029MS1B | Number of Tickets | 23 | Number of cracks | 1 | 7 | Out of Spec | 0 | 0 | 0