## Slide 1: Design-Build
Presented by: Eric Kahlig
Date: July 20, 2018
Notes: Notes:
Display this screen as participants enter the training room.
To start the training:
Direct students to turn to the first page of their Participant Workbook.
Move on to the next slide in the PowerPoint presentation.

## Slide 2: Design-Build
Course Overview and Introductions
Notes: Introduce yourself to participants; discuss your background and how you came to be teaching this course.
Ask participants to provide self-introductions. Encourage participants to share their name, background, position, and experience with DB.
Ask participants to share their expectations for the course, record these on easel pages, and post pages for reference throughout the day. (Aim to record expectations from 5 to 7 participants to control time).
Orient participants to the course materials and explain that:
You will use a PowerPoint presentation throughout the training to guide the discussion.
The participants can follow along using their Participant Workbook. The workbook contains copies of the slides, as well as supplemental background and reference information to help clarify and further emphasize the major points of the discussion.
Review the basic ground rules for the course:
  Participate
  Return from breaks on time
  Attentively listen when others talk.
  Respect the opinions and attitudes of others.
  Turn cell phone on mute.
Encourage participants to be active participants in the learning process, noting that they can obtain the maximum benefit from the course by asking and answering questions, participating in discussions and activities, and by sharing their own experiences and ideas.

## Slide 3: Course Overview
Introduction to Design-Build (DB)
Project Development
Procurement and Contracting
1
2
3
Contract Administration
4
Course Wrap-Up
5
Notes: Present the basic structure of the course, which consists of 4 parts:
The first portion of the course provides a brief overview of the DB delivery method, including its advantages and disadvantages and the characteristics that would make a project a good candidate for DB delivery.
The second part explores how the use of DB impacts the traditional project development process and highlights the importance of developing complete and thorough scoping documents.
The third part addresses procurement processes and contracting issues that are unique to DB.
The final part addresses the post-award administration of the design, construction, and closeout phases of a DB project.
Note the following:
Each part will begin and end with a review of the key learning outcomes for that particular portion of the course.
Throughout the course and at the end of each section, review questions will be asked to reinforce the learning outcomes for that section and to preview upcoming material.
To wrap-up the course, student mastery of the material presented will be assessed using a post-course test covering the key learning objectives from each section. Although the test will be open-note, participants will obtain the maximum benefit from the course by paying careful attention throughout the day, asking for clarification when necessary, contributing any personal experiences and anecdotes related to the topic under discussion, and attentively listening to the comments and experiences shared by your colleagues.

## Slide 4: Design-Build
Part 1: Introduction to DB
Notes: Note that you will now begin Part 1, which provides an introductory overview of DB. This section is expected to take about an hour, after which there will be a brief 10 minute break.
Note that the slides throughout the course employ the following acronyms:
DBB = design-bid-build
DB = design-build
DBT = design-build team

## Slide 5: Learning Outcomes
Define DB and explain how differs from traditional project delivery
Understand the background and origins of DB
Identify key Federal and State laws/regulations authorizing and affecting the use of DB
Identify key advantages and disadvantages of using DB
Identify suitable project types for DB
Notes: Briefly review the learning outcomes and indicate that you will revisit the outcomes once again at the end of this section.

## Slide 6: Contents
Design-Bid-Build Overview
Design-Build Overview
Advantages & Limitations of DB
1
2
3
DB Project Selection Criteria
4
Questions/Discussion
5
Notes: Use this slide to present the main topic areas covered in this section.
Note the following:
Although the focus of the course is on DB delivery, we will begin with a brief discussion of the traditional DBB delivery system to provide a foundation for our subsequent discussions on DB. We will move through the initial slides on DBB fairly quickly as the information should be familiar.
Although some time will be set aside at the end of this section for questions, feel free to speak up at any time.

## Slide 7: DBB: Overview
Notes: Explain that ODOT’s traditional delivery system is DBB.

## Slide 8: DBB: Traditional Contracting Method Defined
Clear separation between design and construction
  Designer prepares plans and specifications
  Contractor bids on 100% complete plans and specifications
  Award to the lowest responsible and responsive bidder
Owner retains high level of control and risk
Designer
Constructor
Owner
Contractor Risk Zone
Design
Const
Maintenance
Notes: Use the graphics to emphasize that under DBB there is a clear separation between design and construction, and that no contractual relationship exists between the designer and the contractor. As such, design risk generally resides with the Owner, while the Contractor assumes responsibility for construction means and methods and a 1-year materials and workmanship warranty.
Before turning to the next slide, use this slide to provoke thought.
Ask participants:
What do you see as the top 3or 4 goals for a typical construction project? (Possible answers could include on-time delivery, meeting the project budget, obtaining a certain quality level, etc.)
What are some advantages of DBB that would help you meet these goals?
What are some of the disadvantages of DBB that would impede you from meeting these goals?

## Slide 9: DBB: Advantages
Applicable to a wide range of projects
Well established and easily understood
Owner retains design control
Provides lowest price that responsible, competitive bidders can offer
Established legal precedents
Notes: Depending on how active participants were in the prior Q&A session, you may only need to use this slide to confirm what the participants have already stated. If participants were less vocal, briefly review some of the benefits of DB, which include the following:
• Applicable to a wide range of projects
• Well established and easily understood
• As construction features are typically fully specified, DBB provides agencies with significant control over the end product
• Clearly defined roles for all parties
• Provides the lowest initial price that responsible, competitive bidders can offer
• Extensive litigation has resulted in well-established legal precedents
Based on these advantages, ask participants if they can identify any project conditions that would benefit from the use of DBB. Possible answers may include:
• ODOT needs to completely define the scope using 100% complete plans and specifications
• Significant risks or third-party issues (e.g., ROW, utility, environmental) that can be best resolved or managed by ODOT

## Slide 10: DBB: Risks and Limitations
Two contracts to manage
  Disagreements between designer and contractor flow through ODOT
  Potential for adversarial relationships (Parties have differing agendas/objectives)
ODOT bears risk of design adequacy
No contractor involvement in design
Slowest project delivery method
  No opportunities for time savings by fast-tracking construction
Limited opportunity for innovation
Greater potential for errors and omissions, change orders, delays, and other adverse outcomes
Notes: 1. Briefly review the content on the slide, noting that the separation of design and construction services can foster adversarial relationships between the Department, designers, and contractors; can restrict innovation; and result in high cost and time growth.
2. Ask participants to share if they have experienced any of these disadvantages on a project.

## Slide 11: DB: Overview
Notes: Explain that you will devote the remainder of the course to DB.
If you haven’t already done so, poll participants to determine who has had experience with DB.

## Slide 12: DB Defined
DB is a project delivery approach in which one entity (the design-builder or design-build team) enters into a single contract with the owner to provide for engineering/design services and construction services.
Notes: Read through the definition of DB, emphasizing that under DB, ODOT will enter into a single contract for both engineering/design services and construction.
Note that the DBT may be a single firm, a consortium, joint venture, or other organization. However, the fundamental element of DB delivery remains that one entity assumes primary responsibility for both design and construction of the project.

## Slide 13: Key Differences between DBB and DB
Design-Bid-Build
  Multiple contracts
  Owner retains all design risk
Design-Build
  Single contract
  Contractor assumes some design risk
Designer
Constructor
Owner
Contractor Risk Zone
Design
Const
Maintenance
Design-Build Team
Owner
Contractor
Risk Zone
Design
Const
Maintenance
Notes: Note that participants should be familiar with the graphics shown on the left based on the earlier DBB discussions.
Contrast these graphics with those shown on the right for DB. Note the following key differences:
• The Department enters into only one contract for design and construction services.
• Some (but not all) of the design risk shifts to the DBT.
• Maintenance risk, during the life of the physical construction, primarily remains the same.
Explain that even under DB, some design risk will continue to reside with the Department due to its responsibility to fully define the project scope.

## Slide 14: Historical Perspective of DB
1800 BC
DB Origins
Design-builders can trace their roots to the Master Builders of ancient times.
Classical Greece
Code of Hammurabi
(obligation of design & construction to society)
FHWA publishes Final Rule on DB Contracting
Renaissance
Emergence of DBB
1450
450 BC
Miller Act (Legal separation)
1960s
Private Sector Re-emergence of DB
1935
1990
FHWA SEP-14 Program
2002
Notes: Present this slide to provide a historical perspective of DB. Note that in the interest of time, for those interested, a more complete summary of the evolution of DB is provided in the Participant Workbook.
Emphasize that DB does not represent a departure to something new, but rather a full-circle return to how buildings were constructed in ancient times.
• As denoted by the gray circles on the slide, up until the mid-1400s, construction was accomplished by so-called Master Builders who oversaw design and construction.
• With the Renaissance and the rise of the modern-day architect, the design and construction fields began to separate (see the red circles on the graphic). Alberti is known as the first modern day architect in that he developed drawings, which were then used by others to construct buildings.
• The Industrial Revolution encouraged further specialization and segmentation of the design and construction industries through the rise of Professional Societies and divisions of labor into trades.
• In response to the growing segmentation of the construction industry, Congress enacted several laws that served to endorse the DBB delivery model, chief among these were the Miller Act and the Brooks Act:
  By requiring the posting of bonds, the Miller Act of 1935 essentially took designers out of the construction business because they typically did not have the capital needed to post a bond.
  The Brooks Act of 1972 reinforced the DBB project delivery method by requiring government agencies to award architectural and engineering contracts based solely on qualifications, rather than price.
• As owners began to experience problems with DBB, DB re-emerged as a possible solution for eliminating the often adversarial relationships between designers and contractors and for obtaining better cost certainty.
• In 1990, FHWA implemented Special Experimental Project No.14, Innovative Contracting (SEP-14) as a vehicle for State highway agencies to use Federal-aid funds to experiment with certain alternative contracting methods, including DB, for selected projects.
• 1998: The Transportation Equity Act for the 21st Century (TEA-21) took the first steps in developing regulations for the regular use of DB on federally funded transportation projects.
• 2003: FHWA’s Final Rule on DB Contracting becomes effective.

## Slide 15: Historical Background on ODOT’s DB Program
1995: Pilot program
  6 pilot projects, ranging from $250,000 to $14 million
  Findings:
    Significant time savings over traditional DBB
    Few or no change orders and claims
    Lower ODOT administrative costs
    Reduced inspection requirements
    More cooperative atmosphere
    Clear scope of work required
    One-step procurement process may not be suitable for complex jobs
1999: ODOT granted additional DB authority
2011: Quality Based Selection authority
Notes: Use this slide to transition to a discussion on ODOT’s experience with DB. Note the following:
In 1995 the Ohio State Legislature passed legislation authorizing ODOT to develop and implement a DB pilot program for a maximum of six projects.
ODOT selected six pilot projects ranging in value from $250,000 to $14 million to demonstrate the effectiveness of the DB project delivery method. The slide summarizes the key findings from this pilot program.
In 1999, the Ohio legislature gave ODOT additional DB authority in House Bill 163. This bill allows ODOT to contract a maximum of $250 million using DB.
ODOT’s authority expanded in 2011to allow up to $1billion per fiscal year. The revised legislation allowed ODOT to consider Qualifications by combining technical qualifications and competitive bidding elements.

## Slide 16: ODOT DB Project Program History
Fiscal Year | # of Projects | Total Value | Average of Project Size
1998 | $ 1 | $ 13,888,653 | $ 13,888,653
2000 | $ 6 | $ 113,996,441 | $ 18,999,407
2001 | $ 11 | $ 96,124,911 | $ 8,738,628
2002 | $ 9 | $ 4,762,840 | $ 529,204
2003 | $ 23 | $ 45,953,966 | $ 1,997,999
2004 | $ 7 | $ 11,060,996 | $ 1,580,142
2005 | $ 4 | $ 31,179,305 | $ 7,794,826
2006 | $ 4 | $ 8,327,978 | $ 2,081,994
2007 | $ 2 | $ 7,383,920 | $ 3,691,960
2008 | $ 5 | $ 8,655,327 | $ 1,731,065
2009 | $ 5 | $ 12,917,969 | $ 2,583,594
2010 | $ 25 | $ 78,223,915 | $ 3,128,957
2011 | $ 19 | $ 534,973,914 | $ 28,156,522
2012 | $ 13 | $ 109,610,289 | $ 8,431,561
2013 | $ 24 | $ 121,123,694 | $ 5,046,821
2014 | $ 38 | $ 625,920,085 | $ 16,471,581
2015 | $ 44 | $ 490,235,402 | $ 11,141,714
2016 | $ 57 | $ 206,662,009 | $ 3,625,649
2017 | $ 22 | $ 57,703,748 | $ 2,622,898
2018 | $ 28 | $ 530,633,133 | $ 18,951,183
2019 | $ 2 | $ 87,282,562 | $ 43,641,281
Grand Total | $ 349 | $ 3,196,621,056 | $ 9,159,373
Notes: Emphasize that the program has add multiple increases and decreases through the years.
Initial push from 2001 to 2003 was an initiative from management to delivery DB projects in every district.
2010 increase was due to ARRA
Major push from 2014 through 2018 because of Ohio Bridge Partnership
Highlight some of ODOT’s DB accomplishments to emphasize that DB does not represent a new departure for the Department.
Poll participants to see if they were involved with any of the projects shown on the slide.

## Slide 17: ODOT DB Program – Key Projects
  CCG1
  670/71 Columbus Crossroads
  CCG2
  71 Widenings (3 projects)
  Martin Luther King Interchange
  Opportunity Corridor 2
  Ohio Bridge Partnership Program
  Opportunity Corridor 3
  I-480 Valley View Bridge
  Luc-2 Anthony Wayne Bridge Dehumidification
Notes: CCG1 – first project to incorporate the overall design and approach as an award consideration
670/71 – first project to be taken to court. First major interchange
71 widenings – remaining corridor between Columbus and Cleveland was widened using DB: 25.27 Miles
MLK – First to be shortlisted and Low bid
OBPP – 200+ bridges in 3 years
Opp Corr 3 – First project to use non-traditional goals & to push the approach as a deciding factor (up to 40%)
I-480 Valley View bridge – 4300ft bridge addition (middle) – used one on one confidential meetings during procurement & Pass/Fail evaluation
Luc-2 Dehumidification of the structure with O&M portions.
Main point: Differing types of projects which all have specific needs which were able to be addressed using DB delivery.

## Slide 18: Authority/Legal Basis for Use of DB
Federal Authority
  Law: Title 23 USC 112(b)(3)
    Provides FHWA’s statutory requirements for DB project delivery
  Federal Regulations: Title 23 CFR Part 636
    Provides FHWA’s regulatory policy regarding use of DB (published December 10, 2002)
    August 14, 2007: Subsequent revisions made by SAFETEA-LU
      Eliminated $ thresholds
      Granted permission to release an RFP or award a DB contract prior to finalization of NEPA process
      DB procurement processes that deviate from 23 CFR 636 may still require approval under SEP-14
State Authority
  ORC 5517.011
Notes: Briefly review this slide, noting that the legal basis for using DB on ODOT projects can be found in:
• FHWA’s DB Final Rule (23 CFR 636)
• ORC 5517.011 (note that the Participant Workbook contains an extract from the Code)
2. Explain that this legal authority provides the basis for awarding DB contracts using either a low bid or value based procurement process.

## Slide 19: ODOT’s DB Delivery Options
Low-Bid DB (one step)
  Majority of ODOT’s DB projects
  Contract awarded to lowest prequalified bidder
Two-Step Low Bid
  MLK Interchange
  Sum-271
  CCG6B
Value-Based DB
  5 value-based projects completed to date
  Contract awarded to bidder with the best combination of bid price and technical qualifications assessment
Two-Step Technically Responsive Low-Bid
  Contract awarded to a bidder with a technically responsive proposal and lowest bid
Notes: Briefly review the content on the slide, emphasizing that even though ODOT’s Central Office has the ability to use a two-step low bid or value-based procurement process, the majority of its DB projects are awarded using one-step low bid process.
Briefly introduce the main differences between these three approaches:
• Under one-step low bid, pre-qualified Offerors submit bids, which the Department uses to determine the apparent low bidder. This process is fairly similar to the approach used to procure construction services for a traditional DBB project.
• A two-step low bid process entails an RFQ step in which Offerors prepare Statements of Qualification, which the Department then uses to limit the playing field to the most qualified firms on the basis of pass/fail criteria and a limited number of scored criteria. The short-listed DBTs are then invited to prepare a Price Proposal, which the Department uses to determine the apparent Low Bidder.
• Value-based DB contracting also entails an RFQ step, followed by an RFP step in which the short-listed DBTs are invited to submit Technical and Price Proposals, which the Department evaluates and scores to determine the Apparent Best Value Bidder based on a combination of bid price and a technical qualifications assessment.
• Two-Step Technically Responsive Low-Bid. Two-Step Technically Responsive Low-Bid process incorporates a Request for Qualifications (RFQ) step in which Offerors prepare Statements of Qualification (SOQ), which the Department then uses to limit the playing field to the most qualified firms. The short-listed Offerors are then invited to submit Technical and Price Proposals. The Department evaluates the Technical proposal on a Pass/Fail evaluation. Process usually includes a “pre- submission” / Proprietary Technical Information meetings to discuss concept before official submittal.
The revisions of approach have occurred because of changing needs to the project, the reponses from industry, and the adjusting of the processes as we’ve learned more of what works.
Note that you will spend additional time on procurement considerations during Section 3.

## Slide 20: DB: Advantages & Limitations
Notes: Let’s turn to some of the perceived advantages of DB.

## Slide 21: Advantages of DB
Accelerated Project Delivery
  Ability to start or phase construction before entire design is complete
    “fast-tracking” construction
  More efficient procurement of long-lead items
  Earlier cost and schedule certainty
Design (100%)
Construction
Bid
DBB
Design (% completion by ODOT based on project-specific circumstances)
Construction
Bid
DB
Notes: Explain that a key consideration for using DB is its ability to “fast-track” construction by starting construction before the entire design is complete. This allows for a shorter overall delivery schedule, even if actual construction time remains the same.
Earlier contractor involvement also promotes the following:
• More efficient procurement of long-lead items
• Earlier cost and schedule certainty
• Enhanced cost-consciousness and constructability of plans due to improved coordination between designer and contractor

## Slide 22: Advantages of DB
Innovation
  Allows the contractor flexibility in selecting alternative designs, materials, and construction techniques
  Innovation in scheduling/phasing may allow for earlier completion
Less cost growth
Enhanced constructability
  Design can be optimized to contractor’s strengths, potentially leading to time and/or cost savings
Better risk allocation
Single point of responsibility for quality, cost, and schedule
  Minimizes adversarial disputes between designer and contractor
  Reduces change orders and claims related to “errors and omissions”
  Less management and coordination by ODOT
Notes: Review the potential advantages shown on the slide, to the extent that they weren’t already addressed during the Q&A.
Ask the class if they can identity any other potential advantages of DB.

## Slide 23: Risks/Limitations of DB
Reduced owner control over design
Potential for reduced quality (if subordinated to cost and time)
Procurement process can be time-consuming, costly, and complex
Potential to reduce opportunities for smaller construction firms
Lack of understanding of changes in roles and responsibilities
Notes: Use this slide to review some of the main disadvantages and risks of using DB, which may include:
• Less agency control over final design
• Elimination of traditional checks and balances. Designer is no longer agency’s advocate. Quality may be subordinated by cost or schedule considerations.
• Reduced opportunities for smaller, local construction firms
• Higher procurement costs, which may include stipends for proposers
• Traditional funding may not support fast-tracking construction or may require accelerated cash flow
• Accelerated construction can potentially overextend the workforce

## Slide 24: DB: Project Selection
Notes: Note that in this section you will discuss considerations for using DB.

## Slide 25: Criteria for Using DB (Officially)
Project has a clearly defined scope and design basis
Projects that would benefit from:
  Expertise not available in-house
  An expedited delivery schedule (e.g., emergency project)
  Innovation in design and/or construction
No ROW acquisition required through the contract
Minimal third party, environmental, and geotechnical issues
No complicated geotechnical problems
Projects that are Minor or Minimal under ODOT’s PDP
Notes: Explain that best practice suggests that DB provides the greatest benefit on projects for which:
• The project scope can be adequately defined without 100 complete PS&E.
• Reduced schedule duration is needed
• Opportunity for innovation exists
• Outside expertise is needed.
• Early cost certainty is required.
• Minimal third party risks exist or can be mitigated.
In addition, ODOT guidance documents contain the following additional screening criteria:
• Minimal utility coordination required
• Manageable public controversy
• Projects that are environmentally exempt or qualify for a Level 1 Categorical Exclusion
• Projects that are Minor or Minimal under ODOT’s PDP
Conversely, you may want to note that projects that make for good DBB candidates include the following:
• ODOT needs to completely define the scope
• Scope can be best defined using prescriptive specifications
Significant risks or third-party issues (e.g., ROW, utility, environmental) that can be best resolved or managed by ODOT
Admit that the official guidance would eliminate the majority of the best DB projects – none of the largest projects would meet the official criteria.

## Slide 26: Suitable Project Types
Small Projects
  Culvert Replacement/Small Bridge
Mid-Level Projects
  Interstate reconstruction
  Widening
  Replacement or reconstruction or larger bridges
Mega Projects
  Corridor reconstruction
  Unique or complex structures
Notes: Use this slide to identify typical DB project types.
Conversely, you may wish to point out that the following projects would make poor candidates for DB.
• Two-lane resurfacing and overlays
• Bridge painting
• Crack sealing
• Guardrail, RPM, and striping
• Signage

## Slide 27: Questions
Notes: Before closing out this section, ask participants if they have any questions regarding the material covered in Section 1.

## Slide 28: Learning Outcomes
Define DB and explain how differs from traditional project delivery
Understand the background and origins of DB
Identify key Federal and State laws/regulations authorizing and affecting the use of DB
Identify key advantages and disadvantages of using DB
Identify suitable project types for DB
Notes: Review the section learning objectives. Plan to spend 3-5 minutes on this review. Maintain a quick pace throughout the review to keep it interesting and interactive.
Preview the next section by telling participants that, after the break, your will begin discussing the DB project development and scoping process.