## Sheet1
OUPS 1-800-362-2764 |  | Project Number |  | AUG-SMA-2204 | [5 empty] | Last Updated By: | LTH
PM: | MKG |  | OUPS Ticket: | A302601643, B301200561, B301200565, A302601643 | [5 empty] | On: | 2024-10-17
Utility Company | Telephone | Contact | Project Notification and Request for Plans | Received Utility Plans or Positive Response | Sent Stage 1 (35%) Plans | Received Comments | Sent Stage 2 (80%) Plans | Received Comments | Sent Stage 3 (95%) Plans | Received Comments | Remarks
Name and Address | No. | Name
GAS | 330-664-2575 | Michael North |  |  | 2023-04-11 | 2023-05-15 | 2023-11-30 | 2023-12-13 | 2024-10-17 | No Response | Received no conflict letter.
DOMINION ENERGY OHIO
150 S. JACKSON STREET
LIMA, OHIO 45801
ELECTRIC
AES | 937-331-4521 | Bill Ward |  |  | 2023-04-11 | 2023-04-11 | 2023-11-30 | No Response. | 2024-10-17 | No Response | There are no AES facilites in the project area.
1900 DRYDEN ROAD | [7 empty] | No facilties in area.
DAYTON, OHIO 45439
ELECTRIC | 419-394-3303 | Craig Moeller |  |  | 2023-04-11 | 2023-05-01 | 2023-11-30 | 2024-01-02 | 2024-03-03 | 2024-09-13 | City reviewed plans and proivded comments.
CITY OF ST. MARYS
101 E SPRING STREET
ST. MARYS, OHIO 45885 | [10 empty] | City owned electic to be relocated around proposed traffic poles.
WATER | 419-394-3303 | Craig Moeller |  |  | 2023-04-11 | 2023-05-01 | 2023-11-30 | 2024-01-02 | 2024-03-03 | 2024-09-13 | City reviewed plans and proivded comments.
CITY OF ST. MARYS
101 E SPRING STREET | [10 empty] | No Conflict
ST. MARYS, OHIO 45885
CABLE | 419-996-2249 | Mark Richhart |  |  | 2023-04-11 | n/a | 2023-11-30 | 2023-12-05 | 2024-10-17 | No Response | Did not recive any comments on Stage 1.
CHARTER COMMUNICATION | [10 empty] | No Conflicts.
TELEPHONE | 937-498-5105 | Rick Krogman |  |  | 2023-04-11 | n/a | 2023-11-30 | 2023-12-06 | 2024-10-17 | No Response | Did not recive any comments on Stage 1.
CENTURTY LINK | [10 empty] | No Conflict
1400 FOURTH STREET
SIDNEY, OHIO 45365

## Sheet2
Utility | Utility Owners Name | Utility Companies Representatives Name | Utility Companies Representatives Address | Utility Companies Representatives Telephone Numbers | Utility Companies Representatives Email Address | Remarks
Telephone
Electric (Transmission)
Electric (Distribution)
Storm Sewer
Cable
Gas (Transmission)
Gas (Distribution)
Water & Sanitary