## No Lanes Closed (hidden)
Work Zone User Cost Calculations
No Lanes Closed
Project ID:
County-Route-Section:
User Input:
Construction Calendar Year:
|  | Car | B/C Truck
ADT of Section:
Length of Work Zone (Miles):
Original Posted Speed (MPH):
Work Zone Posted Speed (MPH):
Duration of Work Zone (Days):
Calculated Values:
Cost per Hour:
Travel Time Pre-Work Zone (Secs):
Travel Time During Work Zone (Secs):
Delay (Secs):
Delay (Hours):
Delay Cost per Vehicle:
Delay Cost per Day:
Delay Cost for Work Zone Duration:
Total Delay Cost for Work Zone Duration: |  | (Missing Input)
Average Delay Cost per Day: |  | (Missing Input)
Form Version Date: Prior to 2/2/2018
Fill in all highlighted cells.
The Average Delay Cost per Day is the MAXIMUM that may be used as incentive / disincentive.
Date Calculated: | 2026-02-03
Spreadsheet protection password: CONSTRUCTION

## Lane(s) Closed on Mainline
Work Zone User Cost Calculations
Lane(s) Closed on Mainline (Based on Applicable PLCS Segment)
Project ID: |  | 119358
County-Route-Section: |  | CLI-72-2.18
User Input:
Construction Calendar Year: |  | 2027
AADT (Total 2-Way AADT for the Applicable PLCS Segment): |  | 1500
% Trucks (Overall Daily Average for the Applicable PLCS Segment): |  | 17%
Lanes per Direction (Per Direction for the Applicable PLCS Segment): |  | 1
Calculated Values:
|  | Car | B/C Truck
User Cost per Vehicle: |  | 29.1342 | 78.6411
Vehicles per Day (Calculated Directional Equivilant): |  | 622.5 | 127.5
User Cost per Day by Vehicle Type (Directionally): |  | 18136.0327 | 10026.7389
User Cost per Day (Directionally): |  | 28162.7716
User Cost per Day per Lane (Directionally): |  | 28162.7716
User Cost per Hour per Lane (Directionally): |  | 1173.4488
User Cost per Minute per Lane (Directionally): |  | 19.5575
Max Disincentive per Minute per Lane (Directionally): |  | 15
Notes (description, PLCS Segment reference results are applicable to, project phase reference, etc, as applicable): ***TIP: Alt+Enter for a line break in the box below.***
Form Version Date: 2/28/2025
Fill in all highlighted cells relating to the Permitted Lane Closure Schedule (PLCS) Segment(s) that apply to the Construction Limits of the project. If more than one PLCS Segment applies to the Construction Limits, each User Cost per PLCS Segment shall be calculated seperately.
The rounded User Cost per Minute per Lane is the MAXIMUM that may be used as a disincentive. The resulting value is to be applied to the area within the project that matches the PLCS Segment used to calculate the value.
NOTE: Although mainline ramps are treated as a mainline segment for Traffic Management in Work Zones Policy/Standard Procedure purposes, use the Lane(s) Closed on Multi-Lane Ramp worksheet to calculate the maximum disincentive for multi-lane mainline ramps. The method is the same as the Lane(s) Closed on Mainline worksheet; however, the AADT input is not divided by 2 to make the volumes directional on the multi-lane ramp worksheet. The Lane(s) Closed on Multi-Lane Ramp worksheet is also intended for use on multi-lane system and service ramps.
Date Calculated: | 2026-02-03
Spreadsheet protection password: CONSTRUCTION
WHERE TO FIND THE APPLICABLE VALUES TO ENTER:
- AADT: Use the total mainline AADT in both directions combined (2-way AADT). This can be found in the Traffic Count Data System (TCDS) through the PLCS system by locating the PLCS Segment area and selecting the highest volume "active" traffic count station on the mainline within the PLCS Segment area. If there are no active traffic count stations on the mainline in the PLCS Segment area, then use the highest volume "active" traffic count station on the mainline that is adjacent to the PCLS Segment area. To view the traffic count stations within the PLCS, select the gear in the upper right hand corner, select TCDS, select BOTH for Station Number/AADT (optional), select the applicable functional class (optional), and select active. Once the traffic count stations load on the screen they can be viewed in relation to the PLCS Segments. Select a traffic count station and View Detail to see data for use.
- % Trucks: While the PLCS system utilizes half hourly % Truck data, where available, instead use the overall % Trucks value related to the AADT for purposes of User Cost calculations. This value can be found in TCDS where the AADT is found. If the % Truck data is not available for the year of the AADT used, the prior year % Truck value can be used instead. NOTE: The additional data such as % Truck under BC doesn't get filled in until the year end processing step is completed which generates those statistics. This is why % Trucks may be blank for the most recent AADT available.
- Lanes per Direction: Use the number of lanes per direction (preconstruction) per the applicable PLCS Segment. This can be found within the PLCS system when looking at the applicable PLCS Segment Details. NOTE: The traffic count station data in TCDS also includes a number of lanes assigned per direction; however, the TCDS value may differ from the number established in the PLCS Segment due to inclusion of non-through lanes and/or being located near but not within the PLCS Segment area. This is why the PLCS Segment-defined number of lanes per direction (from the PLCS, not TCDS) is to be used.
- Direction on the PLCS: The PLCS Segment Details specify the segment direction. This could be directional (NB, SB, EB, or WB) or bidirectional (EB/WB or NB/SB). If bidirectional, then the User Cost results of the analysis will apply to both directions of the associated PLCS Segment. If the PLCS Segment is directional then the User Cost results of the analysis will apply to only to the same direction of the associated PLCS Segment. NOTE: If User Cost results are needed for more than one PLCS Segment to cover the Construction Limits, each User Cost per PLCS Segment shall be calculated seperately.
PLCS Landing Page (to access the new PLCS):
https://www.transportation.ohio.gov/working/data-tools/resources/permitted-lane-closure
Transportation Data Management System (TDMS):
https://odot.public.ms2soft.com/tcds/tsearch.asp?loc=Odot&mod=

## Lane(s) Closed Calc Method (hidden)
$RUCTOTAL = ($RUCCARS + $RUCTRUCKS)*(#Minutes Closed)*(#Lanes Closed)
$RUCCARS = (CARS/(Minute*Lane))*($/CAR)
$RUCCARS = (((60000/2)*0.90) cars/(24 hr*60 min*3 lanes))*($21.88/car)
$RUCCARS = (6.25 cars/minute-lane)*($21.88/car)
$RUCCARS = $136.75/minute-lane
NOTE: Round $/minute-lane down to the nearest $5; $136.75/minute-lane = $135/minute-lane
$RUCCARS = $135/minute-lane
$RUCTRUCKS = (TRUCKS/Minute*Lane)*($/TRUCK)
$RUCTRUCKS = (((60000/2)*0.10) trucks/(24 hr*60 min*3 lanes)*($59.06/truck)
$RUCTRUCKS = (0.69 trucks/minute-lane)*($59.06/truck)
$RUCTRUCKS = ($41.01/minute-lane)
NOTE: Round $/minute-lane down to the nearest $5; $41.01/minute-lane = $40/minute-lane
$RUCTRUCKS = ($40/minute-lane)
$RUCTOTAL = ($135/minute-lane + $40/minute-lane)*(30 minutes closed)*(1 lane closed)
$RUCTOTAL = ($175/minute-lane)*(30 minutes closed)*(1 lane closed)
$RUCTOTAL = $5250
Information Last Updated: 10/23/18
Spreadsheet protection password: CONSTRUCTION
*
* Based upon how many vehicles would have passed this point in a given timeframe.
Example:
-60,000 AADT, 10% Trucks
-3 total lanes, 1 lane closed (3:2) for 30 minutes beyond permitted
-2018 Construction
Lane(s) Closed on Mainline Road User Cost Calculation Method and Assumptions
Assumptions Made to Simplify the Calculation:
-AADT divided by 2 to obtain a directional AADT (rather than using specific directional percentages).
-Directional AADT divided by 24 gives hourly total volume (rather than using hourly percentages).
-Equal lane utilization.
-Vehicles impacted by the lane closure are only those that would have traveled in the closed lane(s) had they been open (rather than also assessing impacts on vehicles that would have traveled in lane(s) that remained open and had to accomodate the traffic from the closed lane(s)).
-Same % trucks applicable throughout the day.

## Lane(s) Closed Violation Calc (hidden)
Work Zone Disincentive Calculator (Per Violation)
Lane(s) Closed on Mainline (Based on Matching PLCS Segment)
Project ID:
County-Route-Section:
User Input:
Fill out the Lane(s) Closed worksheet first.
Next, fill in the following highlighted cells.
Non-Allowable Lane Closure Start Time (HH:MM AM/PM):
Non-Allowable Lane Closure End Time (HH:MM AM/PM):
Total Non-Allowable Lane Closure Time (in Minutes):
Number of Lanes Closed:
Disincentive to be Applied (Per Matching PLCS Segment):
Form Version Date: xx/xx/xxxx DRAFT
Fill in all highlighted cells for Work Zone Disincentive Calculator, per violation. Highlighted cells in the Disincentive calculator are for use during construction when the need arrises calculate the disincentive to be applied due to a non-allowable closure. If a violation occured that extended into more than one contiguous PLCS Segments, the Lane(s) Closed worksheet shall be filled in using the PLCS segment resulting in the highest User Cost per Minute per Lane impacted by the violation.
Date Calculated: | 2026-02-03
Spreadsheet protection password: CONSTRUCTION

## Lane(s) Closed on Multi-Ln Ramp
Work Zone User Cost Calculations
Lane(s) Closed on Multi-Lane Ramp (Based on Applicable PLCS Segment)
Project ID:
Ramp:
User Input:
Construction Calendar Year:
Directional AADT (Total Ramp AADT on the Directional Ramp):
% Trucks (Overall Daily Average on the Directional Ramp):
Number of Lanes (On the Directional Ramp):
Calculated Values:
|  | Car | B/C Truck
User Cost per Vehicle:
Vehicles per Day (On the Directional Ramp):
User Cost per Day by Vehicle Type (On the Directional Ramp):
User Cost per Day (On the Directional Ramp):
User Cost per Day per Lane (On the Directional Ramp):
User Cost per Hour per Lane (On the Directional Ramp):
User Cost per Minute per Lane (On the Directional Ramp):
Max Disincentive per Minute per Lane (On the Directional Ramp): |  | (MISSING INPUT)
Notes (description, PLCS Segment reference results are applicable to, project phase reference, etc, as applicable): ***TIP: Alt+Enter for a line break in the box below.***
Form Version Date: 2/28/2025
Fill in all highlighted cells relating to the directional multi-lane ramp Permitted Lane Closure Schedule (PLCS) Segment within the Construction Limits of the project. If there is more than one multi-lane ramp impacted within the Construction Limits, each User Cost per multi-lane ramp PLCS Segment shall be calculated seperately.
The rounded User Cost per Minute per Lane is the MAXIMUM that may be used as a disincentive. The resulting value is to be applied to the area within the project that matches the multi-lane ramp PLCS Segment used to calculate the value.
NOTE: Although mainline ramps are treated as a mainline segment for Traffic Management in Work Zones Policy/Standard Procedure purposes, use the Lane(s) Closed on Multi-Lane Ramp worksheet to calculate the maximum disincentive for multi-lane mainline ramps. The method is the same as the Lane(s) Closed on Mainline worksheet; however, the AADT input is not divided by 2 to make the volumes directional on the multi-lane ramp worksheet. The Lane(s) Closed on Multi-Lane Ramp worksheet is also intended for use on multi-lane system and service ramps.
Date Calculated: | 2026-02-03
Spreadsheet protection password: CONSTRUCTION
WHERE TO FIND THE APPLICABLE VALUES TO ENTER:
- AADT: Use the total directional multi-lane ramp AADT. This can be found in the Traffic Count Data System (TCDS) through the PLCS system by locating the PLCS Segment area and selecting the highest volume "active" traffic count station on the multi-lane ramp within the PLCS Segment area. If there are no active traffic count stations on the multi-lane ramp PLCS Segment area, then contact the District Work Zone Traffic Manager for additional direction. To view the traffic count stations within the PLCS, select the gear in the upper right hand corner, select TCDS, select BOTH for Station Number/AADT (optional), select the applicable functional class (optional), and select active. Once the traffic count stations load on the screen they can be viewed in relation to the PLCS Segments. Select a traffic count station and View Detail to see data for use.
- % Trucks: While the PLCS system utilizes half hourly % Truck data, where available, instead use the overall % Trucks value related to the multi-lane ramp AADT for purposes of User Cost calculations. This value can be found in TCDS where the AADT is found. If the % Truck data is not available for the year of the multi-lane ramp AADT used, the prior year % Truck value can be used instead. NOTE: The additional data such as % Truck under BC doesn't get filled in until the year end processing step is completed which generates those statistics. This is why % Trucks may be blank for the most recent multi-lane ramp AADT available.
- Number of Lanes: Use the number of lanes on the directional multi-lane ramp (preconstruction) per the applicable PLCS Segment. This can be found within the PLCS system when looking at the applicable multi-lane ramp PLCS Segment Details. NOTE: The traffic count station data in TCDS also includes a number of lanes assigned for the directional multi-lane ramp; however, the TCDS value may differ from the number established in the PLCS Segment due to inclusion of non-through lanes, etc. This is why the multi-lane ramp PLCS Segment-defined number of lanes (from the PLCS, not TCDS) is to be used.
- Direction on the PLCS: The directional multi-lane ramp PLCS Segment Details specify the ramp segment direction. This typically relates to the originating ramp direction; however, it could also be coded as a the final ramp direction instead. Regardless of the direction specified for the multi-lane ramp, the User Cost results of the analysis will apply only to the directional multi-lane ramp for the associated PLCS segment. NOTE: If User Cost results are needed for more than one multi-lane ramp PLCS Segment to cover the Construction Limits, each User Cost per multi-lane ramp PLCS Segment shall be calculated seperately.
PLCS Landing Page (to access the new PLCS):
https://www.transportation.ohio.gov/working/data-tools/resources/permitted-lane-closure
Transportation Data Management System (TDMS):
https://odot.public.ms2soft.com/tcds/tsearch.asp?loc=Odot&mod=

## Detour (Actual Drive Time)
Work Zone User Cost Calculations
Detour (Using Actual Drive Time)
Project ID: |  | 119358
County-Route-Section: |  | CLI-72-2.18
User Input:
Construction Calendar Year: |  | 2027
|  | Car | B/C Truck
ADT of Detoured Section: |  | 1500
Time to Drive Normal Route (Min): |  | 8
Time to Drive Detour Route (Min): |  | 15
Duration of Closure (Days): |  | 30
Calculated Values:
User Cost per Vehicle per Hour: |  | 29.1342 | 78.6411
Delay (Min): |  | 7
Delay (Hours): |  | 0.11667
Delay Cost per Vehicle: |  | 3.399
Delay Cost per Day: |  | 5098.4831
Delay Cost for Closure Duration: |  | 152954.493
Total Delay Cost for Closure Duration: |  | (Missing Input)
Average Delay Cost per Day: |  | (Missing Input)
Notes (description, detour route, project phase reference, etc, as applicable): ***TIP: Alt+Enter for a line break in the box below.***
Form Version Date: 2/28/2025
Fill in all highlighted cells.
The Average Delay Cost per Day is the MAXIMUM that may be used as incentive / disincentive.
Date Calculated: | 2026-02-03
Spreadsheet protection password: CONSTRUCTION

## Detour (Distance & Speed)
Work Zone User Cost Calculations
Detour (Using Distance & Speed)
Project ID:
County-Route-Section:
User Input:
Construction Calendar Year:
|  | Car | B/C Truck
ADT of Detoured Section:
Length of Normal Route (Miles):
Length of Detour Route (Miles):
Avg Posted Speed on Normal Route (MPH):
Avg Posted Speed on Detour Route (MPH):
Duration of Closure (Days):
Calculated Values:
User Cost per Vehicle per Hour:
Travel Time Along Normal Route (Secs):
Travel Time Along Detour Route (Secs):
Delay (Secs):
Delay (Hours):
Delay Cost per Vehicle:
Delay Cost per Day:
Delay Cost for Closure Duration:
Total Delay Cost for Closure Duration: |  | (Missing Input)
Average Delay Cost per Day: |  | (Missing Input)
Notes (description, detour route, project phase reference, etc, as applicable): ***TIP: Alt+Enter for a line break in the box below.***
Form Version Date: 2/28/2025
Fill in all highlighted cells.
The Average Delay Cost per Day is the MAXIMUM that may be used as incentive / disincentive.
Date Calculated: | 2026-02-03
Spreadsheet protection password: CONSTRUCTION

## CPI Data
Historical Consumer Price Index for All Urban Consumers (CPI-U): U. S. city average, all items, index averages - Continued
https://www.bls.gov/cpi/tables/supplemental-files/home.htm
(See file titled "Historical CPI-U, December 20xx" for the December of the most recent year posted.)
www.bls.gov/cpi
CPI Year | Semiannual Average |  | Annual Average | % change from 2008 Annual Average | User Cost/Hour |  | Project Year | Actual
| 1st half | 2nd half |  |  | Car | Truck
2008 | 214.429 | 216.177 | 215.303 |  | 19.22 | 51.88 | 2009
2009 | 213.139 | 215.935 | 214.537 | -0.3558% | 19.1516 | 51.6954 | 2010
2010 | 217.535 | 218.576 | 218.056 | 1.279% | 19.4658 | 52.5434 | 2011
2011 | 223.598 | 226.28 | 224.939 | 4.476% | 20.0802 | 54.2019 | 2012
2012 | 228.85 | 230.338 | 229.594 | 6.638% | 20.4958 | 55.3236 | 2013
2013 | 232.366 | 233.548 | 232.957 | 8.2% | 20.796 | 56.134 | 2014
2014 | 236.384 | 237.088 | 236.736 | 9.955% | 21.1333 | 57.0446 | 2015
2015 | 236.265 | 237.769 | 237.017 | 10.09% | 21.1584 | 57.1123 | 2016
2016 | 238.778 | 241.237 | 240.007 | 11.47% | 21.4253 | 57.8327 | 2017
2017 | 244.076 | 246.163 | 245.12 | 13.85% | 21.8817 | 59.0648 | 2018
2018 | 250.089 | 252.125 | 251.107 | 16.63% | 22.4162 | 60.5074 | 2019
2019 | 254.412 | 256.903 | 255.657 | 18.74% | 22.8224 | 61.6038 | 2020
2020 | 257.557 | 260.065 | 258.811 | 20.21% | 23.1039 | 62.3638 | 2021
2021 | 266.236 | 275.703 | 270.97 | 25.86% | 24.1894 | 65.2937 | 2022
2022 | 288.347 | 296.963 | 292.655 | 35.93% | 26.1252 | 70.5189 | 2023
2023 | 302.408 | 306.996 | 304.702 | 41.52% | 27.2006 | 73.4218 | 2024
2024 | 312.145 | 315.233 | 313.689 | 45.7% | 28.0029 | 75.5874 | 2025
2025 |  |  |  |  | 28.5629 | 77.0991 | 2026 | Estimated at 2% increase per year
2026 |  |  |  |  | 29.1342 | 78.6411 | 2027
2027 |  |  |  |  | 29.7169 | 80.2139 | 2028
2028 |  |  |  |  | 30.3112 | 81.8182 | 2029
2029 |  |  |  |  | 30.9174 | 83.4546 | 2030
2030 |  |  |  |  | 31.5358 | 85.1236 | 2031
2031 |  |  |  |  | 32.1665 | 86.8261 | 2032
2032 |  |  |  |  | 32.8098 | 88.5626 | 2033
2033 |  |  |  |  | 33.466 | 90.3339 | 2034
2034 |  |  |  |  | 34.1353 | 92.1406 | 2035
2035 |  |  |  |  | 34.8181 | 93.9834 | 2036
Information Last Updated: 2/28/2025

## FAQ
1) What is the latest adjustment factor for car and truck road user costs for use with the road user cost spreadsheet?
The passenger car and truck costs shown in the Innovative Contracting Manual (ICM) are for 2008 values (provided to ODOT in early 2010 by FHWA Traffic Monitoring & Survey Division). To obtain the current year values, use the Consumer Price Index (CPI) and calculate a ratio to bring the values up to date. The CPI can be found here at:
www.bls.gov/cpi
(Bureau of Labor Statistics website has since been changed. As of 1/31/18, Table 24 can be found at the link below by clicking "Historical CPI-U" under the latest completed year.)
https://www.bls.gov/cpi/tables/supplemental-files/home.htm
Within the PDF report scroll to Table 24 ("Historical Consumer Price Index for All Urban Consumers (CPI-U): U.S. city average, all items - Continued"; the last page of Table 24). We use the annual average values rather than the monthly or semi-annual values to avoid potential volatility of the month-to-month factors.
https://www.bls.gov/cpi/tables/supplemental-files/home.htm
NOTE: The table formerly refered to as Table 24 (for "Historical Consumer Price Index for All Urban Consumers (CPI-U): U.S. city average, all items - Continued") can be found by instead clicking the link above and then clicking on the link under December of the latest published year titled "Historical CPI-U, December 20xx". Scroll to the end of the list for the most recent update. We use the annual values rather than the monthly or semi-annual values to avoid potential volatility of the month-to month factors.
Example: | What cost per passenger car and cost per truck are to be used for road user costs for 2025 (project calendar year 2025)?
The 2008 values given in the ICM are $19.22/Passenger Car and $51.88/Truck.
The annual average CPI for 2008, per the CPI, is $215.303.
The most recent annual average CPI published is for 2024 (as of 2/28/25). We use the 2024 annual average value for project calendar year 2025.
The annual average CPI for 2024, per the CPI, is $313.689.
The 2024 to 2008 ratio ($313.689/$215.303) is 1.4570. (…or the 2024 value is 45.70% higher than the 2008 value.)
2025 Cost per Passenger Car = (2008 Cost per Passenger Car) x (2024 to 2008 Ratio) = $19.22/Passenger Car x 1.4570 = $28.00/Passenger Car
2025 Cost per Truck = (2008 Cost per Truck) x (2024 to 2008 Ratio) = $51.88/Truck x 1.4570 = $75.59/Truck
2) What if I am calculating road user costs for a future year? Do the cost per passenger car and cost per truck change? If so, how?
If calculating road user costs for a future year for a project, the values can be increased by an assumed percentage to obtain a projected future value. As a rule of thumb we use 2% per year based on the recent average trends over the past decade or so (based on the values shown on the Historical CPI-U under "Percent change from previous, Annual Avg").
| Year | % Δ (prior annual avg) | Year | % Δ (prior annual avg) | Year | % Δ (prior annual avg) | Year Range | Avg % | Year Range | Avg %
| 2000 | 3.4 | 2010 | 1.6 | 2020 | 1.2 | 2000-2009 | 2.56 | 2010-2019 | 1.77
| 2001 | 2.8 | 2011 | 3.2 | 2021 | 4.7 | 2001-2010 | 2.38 | 2011-2020 | 1.73
| 2002 | 1.6 | 2012 | 2.1 | 2022 | 8 | 2002-2011 | 2.42 | 2012-2021 | 1.88
| 2003 | 2.3 | 2013 | 1.5 | 2023 | 4.1 | 2003-2012 | 2.47 | 2013-2022 | 2.47
| 2004 | 2.7 | 2014 | 1.6 | 2024 | 2.9 | 2004-2013 | 2.39 | 2014-2023 | 2.73
| 2005 | 3.4 | 2015 | 0.1 | 2025 |  | 2005-2014 | 2.28 | 2015-2024 | 2.86
| 2006 | 3.2 | 2016 | 1.3 | 2026 |  | 2006-2015 | 1.95 | 2016-2025
| 2007 | 2.8 | 2017 | 2.1 | 2027 |  | 2007-2016 | 1.76 | 2017-2026
| 2008 | 3.8 | 2018 | 2.4 | 2028 |  | 2008-2017 | 1.69 | 2018-2027
| 2009 | -0.4 | 2019 | 1.8 | 2029 |  | 2009-2018 | 1.55 | 2019-2028
Example: | What cost per passenger car and cost per truck are to be used for road user costs for project calendar year 2028 (as of 2025)?
Calculate or obtain the current project year values (in this example, 2025; example is above under #1).
2025 Cost per Passenger Car = $28.00/Passenger Car
2025 Cost per Truck = $75.59/Truck
Project the current year values (Project Year 2025) three years forward to 2028 Project Year values, assuming an approximate 2% per year increase.
2028 Cost per Passenger Car = (2025 Cost per Passenger Car) x ((1+(2% per year))^3 years) = $28.00/Passenger Car x ((1+(0.02))^3) = $29.72/Passenger Car
2028 Cost per Truck = (2025 Cost per Truck) x ((1+(2% per year))^3 years) = $75.59/Truck x ((1+(0.02))^3) = $80.21/Truck
3) On the Lane(s) Closed on Mainline worksheet, the user is to enter a total AADT (bidirectional). How does the worksheet know what percentage is for each direction?
It is understood that the volumes may be directional on some facilities (something other than 50%/50%), but for simplicity the worksheet divides the total AADT by 2 (assumming 50% per direction).
4) On the Lane(s) Closed on Mainline worksheet, what do I enter for number of lanes per direction?
The value used should match the number of lanes used in the same respective segment on the Permitted Lane Closure Schedule (PLCS). If the PLCS segment represents one direction, rather than both directions, then the resulting user cost per minute per lane will be only applicable for the direction represented in the PLCS segment. If the PLCS segment represents both directions, the resulting user cost per minute per lane will be applicable in both directions represented in the PLCS segment. In both cases the number of lanes per direction shown on the PLCS segment is the same number that will be entered on the Lane(s) Closed on Mainline worksheet.
5) Why do I get a slightly different result when calculating the cost per minute per lane by hand rather than using the Lane(s) Closed on Mainline and Lane(s) Closed on Multi-Lane Ramp worksheets?
These worksheets have the final user cost per minute per lane coded to always round down to the nearest $5. For example, if the resulting user cost per minute per lane calculates to $118.51 the resulting value is rounded down to $115 per minute per lane.
6) What happened to the No Lanes Closed worksheet?
The No Lanes Closed worksheet has been removed. Since work zone speed limits are now variable the applicability of the worksheet has declined. Additionally, disincentives for violations of the variable speed limits in work zones is now covered within SS 808. If you feel you have a need for this old worksheet please contact Emily (email below).
7) Who do I contact for more information or with questions?
| Contact: | Emily.Willis@dot.ohio.gov
Information Last Updated: 2/28/2025

## Revision History
Road User Cost Spreadsheet Revision History
Information Last Updated: 2/28/2025
Revision Date | Description of Changes Made
2025-02-28 | CPI Data Tab: -Updated CPI data for 2024 (which is used for Project Year 2025). FAQs Tab: -Updated the examples in #1 and #2 to advance the examples one year due to the updated values. -Updated 2024 data under #2 for CPI % change from previous annual average. -Updated 2015-2025 10-year average data under #2 for 10-year average of the annual % changes. Revision History Tab: -Updated the Revision History to include information that was missing for additional revisions between the ones already listed (10/17/2018, 10/23/2018, 10/29/2018 and 5/17/19).
2024-02-27 | Lane(s) Closed on Mainline: -Updated instructions on how to obtain data needed for entries with the new PLCS. -Clarified the data to use with the entries. -Added tip for creating a line break within a cell. -Updated form date. Lane(s) Closed on Multi-Lane Ramp (NEW): -New spreadsheet added to calculate user costs relating to multi-lane ramps (system, mainline, etc). The functions in this tab don't divide the AADT by half to make the volume directional like the Lane(s) Closed on Mainline does. The new PLCS includes PLCS Segments for multi-lane ramps. Detour (Actual Drive Time): -Added tip for creating a line break within a cell. -Updated form date. Detour (Distance & Speed): -Added tip for creating a line break within a cell. -Updated form date. CPI Data Tab: -Updated CPI data for 2022 and 2023 (which is used for Project Years 2023 and 2024). -Expanded Tab to project estimates for future CPI years to 2035 (Project Year 2036). FAQs Tab: -Updated the contact information to remove Chris Wilson. Emily Willis remains. -Updated 2022 and 2023 related data under #2 for trends in CPI % change from prior annual average. Updated the 10 year average % changes from prior annual averages. -Updated the examples to be more current. -Updated FAQ #5 to include the new spreadsheet for Lane(s) Closed on Multi-Lane Ramp. Revision History: -Revision listing order reversed to show the most current update at the top of the list and older updates as you continue down the list.
2022-02-09 | Revision History Tab: -Added a new tab for Revision History and populated the revision history back to the 2/2/2018 revision update. CPI Data Tab: -Updated CPI data for 2020 and 2021 (which is used for Project Years 2021 and 2022). FAQs Tab: -Updated the examples to be more current. -Added data under #2 relating to trends in CPI % change from prior annual average. Calculates and shows the 10 year average % changes from prior annual average. Lane(s) Closed on Mainline, Detour (Actual Drive Time), and Detour (Distance & Speed) Tabs: -Added Form Revision Dates which is also viewable when printed/saved as PDF. This is to more easily detect which revision version of the form was used. The Date Calculated field remains shown and will continue to populate with the current date when using the form.
2020-02-19 | CPI Data Tab: -Updated CPI data for 2019 (which is used for Project Year 2020). -Updated the reference information based on website changes that have occured on the United States Department of Labor site. FAQs Tab: -Updated the reference information based on website changes that have occurred on the United States Department of Labor site. -Updated the contact information from Emily and Duane, to Emily and Chris.
2019-05-17 | Lane(s) Closed on Mainline: -Added Notes box at the request of the districts. Detour (Actual Drive Time): -Added Notes box at the request of the districts. Detour (Distance & Speed): -Added Notes box at the request of the districts.
2019-02-05 | CPI Data Tab: -Updated CPI data for 2018 (which is used for Project Year 2019).
2018-10-29 | Lane(s) Closed on Mainline: -Updated language regarding how to obtain AADT for PLCS segments that use ATRs (use MS2 instead).
2018-10-23 | Lane(s) Closed on Mainline: -Updated to change from cost per 15 minutes per lane to cost per minute per lane. FAQs Tab: -Minor updates. Overall: -General format and cell shading changes.
2018-10-17 | No Lanes Closed: -This tab has been removed due to variable work zone speed limits causing the applicability of the calculations to decline. Disincentives related to Digital Speed Limit (DSL) Sign Assemblies are now found in SS 808. Lane(s) Closed on Mainline (NEW): -Added new tab for lanes closed on the mainline. This is to be used to calculate disincentives for lane closures. FAQs Tab: -Updated to reflect the other changes made. Added 5 additional FAQs regarding Lanes(s) Closed on the Mainline and No Lanes Closed tabs.
2018-02-02 | CPI Data Tab: -Updated CPI data for 2017 (which is used for Project Year 2018). -Changed future year assumed percentage increase from 3% to 2% based on the most recent annual changes reported in the CPI data over the past decade. [From 2008 to 2017 the average % change per year was: 3.8, -0.4, 1.6, 3.2, 2.1, 1.5, 1.6, 0.1, 1.3, and 2.1; 1.69% on average] -Included future year project years up to 2030. FAQs Tab: -Updated email addresses. -Clarified that the 2008 car/truck cost values were provided to ODOT from FHWA Traffic Monitoring & Survey Division in early 2010. -Updated links to Bureau of Labor Statistics website. -Updated the examples to be more current and reflect the 2% future projections rather than the 3% that was used previously.
Prior to 2/2/2018 | Revisions prior to 2/2/2018 are not captured here in this log. This log was added on 2/9/2022 and was back populated with data going back to the 2/2/2018 revision only.