## Spring 26 crack seal
FY | County | Route | MM Start | MM End
26 | SEN | SR 53 | 0 | 8
26 | SEN | SR 231 | 0 | 7
26 | SEN | US224 | 14.8 | 28
26 | SEN | SR 101 | 2 | 14.82
26 | WOO | US6 | 25.386 | 25.44 | INTERESECTION AT 6/23 Paving contracts have avoided the intersection in 3 directions. Needs crack sealed or paved if possible.
26 | SAN | US6 | 0 | 0.114 | INTERESECTION AT 6/23 Paving contracts have avoided the intersection in 3 directions. Needs crack sealed or paved if possible.
26 | WOO | US23 | 1.01 | 6.52
26 | WOO | US23 | 11.837 | 21.047 | Crack sealed 3 years ago. Already showing new cracking.
26 | SAN | US23 | 11.837 | 21.047 | Crack sealed 3 years ago. Already showing new cracking.
26 | WOO | SR25 | 11.921 | 19.662 | Area near Meta entrance will need cleaned prior to them sealing this area.
26 | WOO | SR582 | 0 | 6.58 | Could be skipped if we think it will last till project sells. Project scheduled for FY27 – Pavement in horrible condition between SR25 and IR75. Per Andrew B.
26 | WOO | SR199 | 15.801 | 18.7 | Including ramp from US6 to NB SR199 – Chipseal in 2027
26 | WOO | SR64 | 11.45 | 12.21 | Paving project in FY27 stopping at Reitz Rd. Crack seal to Waterville Bridge, including the Roundabout.
26 | WOO | SR65 | 11.43 | 13.9 | Lines bounce in and out of Corp Limits for Perrysburg. Entire 11.43 - 16.27 could be done inside corp
26 | WOO | SR65 | 14.91 | 16.27 | Lines bounce in and out of Corp Limits for Perrysburg. Entire 11.43 - 16.27 could be done inside corp
26 | WOO | SR281 | 1.09 | 15.09 | In and out of Wayne and Bradner. Could be done inside of the corps
26 | WOO | SR281 | 19.47 | 21.62 | In and out of Wayne and Bradner. Could be done inside of the corps
26 | WOO | SR281 | 22.27 | 23.8 | In and out of Wayne and Bradner. Could be done inside of the corps
26 | WOO | SR281 | 24.61 | 25.5 | In and out of Wayne and Bradner. Could be done inside of the corps
26 | WOO | SR235 | 10.04 | 13.11 | 2nd Chipseal in 2027
26 | WOO | Andrew B | NOTE |  | Can you add language that has them crack seal up to the but joints on intersections. It seems that they are crack sealing straight through them most of the time. This seems to be where our failures are starting now with them not getting all the way over.
26 | OTT | SR163 | 4.05 | 9.98
26 | OTT | SR105 | 0 | 2.71
26 | OTT | SR269 | 4.29 | 5.46
26 | OTT | SR579 | 0 | 8.32
26 | HEN | SR18 | 12 | 14
26 | HEN | SR18 | 17.46 | 18.47
26 | HEN | SR281 | 0 | 5.7
26 | HEN | SR34 | 0 | 3.82
26 | HEN | SR108 | 0 | 5.27
26 | HEN | SR108 | 6.35 | 14.96
26 | SAN | US6 | 23.43 | 32.43 | CENTER LINE ONLY
26 | SAN | US20 | 6.24 | 10.23 | WB ONLY BOTH LANES
26 | WIL | Eliott R. note |  |  | No routes this year
26 | NOP | Tom P |  |  | Will do themselves on nights
26 | LUC | Tom P |  |  | Will do themselves on nights
26 | FUL | Nick Miller note |  |  | Fulton county does not have any locations for the contract crack sealers this year. We have a few short routes that we plan to get crack sealed with county forces.
26
26
26
26
26
26
26
26
26
26
26
26
26
26
26
26
26
26
26
26
26
26
26
26
26