## Stage 2-3
PID 119042 |  |  | Last Updated: | 10/2/2025 - bbb
FRA-62 DRAINAGE IMPROVEMENTS
| DATE SENT | CORRESPONDENCE | RESPONSE DATE | CONFLICT? (YES or NO) | RESPONSES
CABLE | 2024-01-05 | Cover Letter and Utility Plan Set sent via email. |  | ?
Breezeline (fka WOW) | 2025-07-02 | Cover Letter and Utility Plan Set sent via email.
3675 Corporate Drive
Columbus, Ohio 43231 | 2025-10-02 | Calls to number provided for Josh Keen receive a busy signal.
Attn.: Josh Keen
Cell: 614-948-4611
Email: DL_CMHFR@ATLANTICBB.COM
Email: jborreson@breezeline.com
Email: mfrey@breezeline.com
ELECTRIC/CABLE | 2024-01-05 | Cover Letter and Utility Plan Set sent via email. | 2024-01-16 | YES | Attached are the facilities that AT&T has in the area of this project. Cables are not drawn to scale. For exact locations call OUPS.
AT&T (fka SBC) | 2025-07-02 | Cover Letter and Utility Plan Set sent via email.
111 N 4th St.
Columbus, Ohio 43215
Attn.: Donald G. Marshall Jr.
Cell: 614-216-2396
AT&T Repair Service: 888-611-4466
Damage Prevention: 937-296-3929
*Email: dm619w@att.com
Email: G01553@att.com
Email: tl9569@att.com
Email: KG1963@att.com
Email: BT2178@att.com
COMMUNICATION/CABLE | 2024-01-05 | Cover Letter and Utility Plan Set sent via email. | 2024-01-05 |  | Samuel Lutz no longer in Charter's construction coordinator department. New POC; Chris Hamilton.
Charter Communications/Spectrum (aka Time Warner Communications) | 2025-07-02 | Cover Letter and Utility Plan Set sent via email. | 2025-07-07 | YES | Spectrum has Aerial facilities currently attached to existing utility poles marked orange, mainly on the east side of Harrisburg Pike. If these poles are to be relocated, please provide plans with new pole locations and footages / Pole Proposal from the power company – Pole Owner. We do also have some underground in the area that does not look like it will be in conflict. I have attached a print with the locations of our facilities including fiber in the area. Please let us know if you need anything further.
3760 Interchange Rd.
Columbus, Ohio 43204
Attn: Samuel Lutz Chris Hamilton
Office: 614-481-5074
Email: DL-MOH-CONSTRUCTION-FRELO-TEAM@charter.com
Email: Chris,Hamilton@charter.com
COMMUNICATION/CABLE | 2024-01-05 | Cover Letter and Utility Plan Set sent via email. | 2025-10-02 | YES | Verizon has cable buried along the East side of US 62. See attachment
Verizon cable is confirmed to be on the West Side of US 62 - See attached.
Verizon Business | 2025-07-02 | Cover Letter and Utility Plan Set sent via email.
757 Commerce Court
Lewis Center, OH 43035 | 2025-10-02 | Called Mr. Jones. Spoke with him briefly to confirm he had received our Stage 3 submission (he had) and I wanted him to let me know whether or not Verizon had any facilities within the limits of the proposed work. Call back number was left with him to contact after he had a chance to review the plans.
Attn: Maurice Jones
Cell: 614-593-6685
Attn: Bob Dillow
Cell: 614-816-0361
Email: vz.net.columbus@verizon.com
Email: Brian.ansel@verizon.com
Also Email: Terry.shumate@verizonwireless.com
Also Email: John.cornell@verizonwireless.com
Also Email: michael.hennon@verizonwireless.com
Also Email: michael.bondy@verizonwireless.com
Also Email: sven.christianson@verizonwireless.com
ELECTRIC | 2024-01-05 | Cover Letter and Utility Plan Set sent via email. | 2024-01-05 | NO | From my review of these plans and the AEP Distribution maps of the area, it appears we should not have any conflicts with construction.
|  |  | 2024-01-05 | NO | AEP telecom has no fiber in the area of your construction project along US 62 in Jackson TWP.
AEP (City Projects/Distribution) | 2025-07-02 | Cover Letter and Utility Plan Set sent via email.
Engineering Liaison Coordinator |  |  | 2025-07-03 | NO | AEP - Pete Spicer called (614-648-3461), after reviewing stage 3 plans AEP is clear of the proposed work area
777 Hopewell Drive 850 Tech Center Drive
Heath, OH 43056 Gahanna, Ohio 43230
Office: 740-348-5322 614-883-6831
AEP Solution Center: 800-277-2177
Attn: Paul Paxton
Email: ptpaxton@aep.com
Also: Alveson Morgan
Email: aemorgan@aep.com
Also: Una Blanusa, AEP Telecon
Email: ohfiberrelocate@aep.com
GAS | 2024-01-05 | Cover Letter and Utility Plan Set sent via email. | 2024-01-17 | YES | I have reviewed the plan set and it appears that our main looks to be correct on the plan set. It appears that there will be potential conflicts with the service lines to some of our customers with the installation of the new storm lines. Once Stage 2 plans have been developed, please send them to me so I can schedule digs for our service lines to confirm depths to determine if we will be in conflict.
Columbia Gas of Ohio | 2025-07-02 | Cover Letter and Utility Plan Set sent via email. | 2024-05-15 | - | Contacted by Ross Householder to see what the clear date is for the project.
Public Projects Coordinator
3550 Johhny Appleseed Court | 2025-10-02 | Called Mr. Caldwell's cell phone and left a message requesting he contact me to confirm he had received our submittal on July 2, 2025 and if in his review of those plans he identified any concerns. Phone number to contact Resource International at was left. (It should be noted that the Office number at left was called twice and announcement received was that the number is no longer in service.)
Columbus, OH 43231
Attn: Rob Caldwell
Leader Field Engineering
Office: 614-818-2104
Cell: 614-370-1906
Customer Service: 1-800-344-4077
Damage Prevention: 1-866-632-6243
Email: columbiagas_columbuseng@nisource.com
Also Email: rcaldwell@nisource.com
FRANKLIN COUNTY | 2024-01-05 | Cover Letter and Utility Plan Set sent via email. | 2024-01-08 | NO | Franklin County Department of Sanitary Engineering does not have any water or sanitary sewer infrastructure in the area of work as shown in the plans.
Franklin County Sanitary Engineers | 2025-07-02 | Cover Letter and Utility Plan Set sent via email. | 2025-08-19 | NO | Franklin County Department of Sanitary Engineering does not own any of the infrastructure in the project area and has no comments.
280 E. Broad St., Suite 201
Columbus, Ohio 43215-4520
Attn.: Stephen A. Renner Ryan Stowe
Direct Office: 614-525-5850 614-525-4524
Main Office: 614-525-3940
Fax: 614-525-5210
Email: sarenner@franklincountyohio.gov
Email: rjstowe@franklincountyohio.gov
FRANKLIN COUNTY | 2024-01-08 | Cover Letter and Utility Plan Set sent via email. | 2024-01-10 |  | James Ramsey - Please see my comment attached. Most of my comments are intended to be advisory/helpful.
|  |  | 2024-01-10 |  | Steve Buskirk - I had two additional comments related to utilities. Please see attached.
Franklin County Drainage Engineers | 2025-07-02 | Cover Letter and Utility Plan Set sent via email.
280 E. Broad St., Suite 201 970 Dublin Road |  |  | 2025-07-12 | NO | Hi Jim, The request appears to be a utility locate request for any Franklin County infrastructure that may be in the project area. The work proposed in the referenced plan is all located within ODOT’s ROW along US 62 so we will not need to approve the plan. Liz, Can Utilities take a look at the plan to confirm any County infrastructure is properly shown? All, If the team wants to provide informal “consideration” comments to ODOT, some items you may want to look at include: Drainage - “System A” in the plan appears to include work on the Brintlinger and Patzer Ditch within the ODOT ROW, north of Beatty Rd. Drainage - “System C” is in proximity to Patzer Ditch, south of Rensch Rd, but again within the ODOT ROW. Mobility - MOT on unincorporated roads – Beatty Rd, Orders Rd, Rensch Rd, Casa Blvd (Township), Grove City Rd (City/County) As our office has no jurisdiction on this plan so I will not be setting up a formal review. If Utilities, Drainage, or Mobility have any input to share please send it directly to Kevin Jones with Resource International, Inc. kevinj@resourceinternational.com Please let me know if there are any questions. Jim just has two comments, refer to pdf's: update address for Franklin County Engineer. And on planset pg 16 "where the pipe is shallow and close to the road, consider if this is the type of pipe and backfill you want."
Columbus, Ohio 43215-4520
Attn.: Jim Ramsey
Main Office: 614-525-7469
Email: jramsey@franklincountyengineer.org