## Utility Log
OHIO811: Ohio Utility Protection Service (OUPS) 1-800-362-2764 or 811 |  | PID: 120103 | Log Last Updated By: | (GPD) | Last Updated Date: | 2025-12-30
PM: Daniel Soroka(B&N PM); Travis McCarty (GPD PM); Jessica Burlett (Utility Coordinator) |  | PROJECT NAME: FRA-Cemetery Rd-SUP | Project limits and description: Construction of shared use path (SUP) on the south side of the Cemetery Road from Britton Parkway to Trueman Blvd. includes a new pedestrian bridge over I-270 and pedestrian underpass under the eastbound Cemetery Rd to southbound I-270 ramp. the Cemetery Rd EB to I-270 SB entrance ramp and I-270 NB to Cemetery Rd EB exit ramp will be realigned to accommodate the new SUP. Traffic signal upgrades are proposed at 5 intersections, and other minor modifications are proposed to improve pedestrian safety.
|  |  |  | SURVEY & LOCATING | [7 empty] | DESIGN | [9 empty] | UG or OH
Utility Company | Telephone | Contact | Project Notice to Proceed | OHIO811 Design Ticket Placed (B403900247-00B, B403900268-00B, B403900287-00B, B403900324-00B, B403900377-00B, B403900410-00B, A403901446-00A, A403901497-00A): | OHIO811 Design Ticket Positive Response Code: | Received Record Plans: (Yes/No) | OHIO811 Markings Ticket Placed: (B403900253-00B, B403900272-00B, B403900292-00B, B403900325-00B, B403900384-00B, B403900411-00B, A403901452-00A, A403901509-00A) | OHIO811 Markings Ticket 48hr Positive Response: | Expected Date of Markings: | Facilities within project limits: (Yes/No) | Level A Test Hole Required? (Yes/No) | Sent Stage 1 Plans | Received Comments | Sent Stage 2 | Received Comments | Sent Stage 3 Plans | Received Comments | FINAL TRACINGS SENT | Received Comments | Conflict (Yess/No) | Communication/Decisions Made/Remarks:
Name and Address | No. | Name
ELECTRIC | [11 empty] | 2024-11-01 |  | 2025-05-08 | 2025-05-13 | [5 empty] | 2/15/2024 - Record plans provided per email from agt_comm@irth.com. 12/04/2024 - An updated link to the plans set was requested and provided to Mr. Matthews. 01/31/2025 - Mr. Matthews emails to ackonledge AEP is behind in reviews and requests a revised link to the Stage 1 plans. 02/10/2025 - Plans again sento to Mr. Matthews on his request for a third time. He ackonledges he is recieving the links and does has access to the plans. States will have review comments to B&N/GPD "in 2 weeks".
AEP Ohio
700 Morrison Rd | 614.883.6802 | Brent Gates |  | 2024-02-08 | 001 - No Conflict | Yes | 2024-02-08 | 002 Marked | 2024-02-12
Gahanna, OH 43230 |  | bmgates@aep.com
agt_comm@irth.com
Send plans to:
Mr. Bob Matthews
rematthews@aep.com
FIBER & PHONE | [11 empty] | 2024-11-01 | 2024-12-09 | 2025-05-08 | [6 empty] | 2/09/2024 - No Conflict reported per USIC email from dsn-notify@tickets.811tickets.com. 12/09/2024 - Mr. Connell provided markups and plats related to Stage 1. The pedestal on Page 18 can be removed from the proposed path is the single conflict noted.
AT&T Legal Mandate Team, Columbus, Ohio |  | AT&T Columbus Ohio Legal Mandate - General Inbox
Access Construction & Engineering |  | g01553@att.com |  | 2024-02-08 | 001 - No Conflict | No | 2024-02-08 | 001 - No Conflict | 2024-02-12
Send Plans to:
AT&T Services, Inc. | 281-352-3631 | Steve Connell
111 N. 4th Street, 8th Floor, Columbus, Ohio 43215 |  | sc2732@att.com
FIBER & PHONE | [11 empty] | 2024-11-01 | 2024-11-05 | 2025-05-08 | 2025-06-09 | [5 empty] | 2/09/2024 - No Conflict reported per USIC email from dsn-notify@tickets.811tickets.com. 11/05/24 - MCG Utilities rep (Zach Hopper @ zach.hopper@mcgutilities.com) responded and provided pdf stating the AT&T Transmission is "uninvolved" in the project limits.
AT&T Transmission | 440-610-7457 | James Schneider
Managed by: |  | Field Engineer
MCG Utilities |  | james.schneider@mcgfiber.com |  | 2024-02-08 | 001 - No Conflict | No | 2024-02-08 | 001 - No Conflict | 2024-02-12 | Yes
450 W. Willson Bridge Rd. Suite 180 |  | Chad Harkness
Worthington, Ohio 43085 |  | chad.harkness@mcgfiber.com
FIBER & PHONE | [11 empty] | 2024-11-01 |  | 2025-05-08 | [6 empty] | 2/09/2024 - No Conflict reported per USIC email from dsn-notify@tickets.811tickets.com.
Charter Communications |  | Jim O'Reilly |  | 2024-02-08 | 001 - No Conflict | No | 2024-02-08 | 001 - No Conflict | 2024-02-12
Jim.OReilly@charter.com>
Kevin Rich
kevin.rich1@charter.com
Joseph.Candler1@charter.com
dl-southern-ohio-outside-plant@charter.com
ELECTRIC & TRAFFIC | [11 empty] | 2024-11-01 |  | 2025-05-08 | 2025-05-20 | [5 empty] | 2/09/2024 Record plans provided per email from BJWilliamson@columbus.gov.
City of Columbus - Fiber & Traffic | 614.645.0423 | Benjamin J Williamson
1881 E 25th Ave | 614.633.9780 | Engineering Associate 3 |  | 2024-02-08 | 008 - Design Notification | Yes | 2024-02-08 | 001 - No Conflict | 2024-02-12 | Yes
Columbus, OH 43219 |  | BJWilliamson@columbus.gov
GAS | [11 empty] | 2024-11-01 | 2024-11-20 | 2025-05-08 | [6 empty] | 2/09/2024 Record plans provided per email from Harvey \ Michelle \ J <MHarvey@nisource.com>. 11/20/2024 - Mr. Ben Day responded having reviewed Stage 1 plans and stated no conflicts are expected. Mr. Day stated Columbia Gas' last internal survey listed the gas main to having a cover of 11ft-14ft.
Columbia Gas | 614.818.2104 | columbiagas_columbuseng@nisource.com
3550 Johnny Appleseed Ct | 614.370.1906 | Mr. Ben Day
Columbus, OH 43231 | 800.344.4077 | bday@nisource.com |  | 2024-02-08 | 008 - Design Notification | Yes | 2024-02-08 | 001 - No Conflict | 2024-02-12 | Yes
FIBER | [11 empty] | 2024-11-01 | 2024-12-11 | 2025-05-08 | [6 empty] | 2/08/2024 Record plans provided per email from agt_comm@irth.com. 12/11/24 - Mr. Joe Tepper replied with two record plans for Britton Parkway, where the fiber conduit is out of the limits for this project.
Crown Castle | 585.455.5813 | Jon Tarnowski
2 Eastern Oval | 614.940.2462 | Manager - Fiber Construction
Ste 425 |  | jon.tarnowski@crowncastle.com |  | 2024-02-08 | 008 - Design Notification | Yes | 2024-02-08 | 001 - No Conflict | 2024-02-12 | Yes
Columbus, OH 43219 |  | Joseph Tepper
Joseph.tepper@crowncastle.com
GAS | [11 empty] | 2024-11-01 | 2024-11-05 | 2025-05-08 | 2025-05-13 | [5 empty] | 2/23/2024 No Conflict per OUPS design ticket response. 11/05/24 - Ms. Schneck provided a map and confirmed existing 10in facility is traveling on the west edge of the Conrail railroad overpass of cemetery, fromnorth/south, outside of limits.
Energy Transfer | 610.670.3258 | Deb Schneck
6075 Silica Rd |  | Encroachment Reviews Coordinator |  | 2024-02-08 | 001 - No Conflict | No | 2024-02-08 | 001 - No Conflict | 2024-02-12 | No | [9 empty] | NO
Ste A |  | Debra.Schneck@energytransfer.com
Austintown, OH 44515
FIBER & PHONE | [20 empty] | 2/09/2024 - No Conflict reported per USIC email from dsn-notify@tickets.811tickets.com.
Horizon Chillicothe Telephone | 740.772.8200 | Zach Goebbel
68 E Main St. |  | Zach.Goebbel@HorizonConnects.com |  | 2024-02-08 | 001 - No Conflict | No | 2024-02-08 | 001 - No Conflict | 2024-02-12 | No |  | 2024-11-01
Chillicothe, OH 45601
INTERSTATE FIBER OPTIC | [11 empty] | 2024-11-01 |  | 2025-05-08 | [6 empty] | 2/08/2024 Record plans provided per email from cl_irth_comm@irth.com. 12/10/2024 - Lumen automated response explains new process to upload plans for review at portal "RelocationIntakeWebPublic" https://relocation-request.lumen.com/rmpp/#/relocationreq 12/13/24 - Ms. Haley Woods requested an updated link to download plans as the original has expired. A link was sent directly to her email address. 01/13/2025 - Email sent to Ms. Woods requesting review comments and acknowledgement of Stage 1 plans.
Lumen | 1-800-283-4237 | Automated Response from:
f.k.a CenturyLink, Level 3 or Qwest |  | cl_irth_comm@irth.com |  | 2024-02-08 | 008 - Design Notification | Yes | 2024-02-08 | 001 - No Conflict | 2024-02-12 | No
a.k.a. Brightspeed |  | Send Plans for Review:
relocation@lumen.com
and
https://www.lumen.com/en-us/resources/network-maps.html |  | https://relocation-request.lumen.com/rmpp/#/relocationreq
Lquid Pipeline (Petroleum) | [11 empty] | 2024-11-01 | 2024-11-09 | 2025-05-08 | 2025-05-15 | [5 empty] | 2/15/2024 KMZ provided per email from Ayers, Angela C. <acayers@marathonpetroleum.com>. 11/09/2024 - Mr. Morris replied to update contact information to his, and stated he is not expecting any "major conflict". Mr. Morris agrees to the locations of the 6inch pipeline depicted as shown in Stage 1 submittal. Marathon is interested in the hard resurfacing and overlay, then provided Marathon's general requirements. A Marathon representative is required to be onsite for all work within 50’ of a Marathon pipeline. General coordination to take place through OUPS 811. Hard surfacing removal within 25’ horizontally of a Marathon pipeline to be completed via minimal milling or sawcut and soft removal. Any breaking, hammering, or vibratory demolition within this space is restricted for the safety of the pipeline. There shall be no vibratory compaction take place within 15’ horizontally of a Marathon pipeline. Static compaction is acceptable. Mechanical sub-grade treatment activity is restricted within 15’ horizontally of a Marathon pipeline. Material within the space is generally excavated, moved away from the area, treated, and placed back. | UG
Marathon Pipeline |  | Landon Morris
Marathon Pipe Line LLC | Mobile: (419)957-7792 | Senior Right of Way Specialist |  | 2024-02-08 | 001 - No Conflict | Yes | 2024-02-08 | 001 - No Conflict | 2024-02-12 | Yes
1900 West Avenue H |  | lrmorris@marathonpetroleum.com
INTERSTATE FIBER OPTIC | [11 empty] | 2024-11-01 |  | 2025-05-08 | [6 empty] | 2/08/2024 No Conflict per emails from donotreply@verizon.com.
Verizon | 254-721-8977 (cell) | Mr. Robert "Bob" Dillow
f.k.a. MCI |  | Outside Plant Engineer |  | 2024-02-08 | 008 - Design Notification | Yes | 2024-02-08 | 001 - No Conflict | 2024-02-12
8800 Governors Hill Drive |  | robert.dillow@verizon.com
Cincinnati, Ohio 45249 |  | OH811 Ticket managed by:
Team Fishel
TRAFFIC | [13 empty] | 2025-05-08 | [6 empty] | 2/08/2024 Record plans provided per email from Dean.Mutlak@dot.ohio.gov.
ODOT 6 Traffc (District 6) | 740.833.8267 | Dean Mutlak, EIT
Traffic Operations Dept. | 614.230.4681 | Transportation Engineer 1, D06 Highway Management |  | 2024-02-08 | 008 - Design Notification | Yes | 2024-02-08 | 002 Marked | 2024-02-12 |  |  | 2024-11-01
400 East William Street |  | Dean.Mutlak@dot.ohio.gov
Delaware, OH 43015
TRAFFIC/ ELECTRIC | [13 empty] | 2025-05-08 | [6 empty] | 2/09/2024 Record plans provided per email from Sam Reed <Sam.Reed@sam.biz>. 11/06/2024 - Per ODOT ITS general email request, all files for review must be uploaded via LiquidFiles Frile Transfer (ODOT provided link).
ODOT Central ITS | (614) 948-0537 office | Mr. Evan Kraus
Managed by: | (614) 787-4263 cell | Office Technician II - SUE, GPS QA
Surveying and Mapping, LLC (SAM) |  | Evan.Kraus@sam.biz
929 Eastwind Drive, Suite 201 |  | Send Design Plans to:
Westerville, Ohio 43081 | 614-387-0695 | Mr. Paul Beck |  | 2024-02-08 | 008 - Design Notification | Yes | 2024-02-08 | 001 - No Conflict | 2024-02-12 |  |  | 2024-11-01
Paul.Beck@dot.ohio.gov
Construction Coordination with:
| 614-644-7892 | Mr. Drew Janek
drew.janek@dot.ohio.gov
INTERSTATE FIBER OPTIC | [11 empty] | 2024-11-01 |  | 2025-05-08 | 2025-06-01 | [5 empty] | 2/23/2024 No Conflict per OUPS design ticket response.
Zayo Fiber Solutions |  | Colton Woodruff
1525 Rockwell Ave | 216.925.4343 | colton.woodruff@zayo.com
Cleveland, OH 44114 |  | Zayo Fiber / Cobbfendley |  | 2024-02-08 | 001 - No Conflict | No | 2024-02-08 | 001 - No Conflict | 2024-02-12
Kayla Quinton
Kquinton@Cobbfendley.com
ELECTRIC, FIBER, SEWER, STORM, WATER | [11 empty] | 2024-11-01 | 2024-11-05 | 2025-05-08 | [6 empty] | 2/23/2024 - No Conflict per OUPS design ticket response. 4/09/2024 - Placed request through Kiteworks (City of Hilliard) for record plans. 4/11/2024 - Emailed cfuentes@hilliardohio.gov for follow up on record plans request. 4/12/2024 - Plans provided per email from Christine Fuentes <cfuentes@hilliardohio.gov>. 11/04/24 - Mr. Rausch provided sanitary records (1977); The city owns an abandoned in place 16" force main sanitary sewer, with an average depth of 5ft, crossing Cemetery Road and the eastbound-to-southbound ramp to I-270 . The City assumes the sanitary is ductile iron and appears to cross the proposed 15” storm sewer (D-20 to S-21), and maybe even downstream of D-21. The sewer can be removed & disposed of wherever it’s necessary. The city require that wherever the force main is cut, the ends be capped or plugged to eliminate ground water from getting into the abandoned sewer.
City of Hilliard |  | Ms. Christine Fuentes
3800 Municipal Way | 614.334.2457 | GIS Associate
Hilliard, Ohio 43026 |  | cfuentes@hilliardohio.gov |  | 2024-02-08 | 001 - No Conflict | Yes | 2024-02-08 | 001 - No Conflict | 2024-02-12
Clark Rausch, City Engineer, crausch@hilliardohio.gov
Jeff Cox, Project Engineer, jcox@hilliardohio.gov

## OHIO811 Response Codes
01- No Conflict | Underground facilities operated by this member are not in conflict based on information provided in the Excavation Request.
02- Marked | Underground facilities operated by this member at the site of proposed excavation have been marked up to the privately owned facility.
03- Excavation Request Cancelled | Excavator has cancelled this excavation request
04- Locator Coordination | Locate request has not been completed. Locator has/will contact the excavator to coordinate markings.
05- Facility Operator Coordination | Locate request has not been completed. Facility Owner or Operator will contact the excavator to coordinate markings.
06- High Profile or Critical Facility | Facility Owner or Operator requests to be present for the excavation in accordance with ORC 3781.31 (A). Excavator must provide notification of at least one full working day prior to commencing excavation
07- Complex Project (LPRJ) | This response is designated for use with a Complex Project notification only
08- Design Notification (DSGN) | Facility Owner or Operator has completed the design request in accordance with ORC 3781.27 (C) or 153.64 (B) (2)
09- Work Complete | The Facility Owner or Operator or their representatives has deemed the excavation to have been completed prior to the legal start date
999- No Response (LATE) | The Facility Owner or Operator or its representatives has not posted a Positive Response prior to the legal start date. A “LATE” notification has automatically been sent to the Facility Owner or Operator
Not Listed as a Member

## Pending Conflict
PID #
Utility Crossing / Conflict Locations
Assumed Utility Depths (if less than 18" of separation or utility required clearance violation MUST verify with utility or relocation must occur!
Depths are based upon project experience within D6. | [8 empty] | UTILITY TYPE KEY: | Utility
Water |  |  | 4' |  |  |  | 2018-01-31 |  | T | Telephone
Sanitary Sewer |  |  | N/A -Actual | [5 empty] | C | Cable
Storm Sewer |  |  | N/A-Actual | [5 empty] | FO | Fiber Optic
Telephone, Cable |  |  | 2.5' | [5 empty] | FODB | Fiber Optic Duct Bank
Fiber Optic, Electrical |  |  | 3' | [5 empty] | E | Electric
GAS |  |  | 3' | [5 empty] | EDB | Electric Duct Bank
GAS PIPELINE |  |  | 4' | [5 empty] | ST | Storm
[9 empty] | SA | Sanitary
[9 empty] | W | Water
[9 empty] | G | Gas
[9 empty] | GHP | Gas High Pressure
[9 empty] | GPL | Gas Pipeline
[9 empty] | L OR ITS | ODOT OWNED
Ref. No. | Sheet No. | Starting Station | Offset & (RT or LT) | Ending Station | Offset & (RT or LT) | Length | Conflict Location Description | Possible Conflict with what? | # of inches of separation between Existing Utility and proposed work | Is the utility within their own easement? (Y OR N) | Utility Type- (See Key Above for Reference) | If Electric - What is Voltage of line? | Utility Owner | Conflict Resolution | Resolved by what date | Utility Clear Date (sale - 60)
WATER (W- _)