## Sheet1
Conceptual FRA-270-4262 Erection Sequence Table
Erection Phase | Construction Above | MOT | # of Night Closures | Closures are NOT permitted: |  |  | MOTEC System to System closure | MOTEC Mainline closure
|  |  |  | Mon to Fri | Sat | Sun
1 | 270 SB CD | 270 SB CD – outside shoulder closure per MT-95.45
2 | 270 SB CD 270 SB | 270 SB CD to 270 SB - closure | 3 | 5AM-11PM | 7AM-11PM | 7AM-10PM | X | X
Ex. Ramp D3 (270 SB to 70 EB) – closure
270 SB – closure
3 | 270 SB 270 NB 270 NB CD Ex. Ramp B (270 NB to 70 WB) | 270 SB – diverted to 270 SB CD | 3 | 5AM-11PM | 7AM-11PM | 7AM-10PM | X | X
270 NB - closure
270 NB CD - closure
Ex. Ramp B (270 NB to 70 WB) - closure
4 | 270 NB CD Ex. Ramp B (270 NB to 70 WB) | 270 NB CD – outside shoulder closure per MT-95.45 |  |  |  |  | X
|  | Ex. Ramp B (270 NB to 70 WB) – closure | 3 | 5AM-11PM | 7AM-11PM | 7AM-10PM
5 | Ex. Ramp B (270 NB to 70 WB) 70 WB to 270 SB | Ex. Ramp B (270 NB to 70 WB) - closure | 3 | 5AM-11PM | 7AM-11PM | 7AM-10PM | X
70 WB to 270 SB – closure
6 | 70 WB CD 70 WB 70 EB Temp Ramp C2 (270 NB to 70 EB) | Ex. Ramp H (70 WB to 270 SB) - closure | 4 | 5AM-11PM | 7AM-11PM | 7AM-10PM | X | X
70 WB - closure
70 EB - closure
Ex. Ramp D3 (270 SB to 70 EB) - closure
Temp. Ramp C2 (270 NB to 70 EB) – move traffic to Ex. Ramp C2
7 | 70 EB Ex. Ramp C2 (270 NB to 70 EB) Ex. Ramp D2 (70 EB to 270 NB) | 70 EB – closure | 4 | 5AM-11PM | 7AM-11PM | 7AM-10PM | X | X
Ex. Ramp D3 (270 SB to 70 EB) – closure
Ex. Ramp C2 (270 NB to 70 EB) - closure
Ex. Ramp D2 (70 EB to 270 NB) - closure
8 | Ex. Ramp C2 (270 NB to 70 EB) | Ex. Ramp C2 (270 NB to 70 EB) - move traffic to Temp. Ramp C2 (270 NB to 70 EB) |  |  |  |  | X
Notes:
1) MT-099.60 - Short-Term Closure of Multi-Lane Divided Highway to be utilized when swinging girders over open traffic.
2) The above table is based on one conceptual erection sequence modeled during the design phase of the project. The contractor is required to submit an erection plan for approval and can differ from this phasing.
3) Disincentive amounts per the Lane Value Contract Tables on Sheet 47.