UTILITY NOTE

GEA-322/44-08.63/14.93
PID 115876

October 18, 2024

- Bidders are advised that the following utility facilities may not be cleared from the construction area at the time of award of the contract. These utility facilities shall remain in place or be relocated within the construction limits of the project as set out below.

- All station locations listed below are approximate unless otherwise stated.

- Relocations are based on the Construction Centerline.

- If there are any discrepancies between field markings and what the highway plan indicates, please contact Steven Sasala, ODOT District 12 Utilities Coordinator 330-329-9063 prior to any subsurface work being initiated. If applicable, test hole data sheets will be provided to ODOT’s Project Engineer and the State’s Roadway Contractor at the Pre-Construction Meeting.

- All changes to relocation work as described in the Utility Note must be approved by the ODOT Project Engineer and District Utilities Coordinator. ODOT shall not be held responsible for delay claims resulting from agreements made between the utility companies and the State’s Highway Contractor without ODOT’s prior consent to the agreement.

- The State’s Highway Contractor shall notify ODOT’s Project Engineer, in writing, within 24 hours of any project related contact with a utility company.

- Company work time frames DO NOT include Ohio Revised Code 48-hour One Call requirements.

- Utility relocation work is based on the sequence of construction in the highway plan. Any changes made to the sequence of construction, after the project is sold, may impact the utility relocation completion dates.

- It should not be assumed a Company’s work, in all locations, can be performed concurrently, unless otherwise noted. The number of working days for a Company to perform their relocation work may not be consecutive.

- Non-compliance in meeting established target dates could cause ODOT to incur project delays and/or additional costs. In this regard, 5515.02 ORC gives the Department the authority to ensure project clearance and recover costs.

- For further responsibilities of the State’s Highway Contractor and Utility Companies, see the Department of Transportation Construction and Material Specifications, sections 105.07 & 107.16.

- The Companies shall comply with the following requirements, in regards to restoration of areas within the project limits, where their facilities have been relocated due to proposed project work:

  - All excavations shall be backfilled with suitable material and compacted to ODOT specifications.

  - Mounding of dirt over trenches will not be permitted. Preliminary cleanup will be required while working and unsuitable material hauled away.

  - Trenches are not to remain open overnight, other than what is needed to start the next day’s work. Those trenches shall be covered with a steel plate and designated with safety cones or barrels.

  - All disturbed right of way shall be restored to its original condition or better, and seeded and mulched as per Item 659, ODOT specifications.

  - All trenched driveway approaches shall be backfilled with granular material and compacted to ODOT specifications. Driveway surfaces shall be replaced in kind.

  - The State’s Highway Contractor may need to coordinate his underground work with a/all Utility Companies within the project limits.

CEI - The Illuminating Co. – John Zassick - (440) 546-8706

The Company has aerial distribution power lines within the project limits as shown in the plans.

The 13,200 V crossing SR 44 between poles 568985 and 863943 will not permit OSHA clearances during culvert construction. De-energize and or dropping is approved without conditions.

At the US 322 culvert, between poles 43360 and 43363: the 36,000 V (R-21-MF and R-22-MF) can be temporarily de-energized March 1 to May 31, by installing open disconnects just east of the work site and closing switch #46 22-MF tie to 15-ST. And closing switch #47 21-MF tie to 17-ST. Also, at Quaker Sub Close switch #21 and open switch #22. In case of an emergency, with 2 hours’ notice, we may ask to halt work so that we can put the circuits back to normal.

Also at the US 322 culvert: the 5,000 V circuit can be de-energized under the following conditions: between February 1 and May 31; shorter durations preferred; the lines can be dropped.

If modifications or de-energizing of Illuminating Co. facilities are required to permit construction activities, be advised the current line shop lead time is 16 weeks + engineering, unless new metered service. Provide written notice for any work to proceed.

Non-Illuminating Co. personnel are not permitted to hold or brace poles.

Enbridge (formerly Dominion Energy Ohio) – Joshua Mis (330) 571-9135

The Company has a gas line to the south and to the north of the SR-44 existing culvert.  Both lines appear to be outside of the project work and not in conflict.

If during construction any perceived issue, conflict, or problem occurs with an Enbridge facility, the authorized agent for the project should notify Enbridge immediately by contacting the designer listed above or by email to relocation@dominionenergy.com.  Enbridge will make best efforts to work with the authorized agent for the project and the contractor to resolve conflicts and prevent delays.

The Company does not have facilities within the US-322 project site.

Northeast Ohio Natural Gas Corp. – Tim Reilly (440) 728-0575

The Company has a 4” gas line on the south side of US-322 that runs beneath the existing culvert and will be relocated in January 2025.

If during construction any perceived issue, conflict, or problem occurs with a Northeast Ohio Natural Gas facility, the authorized agent for the project should notify the company immediately by contacting the designer listed above or by email to treilly@neogas.com.

The Company does not have facilities within the SR-44 project site.

Charter Communication – Mark Jackson – (216)-214-7780

Charter Communication has existing overhead facilities attached to the power poles. These facilities will need to be relocated or deenergized during construction.

If during construction any perceived issue, conflict, or problem occurs with a Charter facility, the authorized agent for the project should notify Charter immediately by contacting the designer listed above or by email to MarkJackson@charter.com.

Windstream – Jeff Gulyas – (216)-385-1669

Windstream has existing overhead facilities within the SR-44 project limits crossing over the culvert and will need to be relocated.

If during construction any perceived issue, conflict, or problem occurs with a Windstream facility, the authorized agent for the project should notify Windstream immediately by contacting the designer listed above or by email eric.lacourse@windstream.com.