***ITEM 614, MAINTAINING TRAFFIC***

*A MINIMUM OF* ***1-LANE*** *OF TRAFFIC IN EACH DIRECTION SHALL BE MAINTAINED ON* ***R-5 AND R-14*** *AT ALL TIMES BY USE OF THE EXISTING PAVEMENT AND THE STANDARD DRAWINGS LISTED ON THE TITLE SHEET.*

***ALL PARKING LOTS AND CAMP ROADS ADJACENT TO R-5 AND R-14 MAY BE CLOSED DURING CONSTRUCTION IN COORDINATION WITH THE PARK MANAGER ADAM SIKORA (740-439-3521).***

*TWO-WAY TRAFFIC SHALL BE MAINTAINED AT ALL TIMES EXCEPT THAT ONE-WAY TRAFFIC WILL BE PERMITTED FOR MINIMUM PERIODS OF TIME CONSISTENT WITH THE REQUIREMENTS OF THE SPECIFICATIONS FOR PROTECTION OF COMPLETED ASPHALT CONCRETE COURSES INCLUDING REPAIRS.*

***LENGTH AND DURATION OF LANE CLOSURES AND RESTRICTIONS SHALL BE AT THE APPROVAL OF THE ENGINEER.*** *THE MAXIMUM LANE CLOSURE LENGTH SHALL BE PER* ***MT-97.12.*** *IT IS THE INTENT TO MINIMIZE THE IMPACT TO THE TRAVELING PUBLIC. LANE CLOSURES OR RESTRICTIONS OVER SEGMENTS OF THE PROJECT, IN WHICH NO WORK IS ANTICIPATED WITHIN A REASONABLE TIME FRAME, AS DETERMINED BY THE ENGINEER, SHALL NOT BE PERMITTED. THE LEVEL OF UTILIZATION OF MAINTENANCE OF TRAFFIC DEVICES SHALL BE COMMENSURATE WITH THE WORK IN PROGRESS.*

*ALL WORK AND TRAFFIC CONTROL DEVICES SHALL BE IN ACCORDANCE WITH CMS 614 AND OTHER APPLICABLE PORTIONS OF THE SPECIFICATIONS, AS WELL AS THE OHIO MANUAL OF UNIFORM TRAFFIC CONTROL DEVICES. PAYMENT FOR ALL LABOR, EQUIPMENT AND MATERIALS SHALL BE INCLUDED IN THE LUMP SUM CONTRACT PRICE FOR ITEM 614, MAINTAINING TRAFFIC, UNLESS SEPARATELY ITEMIZED IN THE PLAN.*

***WORK RESTRICTIONs***

*THE CONTRACTOR MAY ONLY WORK* ***MONDAY TO THURSDAY*** *FROM*

***7AM TO 7PM*** *DURING THE PROJECT.**ANY WORK OUTSIDE THESE HOURS, THE CONTRACTOR WILL NEED APPROVAL OBTAINED IN WRITING FROM THE PARK MANAGER.*

*ALL WORK ASSOCIATED WITH* ***CAMP ROADS (R-6, R-10, R-13, R-20, R-24, R-25) AND CAMPER PADS*** *SHALL**OCCUR FROM* ***MAY 2ND TO MAY 26TH, 2022.*** *THE CAMPGROUND WILL BE CLOSED DURING THIS TIME.* ***THE ABOVE TIME RESTRICTIONS WILL NOT APPLY.***

*NO WORK SHALL OCCUR* ***MEMORIAL DAY*** *WEEKEND STARTING AT 12PM THE FRIDAY BEFORE UNTIL 7AM THE TUESDAY AFTER MEMORIAL DAY.*

*NO WORK SHALL OCCUR* ***JULY 4TH*** *WEEKEND STARTING AT 12PM THE FRIDAY BEFORE UNTIL 7AM THE TUESDAY AFTER JULY 4TH.*

*liqudated damages per* ***cms 108.07*** *shall be assessed IF the dates stated above ARE NOT MET.*

***PROJECT COMPLETION DATE***

***AUGUST 15TH, 2022***

***NOTIFICATION OF ROAD CLOSURE OR RESTRICTIONS***

*THE CONTRACTOR WILL ADVISE THE PROJECT ENGINEER A MINIMUM OF TWENTY-ONE (21) DAYS PRIOR TO THE FOLLOWING: THE START OF CONSTRUCTION ACTIVITIES, LANE RESTRICTIONS, LANE CLOSURES, AND OR ROAD CLOSURES. THE PROJECT ENGINEER WILL FORWARD THIS INFORMATION TO THE FOLLOWING:*

*DISTRICT PUBLIC INFORMATION OFFICER (PIO) BY FAX AT (614) 887-4510 OR EMAIL AT* *D05.PIO@DOT.STATE.OH.US*

*DISTRICT PERMIT SECTION BY FAX AT (614) 887-4525 OR EMAIL AT* *BRIAN.BOSCH@DOT.STATE.OH.US*

*CENTRAL OFFICE SPECIAL HAUL PERMITS SECTION BY FAX AT (614) 728-4099 OR EMAIL AT* *HAULING.PERMITS@DOT.STATE.OH.US*

*THE PIO WILL, IN TURN, NOTIFY THE PUBLIC, THE LOCAL EMERGENCY SERVICES, AFFECTED SCHOOLS AND BUSINESSES, AND ANY OTHER IMPACTED LOCAL PUBLIC AGENCY OF ANY OF THE ABOVE MENTIONED ITEMS, VIA MEDIA SOURCES.*

***DROP-OFFS IN WORK ZONES***

*DROP-OFFS THAT DEVELOP DURING CONSTRUCTION OPERATIONS AND THAT ARE NOT OTHERWISE PROVIDED FOR IN THE PLANS SHALL BE TREATED AS SHOWN ON STANDARD DRAWING* ***MT-101.90****. WHERE THE PLANS DO NOT PROVIDE SPECIFIC ITEMS FOR LABOR, EQUIPMENT, OR MATERIALS TO IMPLEMENT THE DROP-OFF TREATMENTS SPECIFIED, THEY SHALL BE INCLUDED FOR PAYMENT IN THE LUMP SUM BID FOR ITEM 614, MAINTAINING TRAFFIC.*

***BUTT JOINT***

*ALL BUTT JOINTS SPECIFIED OR SHOWN IN THE PLAN SHALL BE AS PER STANDARD DRAWING* ***BP-3.1*** *UNLESS OTHERWISE SHOWN.*

***ITEM 614, WORK ZONE PAVEMENT MARKINGS***

*THE CONTRACTOR SHALL PLACE ALL WORK ZONE PAVEMENT MARKINGS IN ACCORDANCE WITH* ***CMS 614.11*** *AND STANDARD DRAWING* ***MT-99.20*** *UNLESS OTHERWISE DIRECTED BY THE ENGINEER. THE QUANTITIES BELOW ARE FOR PLACEMENT OF TEMPORARY MARKINGS ON THE PROPOSED ASPHALT CONCRETE COURSE(S).*

***ITEM 614, WORK ZONE CENTER LINE, CLASS III, 642 PAINT***

***(SURFACE): 4.25 MILE***

***ITEM 614, WORK ZONE CHANNELIZING LINE, CLASS III, 642 PAINT***

***(SURFACE): 100 FEET***