## Auto Table
|  |  |  | STRUCTURE REPAIR (HAM-71-1440) | (100% 01/IMS/BR FUNDING) |  |  |  |  | (01/NHS/BR FUNDING SPLIT)
ITEM | EXTENSION | TOTAL | UNIT | DESCRIPTION | ABUTMENT | PIERS | SUPERSTRUCTURE | GENERAL | REFERENCE
202 | 11203 | LS | LUMP | PORTIONS OF STRUCTURE REMOVED, OVER 20 FOOT SPAN, AS PER PLAN | LUMP |  | LUMP |  | 15
503 | 11100 | LS | LUMP | COFFERDAMS AND EXCAVATION BRACING | LUMP
503 | 21300 | LS | LUMP | UNCLASSIFIED EXCAVATION | LUMP
202 | 75260 | 516 | FT | VANDAL PROTECTION FENCE REMOVED |  |  | 516
509 | 10001 | 5309 | LB | EPOXY COATED REINFORCING STEEL, AS PER PLAN | 564 |  | 4745
509 | 20000 | 200 | LB | REINFORCING STEEL, REPLACEMENT OF EXISTING REINFORCING STEEL | 100 |  | 100 |  | 15
509 | 25001 | 9318 | LB | UNCOATED REINFORCING STEEL, AS PER PLAN | 1051 |  | 8267 |  | 15
510 | 10001 | 1664 | EA | DOWEL HOLES WITH NONSHRINK, NONMETALLIC GROUT, AS PER PLAN | 176 |  | 1488 |  | 15
511 | 53014 | 104 | CY | CLASS QC3 CONCRETE, MISC.: LIGHT WEIGHT SUPERSTRUCTURE CONCRETE WITH QC/QA, AS PER PLAN (DECK, PARAPET AND SIDEWALK) |  |  | 104 |  | 16
511 | 53014 | 6 | CY | CLASS QC3 CONCRETE, MISC.: SUBSTRUCTURE CONCRETE WITH QC/QA, AS PER PLAN (WING WALLS & PARAPETS) | 6 |  |  |  | 17
511 | 53014 |  | CY | CLASS QC3 CONCRETE, MISC.: APPROACH SLAB CONCRETE WITH QC/QA, AS PER PLAN (APPROACH SLAB & APPROACH SLAB SIDEWALK) |  |  |  |  | 17
512 | 10050 | 356 | SY | SEALING OF CONCRETE SURFACES (NON-EPOXY) |  |  | 325 | 31
512 | 10101 | 698 | SY | SEALING OF CONCRETE SURFACES (EPOXY-URETHANE), AS PER PLAN | 179 | 3 | 516 |  | 18
512 | 10600 | 26 | FT | CONCRETE REPAIR BY EPOXY INJECTION | 26
512 | 74000 | 1023 | SY | REMOVAL OF EXISTING COATINGS FROM CONCRETE SURFACES | 179 | 3 | 841
512 | 74500 | 261 | FT | REMOVAL OF EXISTING PAVEMENT MARKING |  |  | 261
513 | 10200 | 1087 | LB | STRUCTURAL STEEL MEMBERS, LEVEL UF |  | 1087
514 | 50 | 398 | SF | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL |  | 398
514 | 56 | 398 | SF | FIELD PAINTING EXISTING STRUCTURAL STEEL, PRIME COAT |  | 398
514 | 60 | 398 | SF | FIELD PAINTING STRUCTURAL STEEL, INTERMEDIATE COAT |  | 398
514 | 66 | 398 | SF | FIELD PAINTING STRUCTURAL STEEL, FINISH COAT |  | 398
514 | 504 | 9 | MNHR | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL |  | 9
514 | 10000 | 4 | EACH | FINAL INSPECTION REPAIR |  | 4
514 | 21001 | LS | LUMP | FIELD PAINTING OF DAMAGED STRUCTURAL STEEL, AS PER PLAN |  |  | LUMP
517 | 75123 | 566 | FT | RAILING (CONCRETE PARAPET WITH TWIN STEEL TUBE RAILING AND VANDAL PROTECTION FENCE), AS PER PLAN | 50 |  | 516 |  | 17
517 | 75601 | 180 | FT | DEEP BEAM BRIDGE RETROFIT RAILING , AS PER PLAN |  |  | 180
519 | 11100 | 52 | SF | PATCHING CONCRETE STRUCTURE | 45 | 7
843 | 50000 | 32 | SF | PATCHING CONCRETE STRUCTURES WITH TROWELABLE MORTAR | 32
846 | 00110 | 42.6 | CF | POLYMER MODIFIED ASPHALT EXPANSION JOINT SYSTEM |  |  | 42.6
SPECIAL | 53000200 | LS | LUMP | STRUCTURES: CONSULTANT FOR CONCRETE QUALITY CONTROL INCLUDING TESTING AND INSPECTION | LUMP |  | LUMP |  | 17
607 | 39931 | 516 | FT | VANDAL PROTECTION FENCE, 12' CURVED, COATED FABRIC, AS PER PLAN |  |  | 516
625 | 25502 | 294 | FT | CONDUIT, 3", 725.05 | 36 |  | 258
625 | 29920 | 1 | EA | STRUCTURE JUNCTION BOX |  |  | 1

## HAM-71-1440 Quantity Calcs
STATE OF OHIO
DEPARTMENT OF TRANSPORTATION
DISTRICT 8
505 S. STATE ROUTE 741
LEBANON, OHIO 45036
PHONE: (513) 932-3030
FAX: (513) 932-7651
JOB/ PID # |  | HAM-71-1440 PID 102793
CALC BY |  | CAH | DATE | - | 2022-04-19
CHECKED BY |  |  | DATE | -
202 | 11201 | PORTIONS OF STRUCTURE REMOVED, AS PER PLAN |  | LS
202 | 75260 | VANDAL PROTECTION FENCE REMOVED | 516 | FT
509 | 25001 | UNCOATED REINFORCING STEEL, AS PER PLAN (INFORMATION ONLY) | 16377 | LBS
509 |  | GFRP REBAR | 0 | FT
510 | 10001 | DOWEL HOLES WITH NONSHRINK, NONMETALLIC GROUT, APP | 1664 | EA
|  | Sidewalk & Sidewalk Parapet | 1488 | EA
|  | Rear Abutment Backwall | 0 | EA
|  | Rear Abutment Sidewalk Wing Wall | 88 | EA
|  | Forward Abutment Backwall | 0 | EA
|  | Forward Abutment Sidewalk Wing Wall | 88 | EA
|  | Rear Approach Slab = | 0 | EA
|  | Forward Approach Slab = | 0 | EA
511 | 53014 | CLASS QC3 CONCRETE, MISC.: LIGHT WEIGHT SUPERSTRUCTURE CONCRETE WITH QC/QA, AS PER PLAN (DECK, SIDEWALK & PARAPETS) | 103.9167 | CY
|  | Sidewalk Parapet => 3' Tall * 1' Wide *258' Long * 2 Sides = | 1548 | CF
|  | Sidewalk => 0.813' Tall (Avg) * 6' Wide *258' Long = | 1257.75 | CF
|  | Deck Ends = 2 Ends x 2' Long x 0' Wide * 0.92' Thk = | 0 | CF
511 | 53014 | CLASS QC3 CONCRETE, MISC.: SUBSTRUCTURE CONCRETE WITH QC/QA, AS PER PLAN (WING WALLS & PARAPETS) | 5.7778 | CY
|  | Rear Abutment Backwall = | 0 | CF
|  | Foward Abutment Backwall = | 0 | CF
|  | Wingwall Replacement under Sidewalk Parapet => | 0 | CF
|  | Sidewalk Parapet = 3.0' Tall (Avg) *1 Thick * 13' Long * 4 Wingwalls | 156 | CF
511 | 53014 | CLASS QC3 CONCRETE, MISC.: APPROACH SLAB CONCRETE WITH QC/QA, AS PER PLAN (APPR. SLAB & APPR. SLAB SIDEWALK) | 9.7407 | CY
|  | Rear Approach Slab Widening => CADD => 21 SF + 14 SF = 35 SF * 1.25' thk. = | 43.75 | CF
|  | Rear Approach Slab Sidewalk = 25' long * 4.5' wide * 0.78' thk = | 87.75 | CF
|  | Forward Approach Slab Widening => CADD => 21 SF + 14 SF = 35 SF * 1.25' thk. = | 43.75 | CF
|  | Forward Approach Slab Sidewalk = 25' long * 4.5' wide * 0.78' thk = | 87.75 | CF
512 | 10100 | SEALING OF CONCRETE SURFACES (EPOXY-URETHANE) | 697.4444 | SY
|  | Deck Length x perimeter of Deck and Parapet to be sealed = 258*(9'+9')/9 | 516 | SY
|  | Abutment face x 2 = [430 SF (Breast and Back Wall) + (45'*2' Beam Seat)] x 2/9 | 115.5556 | SY
|  | Wingwalls x 4 = 95 SF x 4 / 9 | 40 | SY
|  | Wingwall Parapet = (32 SF*2 SIDES + 19'*1' Top and Ends )*4/9 | 22.6667 | SY
|  | Pier Columns = (5'*4' + 3'*3')/9 | 3.2222 | SY
512 | 10050 | SEALING OF CONCRETE SURFACES (NON-EPOXY) | 355.6996 | SY
|  | Deck Length x perimeter of Sidewalk to be sealed = 258*(5.66'+5.66')/9 | 324.5067 | SY
|  | Approach Slab Sidewalk = (5.66'*12.4')*4/9 | 31.1929 | SY
512 | 74000 | REMOVAL OF EXISTING COATINGS FROM CONCRETE SURFACES | 1021.9511 | SY
|  | Deck Length x perimeter of Deck, Parapet and Sidewalk to be sealed = 258*(14.66'+14.66')/9 | 840.5067 | SY
|  | Abutment face x 2 = [430 SF (Breast and Back Wall) + (45'*2' Beam Seat)] x 2/9 | 115.5556 | SY
|  | Wingwalls x 4 = 95 SF x 4 / 9 | 40 | SY
|  | Wingwall Parapet = (32 SF*2 SIDES + 19'*1' Top and Ends )*4/9 | 22.6667 | SY
|  | Pier Columns = (5'*4' + 3'*3')/9 | 3.2222 | SY
512 | 10600 | CONCRETE REPAIR BY EPOXY INJECTION | 26 | FT
513 | 21500 | REPLACE DETERIORATED END CROSSFRAMES | 1605 | LB
514 | 50 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL | 398 | SF
514 | 56 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT | 398 | SF
514 | 60 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, INTERMEDIATE COAT | 398 | SF
514 | 66 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, FINISH COAT | 398 | SF
514 | 504 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | 9 | MNHR
514 | 10000 | FINAL INSPECTION REPAIR | 4 | EA
514 | 21001 | FIELD PAINTING OF DAMAGED STRUCTURAL STEEL, AS PER PLAN | LUMP
516 |  | JACKING AND TEMPORARY SUPPORT OF SUPERSTRUCTURE, AS PER PLAN | LUMP
516 | 13600 | 1/2" PREFORMED EXPANSION JOINT FILLER | 205.9193 | SF
|  | Width of Superstructure/cos(skew) x Depth of Joint Filler x Both Abutments = 36/cos(19) * 28" x 2 | 169.9193 | SF
|  | At Wingwall = 3' x 3' x 4 Wingwalls | 36 | SF
516 | 43100 | ELASTOMERIC BEARING WITH INTERNAL LAMINATES AND LOAD PLATE (NEOPRENE) | 8 | EA
No. of Beams x Both Abutments = 4 x 2
516 |  | STRIP SEAL EXPANSION JOINT WITH ELASTOMERIC SEAL | 86.6 | FT
43.3 ' x 2 Ends
518 |  | SCUPPER | 8 | EA
518 |  | PLUG SCUPPER | 4 | EA
519 |  | SPECIAL- COMPOSITE FIBER WRAP SYSTEM
|  | Pier Columns = PI*3'*(2'+2'+2'+12'+4.5')/9 | 23.5619 | SY
517 | 75123 | RAILING (CONCRETE PARAPET WITH TWIN STEEL TUBE RAILING AND VANDAL PROTECTION FENCE), AS PER PLAN | 565.332 | FT
|  | Superstructure Sidewalk Parapet Railing => 258' Long * 2 sides= | 516 | FT
|  | Substructure Sidewalk Parapet Railing => 12.33' Long * 4 Wingwalls = | 49.332 | FT
519 |  | PATCHING CONCRETE STRUCTURE | 52 | SF
|  | RearAbutment = (1+2+2+7+4+1+4+2+6+4) = | 33 | SF
|  | Forward Abutment = (1+4+4+1+2) = | 12 | SF
|  | Piers = (6+1) = | 7 | SF
530 | 200 | STRUCTURES: CONSULTANT FOR CONCRETE QUALITY CONTROL INCLUDING TESTING AND INSPECTION | LUMP
607 | 39930 | VANDAL PROTECTION FENCE, 12' CURVED, COATED FABRIC | 516 | FT
625 | 25502 | CONDUIT, 3", 725.05
|  | ABUTMENT & DECK PARAPETS =(18+258+18) | 294 | FT
625 | 29920 | STRUTURE JUNCTION BOX | 2 | EA

## VOID_HAM-71-1440_STEEL & PAINT
ITEM 514 - (Paint the structural steel using OZEU 514 specifications using Federal Color Number 14070 Green/15450 Blue).
[7 empty] | Endspan |  |  |  | V1 |  |  |  | V2 | 207.125 |  |  | Midspan
| 514 | 00050 | SURFACE PREPARATION OF EXISTING STRUCTURAL STEEL | SQ FT | 397.75 |  | Assume exterior face of girder only (disturbed by overhang forms) = 1D surface area: (2D-3Bf-Tw) | 37 | in | 2D+3W-2tw | surface area: | 0 | in | 2D+3W-2tw | surface area: | 0 | in | 2D+3W-2tw | surface area: | 0 | in | 2D+3W-2tw
| 514 | 00056 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, PRIME COAT | SQ FT | 397.75 |  | PG44x.375 Straight (16" Flange) Flange thickness varies: 1.125" min to 3.125" max | 3.0833 | ft |  | 72" PL. Girder Straight (18" Wide Flange) Flange thickness: 1.75 | 0 | ft |  | 72" PL. Girder Straight (18" Wide Flange) Flange thickness: 2.125" MIN, 2.5" MAX | 0 | ft |  | 72" PL. Girder Straight (18" Wide Flange) Flange thickness: 1.25" MIN, 1.50" MAX | 0 | ft | [8 empty] | Rear Abutment End Crossframes for Beams 1-7
| 514 | 00060 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, INTERMEDIATE COAT | SQ FT | 397.75 |  | length: | 258 | ft |  | length: | 0 | ft |  | length: | 0 | ft |  | length: | 0 | ft
| 514 | 00066 | FIELD PAINTING OF EXISTING STRUCTURAL STEEL, FINISH COAT | SQ FT | 397.75 |  | designation: | End Span |  |  | designation: | V1 |  |  | designation: | V2 |  |  | designation: | Midspan |  |  | Abutment end crossframe | [6 empty] | Rear/Forward Abutment End Crossframes for Girders 1-4 | [6 empty] | L4x4x5/16
| 514 | 00504 | GRINDING FINS, TEARS, SLIVERS ON EXISTING STRUCTURAL STEEL | MANHOURS | 9 |  | area: | 795.5 | sq ft |  | area: | 0 | sq ft |  | area: | 0 | sq ft |  | area: | 0 | sq ft |  |  | C= | 6.96 | ft |  |  |  | Abutment End Crossframe | [6 empty] | 8.2 | lb per ft
| 514 | 10000 | FINAL INSPECTION REPAIR | EACH | 4 |  | Assume 25% of outside girder fascia for paint clean up . Assume braces every 4' o.c. (Area + 10%) | 198.875 | sq ft |  | area + 10%: | 0 | sq ft |  | area + 10%: | 0 | sq ft |  | area + 10%: | 0 | sq ft |  | W30x132 | Girder Spacing = | 83.52 | in | [5 empty] | C | C/3 | C/6 |  |  | tf = | 1.125 | in
[7 empty] | Total Beam Length = |  | 258 | ft | [13 empty] | Beam Web Ht= | 28 | in |  |  |  |  | C= | 11.72 | 3.9067 | 1.9533 |  |  | in
[7 empty] | Total Area per beam |  | 198.875 | sq ft |  | Internal Hinges | 0 | Sq Ft | [16 empty] | Girder Ht= | 39.75 | in |  |  |  | in
[7 empty] | Total # of Beams |  | 2 |  |  | Scuppers | 0 | Sq Ft |  |  | Bearings | Slider-Expan. | Fixed | Elastomeric | [11 empty] | 3.3125 | ft | 26.2347 |  | 14.7882 | in
[7 empty] | Total Paint Area |  | 397.75 | sq ft | [6 empty] | Painted Area (SF) | 1.76 | 1.76 | 5
[17 empty] | Quantity | 0 | 0 | 0 |  |  |  | 2.3333 | FT | [12 empty] | 1.333 | Ft
[5 empty] | 6"x60"x1/2" Vert. Stiffener Wt: |  | Vert. Stiffener surf. area: |  | 5 | Sq Ft | [6 empty] | Total Area (SF) | 0 | 0 | 0 |  |  |  | 28 |  |  |  | 4.1899 | FT |  |  | 3.8455 |  |  | 5.122 |  |  | 0.87978 | Sq Ft
[5 empty] | 51.0417 | lb | # of Stiffeners |  | 0 | Each | [19 empty] | 5.122 | 3.3125 | [6 empty] | 7 | Ft
[7 empty] | Area = |  | 0 | Sq Ft | [7 empty] | Total | 0 | [18 empty] | 4.62 | Sq Ft
[7 empty] | Stiffener edge included with web painting | [10 empty] | Add 10% | 0 | [6 empty] | 6.96
[31 empty] | 3.9067 | 1.9533
[7 empty] | Abut. Brg. Stiff. surf. area: |  | 3.6667 | Sq Ft | [12 empty] | Total L3x3x3/8" X-Frame member length = |  |  | 15.3397 | Ft
[7 empty] | # of Stiffeners |  | 0 | Each |  |  |  | Painting | [17 empty] | length= | 11.72+(2*5.122)+(2*3.8455)
[7 empty] | Area = |  | 0 | Sq Ft |  |  |  | Total | 397.75 | [7 empty] | Paint area per End Crossframe |  |  | 15.3397 | Sq Ft | [5 empty] | 29.655 | ft
[7 empty] | Stiffener edge included with web painting | [15 empty] | Incl. Gusset Pl. => = |  | Area + 10% | 16.8737 | Sq Ft
[7 empty] | Abutment End Crossframes | [23 empty] | Paint area per = |  | 39.5361 | Sq Ft
[7 empty] | surface area: | 1.33 | ft | [21 empty] | End Crossframe
[7 empty] | length: | 29.65 | ft
[7 empty] | designation: | End Crossframes | [15 empty] | Intermediate Bridge Crossframes | [6 empty] | Steel Weight for end Crossframes
[7 empty] | quantity: | 0 | [16 empty] | C | [7 empty] | 243.1713 | Pounds
[7 empty] | area: | 0 | sq ft
[7 empty] | area + 10%: for Gusset Plates | 0 | sq ft | [14 empty] | C= | 10 | ft
[7 empty] | Intermediate Bridge Crossframes | [15 empty] | PG60"x0375" | Beam Ht = | 60 | in |  |  |  |  | Add 10% for gusset plates |  | 267.4885 | Pounds
[7 empty] | surface area Diag: | 1 | ft | [15 empty] | 5 | ft
[7 empty] | surface area Hor: | 1 | ft
[7 empty] | length Diag: | 11.1 | ft | [21 empty] | # of End Crossframes |  | 6
[7 empty] | length Hor: | 10 | ft
[7 empty] | designation: | Int. 3 Leg X-frame | [15 empty] | 4.3333 | FT |  | 10.5938 | FT
[7 empty] | quantity: | 0 | [15 empty] | 52 | [6 empty] | Total Weight of End Crossframe Structural Steel |  | 1604.9308 | Pounds
[7 empty] | area: | 0 | sq ft
[7 empty] | area + 10%: for Gusset Plates | 0 | sq ft
9.667
[7 empty] | Lateral Crossframes | [15 empty] | Tot. Hor. Length |  |  | 9.667 | Ft
[7 empty] | surface area: | 0 | ft | [13 empty] | Tot. Diagonal Length |  |  | 10.5938 | Ft
[7 empty] | length: | 0 | ft | [13 empty] | Total Paint Area = |  |  | 30.8546 | Sq Ft
[7 empty] | designation: | Lateral Crossframes | [14 empty] | Incl. Gusset Pl. => = |  | Area + 10% | 33.9401 | Sq Ft
[7 empty] | quantity: | 0 | [14 empty] | Total Length = |  |  | 30.8546
[7 empty] | area: | 0 | sq ft | [14 empty] | L3x3x1/2 | Steel Wt = | 290.0333 | LB
[7 empty] | area + 10%: for Gusset Plates | 0 | sq ft
ITEM 513 - TRIMMING BEAM ENDS | [25 empty] | 2850.9656
Note on F10: choward4: Calculated Value
Note on F11: choward4: Calculated Value

## Sheet5
ITEM 512 - SEALING OF CONCRETE SURFACES WITH EPOXY-URETHANE
BRIDGE DECK/PARAPET
BRIDGE DECK LENGTH = |  |  | 412 | FT
DECK EDGE/SBR PARAPET PERIMETER = |  |  | 11.3 | FT
DECK EDGE/Sidewalk/BR-2 PARAPET PERIMETER = |  |  | 17.7 | FT
# OF SIDES = |  |  | 1
SEALING AREA = |  |  | 11948 | SQ FT
|  |  | 1328 | SQ YD
PIER CAPS
# OF PIERS = |  |  | 3
PIER THICKNESS |  |  | 3 | FT
PIER CAP HEIGHT |  |  | 0 | FT
PIER CAP LENGTH |  |  | 0 | FT
PIER COLUMN HEIGHT |  |  | 12 | FT
PIER COLUMN PERIM. |  |  | 9.4248 | FT
PIER COLUMN DIAM. |  |  | 3 | FT
END OF PIER CAP AREA |  |  | 0 | SQ FT
# OF ENDS |  |  | 2
TOTAL AREA = |  |  | 0 | SQ FT
TOP OF PIER CAP AREA |  |  | 0 | SQ FT
# OF TOP AREAS |  |  | 1
SIDE OF PIER CAP |  |  | 0 | SQ FT
# OF SIDE AREAS |  |  | 2
TOTAL AREA = |  |  | 0 | SQ FT
BOTTOM OF PIER CAP/ TOP OF PIER COLUMN
BOTTOM AREA = |  |  | 35.3429 | SQ FT
# OF BOTTOM AREAS |  |  | 1
PIER COLUMN HEIGHT = |  |  | 12 | FT
PIER COLUMN AREA = |  |  | 113.0973 | SQ FT
# OF PIER COLUMNS = |  |  | 5 | EA
TOTAL COLUMN AREA = |  |  | 565.4867 | SQ FT
TOTAL AREA = |  |  | 1802.4888 | SQ FT
|  |  | 201 | SQ YD
REAR ABUTMENT (ASSUME ALL CONCRETE IS SEALED ABOVE TOP OF FOOTING)
BEAM SEAT WIDTH = |  |  | 0 | FT
BEAM SEAT LENGTH = |  |  | 0 | FT
HEIGHT FROM GROUND TO BEAM SEAT = |  |  | 0 | FT
BACKWALL THICKNESS = |  |  | 0 | FT
BACKWALL HEIGHT = |  |  | 0 | FT
FACE OF BEAM SEAT = |  |  | 0 | SQ FT
BEAM SEAT = |  |  | 0 | SQ FT
SIDES OF BEAM SEAT |  |  | 0 | SQ FT
FACE OF BACKWALL= |  |  | 60 | SQ FT
LEFT WINGWALL= |  |  | 0 | SQ FT (CADD)
SIDES & TOP OF WINGWALL PARAPETS = |  |  | 0 | SQ FT
RIGHT WINGWALL= |  |  | 0 | SQ FT (CADD)
SIDES & TOP OF WINGWALL PARAPETS = |  |  | 0 | SQ FT
ABUTMENT PARAPET
SBR LENGTH = |  |  | 20.16 | FT
SBR PARAPET PERIMETER = |  |  | 9 | FT
BR-2 LENGTH |  |  | 16.75
BR-2 PARAPET PERIMETER = |  |  | 7 | FT
# OF SIDES = |  |  | 1
SEALING AREA = |  |  | 298.69 | SQ FT
|  |  | 34 | SQ YD
APPROACH SLAB SIDEWALK
LENGTH = |  |  | 25 | FT
SIDEWALK PERIMETER = |  |  | 8 | FT
# OF SIDES = |  |  | 1
SEALING AREA = |  |  | 200 | SQ FT
|  |  | 23 | SQ YD
ABUTMENT TOTAL AREA = |  |  | 558.69 | SQ FT
|  |  | 63 | SQ YD
FORWARD ABUTMENT (ASSUME ALL CONCRETE IS SEALED ABOVE TOP OF FOOTING)
BEAM SEAT WIDTH = |  |  | 0 | FT
BEAM SEAT LENGTH = |  |  | 0 | FT
HEIGHT FROM GROUND TO BEAM SEAT = |  |  | 0 | FT
BACKWALL THICKNESS = |  |  | 0 | FT
BACKWALL HEIGHT = |  |  | 0 | FT | 0
FACE OF BEAM SEAT = |  |  | 0 | SQ FT
BEAM SEAT = |  |  | 0 | SQ FT
SIDES OF BEAM SEAT |  |  | 0 | SQ FT
FACE OF BACKWALL= |  |  | 60 | SQ FT
LEFT WINGWALL= |  |  | 0 | SQ FT (CADD)
SIDE, TOP & BACK OF WINGWALL = |  |  | 0 | SQ FT
RIGHT WINGWALL= |  |  | 0 | SQ FT (CADD)
SIDE, TOP & BACK OF WINGWALL = |  |  | 0 | SQ FT
ABUTMENT PARAPET
SBR LENGTH = |  |  | 24.5 | FT
SBR PARAPET PERIMETER = |  |  | 9 | FT
BR-2 LENGTH |  |  | 26.67
BR-2 PARAPET PERIMETER = |  |  | 7 | FT
# OF SIDES = |  |  | 1
SEALING AREA = |  |  | 407.19 | SQ FT
ABUTMENT TOTAL AREA = |  |  | 467.19 | SQ FT
|  |  | 52 | SQ YD
APPROACH SLAB SIDEWALK
LENGTH = |  |  | 25 | FT
SIDEWALK PERIMETER = |  |  | 8 | FT
# OF SIDES = |  |  | 1
SEALING AREA = |  |  | 200 | SQ FT
|  |  | 23 | SQ YD
|  |  | 667.19 | SQ FT
|  |  | 75 | SY
GRAND TOTAL = |  |  | 1667 | SQ YD
ITEM 512 - REMOVAL OF EXISTING CONCRETE SEALER |  |  |  | 201 | SQ YD
ITEM 512 - SEALING CONCRETE BRIDGE DECK WITH HMWM RESIN
APPROACH SLAB LENGTH = |  |  | 20 | FT
APPROACH SLAB WIDTH = |  |  | 26.17 | FT
# OF APPROACH SLABS = |  |  | 2
APPROACH SLAB SEALING AREA = |  |  | 1046.8 | SQ FT = | 116.3111 | SQ YD
BRIDGE DECK LENGTH |  |  | 412 | FT | (BRIDGE LIMITS)
BRIDGE DECK WIDTH = |  |  | 26.17 | FT | (CONSTRUCTION JOINT)
BRIDGE DECK SEALING AREA = |  |  | 10782.04 | SQ FT = | 1198.0044 | SQ YD
TOTAL = | 1315 | SQ YD
ITEM 519 - PATCHING CONCRETE STRUCTURE
Deck Slab |  | 0 | SF
Rear Abutment
Repair Area Height = |  |  | 0 | FT
Repair Area Width = |  |  | 0 | FT
# of Repair Areas = |  |  | 1
Repair Area = |  | 0 | SQ FT
Fwd Abutment
Repair Area Height = |  |  | 0 | FT
Repair Area Width = |  |  | 0 | FT
# of Repair Areas = |  |  | 1
Repair Area = |  | 0 | SQ FT
Pier 3 Cap
Repair Area Height = |  |  | 0 | FT
Repair Area Width = |  |  | 1.5 | FT
# of Repair Areas = |  |  | 1
Repair Area = |  | 0 | SQ FT
Pier Columns
Repair Area Height = |  |  | 0 | FT
Repair Area Width = |  |  | 0 | FT
# of Repair Areas = |  |  | 1
Repair Area = |  | 15 | SQ FT
Total = |  | 15 | SQ FT
ITEM 607 - VANDAL PROTECTION FENCE, 6' STRAIGHT, COATED FABRIC
VPF ON SBR PARAPET = | 412 | FT

## Sheet2
STATE OF OHIO
DEPARTMENT OF TRANSPORTATION
DISTRICT 8
505 S. STATE ROUTE 741
LEBANON, OHIO 45036
PHONE: (513) 932-3030
FAX: (513) 932-7651
JOB/ PID # |  | PRE-40-0673 PID108849
CALC BY |  | GTF | DATE | - | 2020-04-23
CHECKED BY |  |  | DATE | -
202 | 11201 | PORTIONS OF STRUCTURE REMOVED, AS PER PLAN |  | LS
509 | 10000 | EPOXY COATED REINFORCING STEEL | 6132 | LBS
510 | 10000 | DOWEL HOLES WITH NONSHRINK, NONMETALLIC GROUT | 56 | EA
511 | 53014 | CLASS QC3 CONCRETE, MISC.: SUPERSTRUCTURE CONCRETE WITH QC/QA, AS PER PLAN | 32.6667 | CY
|  | Deck Width x Deck Length x Deck Thk. =39 x 49 x .5 | 882 | CF
511 | 53014 | CLASS QC3 CONCRETE, MISC.: SUBSTRUCTURE CONCRETE WITH QC/QA, AS PER PLAN | 0.68056 | CY
|  | Wingwall Thickness x Wingwall Depth x Wingwall Length x 4 | 18.375 | CF
512 | 10000 | SEALING OF CONCRETE SURFACES | 94.8889 | SY
|  | Deck Length x perimeter of Deck Edge to be sealed x 2 = (49 x 3x 2)/9 | 32.6667 | SY
|  | abutment face x 2 = 20 SY x 2 | 40 | SY
|  | WINGWALLS x 2 = 50 SF x 4 / 9 | 22.2222 | SY
512 | 44401 | TYPE B WATERPROOFING | 14 | SY
|  | Area of Beam End x 9 x both ends = (7 x 9 x 2) | 126 | SF
512 | 74000 | REMOVAL OF EXISTING COATINGS FROM CONCRETE SURFACES | 62.2222 | SY
|  | Existing sealer on abutment face x 2 = 20 SY x 2 | 40 | SY
|  | Existing sealer on WINGWALLS x 2 = 50 SF x 4 / 9 | 22.2222 | SY
515 | 12051 | PRESTRESSED CONCRETE COMPOSITE BOX BEAM BRIDGE MEMBERS, LEVEL 1, CB21-48, AS PER PLAN (48'-9" LONG) | 9 | EA
516 | 13600 | 1" PREFORMED EXPANSION JOINT FILLER | 205.9193 | SF
|  | Width of Superstructure/cos(skew) x Depth of Joint Filler x Both Abutments = 36/cos(19) * 28" x 2 | 169.9193 | SF
|  | At Wingwall = 3' x 3' x 4 Wingwalls | 36 | SF
516 | 41100 | 1/8" PREFORMED BEARING PAD | 36 | EA
No. of Beams x 2 x Both Abutments = 9 x 2 x 2
516 | 43100 | ELASTOMERIC BEARING WITH INTERNAL LAMINATES ONLY (NEOPRENE) | 36 | EA
No. of Beams x 2 x Both Abutments = 9 x 2 x 2
517 | 70000 | RAILING (TWIN STEEL TUBE) | 105 | FT
SPECIAL | 51822300 | STEEL DRIP STRIP | 98 | FT
Deck Length x 2
846 | 00110 | POLYMER MODIFIED ASPHALT EXPANSION JOINT SYSTEM | 22 | CF
Calc in Plan