## Sheet1
DESCRIPTION OF CRITICAL WORK | CALENDAR DAYS TO COMPLETE | DISINCENTIVE ($ PER DAY) | WORK WINDOW
|  |  | START | END
ALL WORK REQUIRING ROAD CLOSURE | 210 | PER C&MS 108.07 | 2024-10-15 | 2025-09-26