## OUPS Contacts
HAM-74-13.35 PID 110563
OUPS Contact List (Call 1-800-362-2764)
Project Engineer | Call Date/Time
Trey Jackson | 7/8/22 @ 3:08 pm
Description of Project Limits:
Utilities Contacted by OUPS | Utility Contact | Utility Contact Number
BP Pipelines (North America) Inc. Land & ROW Department 30 South Wacker Drive, Suite 900 Chicago, IL 60606 | Matt Rairigh matt.rairigh@bp.com Plan Reviews to: bppipelinesrow@bp.com | 312-766-2430
Cincinnati Bell Telephone (Underground) 221 East 4th Street, Bldg. 121-900 Cincinnati, OH 45201 | Breck Cowan breck.cowan@altafiber.com Plan Reviews to: roadprojects@cinbell.com | 513-565-7187
Cincinnati Bell Telephone (Aerial) 209 West 7th Street, Bldg. 121-900 Cincinnati, OH 45202 | Robert Strochinsky, Kevin Clapp Plan Reviews to: roadprojects@cinbell.com | 513-565-6014
Cincinnati Stormwater Management Utility 4747 Spring Grove Avenue Cincinnati, OH 45232 | Nick Christopfel Plan Reviews to: Nick.Christopfel@cincinnati-oh.gov | 513-591-7783
Greater Cincinnati Water Works 4747 Spring Grove Avenue Cincinnati, OH 45232 | Mike Cossins Michael.Cossins@gcww.cincinnati-oh.gov | 513-591-5056
Metropolitan Sewer District 1600 Gest Street Cincinnati, OH 45204 | Robert Franklin Plan Reviews to: MSDUtilityReview@cincinnati-oh.gov | 513-244-1300
Duke Energy Electric (Distribution) 2010 Dana Avenue Cincinnati, OH 45207 | Chris Tepe chris.tepe@duke-energy.com | 513-514-8209
Duke Energy Electric (Transmission) 139 East 4th Street, Room 552A Cincinnati, OH 45202 | Tim Meyer Tim.Meyer@duke-energy.com | 513-287-1266
Duke Energy Electric (Gas) 139 East 4th Street, Room 460A Cincinnati, OH 45202 | Mark Branscum, Andy McNichols mark.branscum@duke-energy.com Plan Reviews to: OH/KYHousebill@duke-energy.com | 513-287-2517
Utilities Not Contacted by OUPS | Utility Contact | Utility Contact Number
Utility Name Street Address City, State Zip Code | Engineer Name E-mail address | Phone: (000) 000-0000 Fax: (000) 000-0000
Utility Name Street Address City, State Zip Code | Engineer Name E-mail address | Phone: (000) 000-0000 Fax: (000) 000-0000
Utility Name Street Address City, State Zip Code | Engineer Name E-mail address | Phone: (000) 000-0000 Fax: (000) 000-0000
Railroads | Railroad Contact | Railroad Contact Number
Railroad Name Street Address City, State Zip Code | Engineer Name E-mail address | Phone: (000) 000-0000 Fax: (000) 000-0000
Railroad Name Street Address City, State Zip Code | Engineer Name E-mail address | Phone: (000) 000-0000 Fax: (000) 000-0000
Railroad Name Street Address City, State Zip Code | Engineer Name E-mail address | Phone: (000) 000-0000 Fax: (000) 000-0000

## Stage 1 Submittal
HAM-74-13.35 PID 110563
OUPS Stage 1 Project Submittal Checklist Form
Utilities Contacted by OUPS | Utility Contact | Utility Contact Number | Cover Letter | Stage 1 Design Package | Date Submitted to Utility | Date of Fishbeck Follow Up | Date of Response from Utility | Information Received from Utility | Notes | Notes after Stage 1 Submission
BP Pipelines (North America) Inc. Land & ROW Department 30 South Wacker Drive, Suite 900 Chicago, IL 60606 | Matt Rairigh matt.rairigh@bp.com Plan Reviews to: bppipelinesrow@bp.com | 312-766-2430 | Yes or No | Yes or No | 2007-01-01 | 2007-01-03 | 2007-01-02 | Yes or No and What | Additional Project Details | Additional Project Details
BP Pipelines (North America) Inc. Land & ROW Department 30 South Wacker Drive, Suite 900 Chicago, IL 60606 | Matt Rairigh matt.rairigh@bp.com Plan Reviews to: bppipelinesrow@bp.com | 312-766-2430 | Yes | 2022-11-01 | 2022-11-01 | 11/22/2022 and 12/7/22 | 11/22/2022 and 12/7/22 and 1-9-23 | No conflict identifed from OUPS ticket | Include the following in correspondence: keith.boyle@bp.com, timothy.fehr@bp.com. Gasline should not be impacted by work scoped along the RT side of Race Road. Assuming no gasline impacts, but need BP to confirm. District 8 reached out 1-3-23. Marco Gasca with Entrust Solutions Group reached out 3-30-23 to inform they are performing plan review on behalf of BP. Include all in future correspondence. Marco sent comments from Stage 1 review on 4-18-23. Jon replied to comments 4-19-23. | We currently do not anticipate an impact to BP pipelines, but again this is based on approximate location per OUPS field markings
Cincinnati Bell Telephone (Underground) 221 East 4th Street, Bldg. 121-900 Cincinnati, OH 45201 | Breck Cowan breck.cowan@altafiber.com Plan Reviews to: roadprojects@cinbell.com | 513-565-7187 | Yes | 2022-11-01 | 2022-11-01 | N/A | 2022-11-02 | No conflict identifed from OUPS ticket | Inquired if utility easement exists at the Green Township owned property at the Northeast quadrant 10-4-22. Easement provided from CinBell. Owner mentioned likely required to bore under I-74. | The plans correctly show existing CBT/altafiber UG facilities. We will be exploring (2) options. Our intention is to replace what FO and copper lines we require on the existing aerial crossing on the east side of Race Road. Our other option is a bore from MH to MH underneath I-74. This would be a very costly scenario for CBT/altafiber and would be a last recourse.
Cincinnati Bell Telephone (Aerial) 209 West 7th Street, Bldg. 121-900 Cincinnati, OH 45202 | Robert Strochinsky, Kevin Clapp Plan Reviews to: roadprojects@cinbell.com | 513-565-6014 | Yes | 2022-11-01 | 2022-11-01 | 2022-11-29 | 2022-11-29 | No conflict identifed from OUPS ticket | Aerial should not be impacted by scope of work. No aerial in project limits. | No impacts
Cincinnati Stormwater Management Utility 4747 Spring Grove Avenue Cincinnati, OH 45232 | Nick Christopfel Plan Reviews to: Nick.Christopfel@cincinnati-oh.gov | 513-591-7783 | Yes | 2022-11-01 | 2022-11-01 | 11/29/2022, 12/7/22, 12/20 | 2022-12-20 | No conflict identifed from OUPS ticket | Storm should not be impacted by scope of work | No impacts
Greater Cincinnati Water Works 4747 Spring Grove Avenue Cincinnati, OH 45232 | Mike Cossins Michael.Cossins@gcww.cincinnati-oh.gov | 513-591-5056 | Yes | 2022-11-01 | 2022-11-01 | 11/29/2022, 12/7/22 | 2022-12-07 | No conflict identifed from OUPS ticket | To be impacted by scope of work. Provided basemaps to GCWW 12-7-22, they are investigating impacts. GCWW does not believe the 24" line wil be impacted by construction. Fishbeck to provide drawing for guardrail posts for 12" line potential impacts. GCWW may provide notefor include into Fishbeck plans, to not undermine the 24" waterline. The north end will not be impacted with new guardrail location since 6.7' of cover and post embedment for Type 1 BTA is 49". The south end will not be impacted, similiar reason, and waterline location within Type T anchor assmbley. | ODOT to provide reference note for utility conflict with guardrail post locations.
Metropolitan Sewer District 1600 Gest Street Cincinnati, OH 45204 | Robert Franklin Plan Reviews to: MSDUtilityReview@cincinnati-oh.gov | 513-244-1300 | Yes | 2022-11-01 | 2022-11-01 | 2022-11-04 | 2022-11-03 | No conflict identifed from OUPS ticket | Provide 18" outside vertical clearance and 10' outside horizontal clearance from existing or proposed sewers. Asking MSD to verify northern most manhole, as does not show up in survey or google. Assume the manhole is paved over per MSD. | No impacts
Duke Energy Electric (Distribution) 2010 Dana Avenue Cincinnati, OH 45207 | Chris Tepe chris.tepe@duke-energy.com | 513-514-8209 | Yes | 2022-11-01 | 2022-11-01 | 2022-11-11 | 2022-11-10 | No conflict identifed from OUPS ticket | Electric should not be impacted by scope of work. Duke inquired which side of the bridge the contractor will deploy cranes from. Fishbeck mentioned this is a means and methods and contractor will have to adhere to duke and osha complaince. No further action for stage 1. Confirmed with D8 utility coordinator. Checked on status of if easements are in place 12/22/22. Duke provided easements 1-4-23. | No impacts
Duke Energy Electric (Transmission) 139 East 4th Street, Room 552A Cincinnati, OH 45202 | Tim Meyer Tim.Meyer@duke-energy.com | 513-287-1266 | Yes | 2022-11-01 | 2022-11-01 | N/A | 2022-11-11 | No conflict identifed from OUPS ticket | Electric should not be impacted by scope of work. Confirmed no lines within project limits. | No impacts
Duke Energy Electric (Gas) 139 East 4th Street, Room 460A Cincinnati, OH 45202 | Mark Branscum, Andy McNichols mark.branscum@duke-energy.com Plan Reviews to: OH/KYHousebill@duke-energy.com | 513-287-2517 | Yes | 2022-11-01 | 2022-11-01 | 11/7/2022, 11/29/22 | 2022-11-03 | No conflict identifed from OUPS ticket | Gasline may be impacted .To verify with plans/correspondence provided by owner. Reached out to Duke to see if gasline alignment information can be provided electronically or further explain. Recommend test hole locations to Duke. Responded to Andy 11/30/22 with plans and test hole recommendations. Duke provided test hole locations incoproated 12-20-23. | No impacts

## Stage 2 Submittal
HAM-74-13.35 PID 110563
OUPS Stage 2 Project Submittal Checklist Form
2007-11-29
#REF!
Utilities Contacted by OUPS | Utility Contact | Utility Contact Number | Cover Letter | Stage 2 Design Package | Date Submitted to Utility | Date of Fishbeck Follow Up | Date of Response from Utility | Information Received from Utility | Notes
BP Pipelines (North America) Inc. Land & ROW Department 30 South Wacker Drive, Suite 900 Chicago, IL 60606 | Matt Rairigh matt.rairigh@bp.com Plan Reviews to: bppipelinesrow@bp.com | 312-766-2430 | Y | 2023-04-21 | 2023-04-21 | 5/22/2023, 1/11/24 | 5/19/2023 and 6/1/23 | Comment and Response Tracking spreadsheet provide by EnTrust Solutions Group. Confirmation relocation will not be required. BP provided locates of gasline location, which is in conflict with previous gasline location. JPC emailed Entrust on 7-5-23 to determine which gasline shall be shown in the plans. Entrust noted to show the gasline per field markings in the survey from OUPS. entrust recommends potholes and JPC emailed 7-17-23 to verify who would cover this cost. BP provided easement along Race road. JPC emailed 7-26 to inform BP potholing and utility protection design is not covered as reimbursable costs. Inquring on how BP would like to proceed. Emailed 1-11-24 to see if any further informatinon available to determine if guardrail posts will be in conflict with the gasline. BP replied 1-11-24 that status is still unknown. | Emailed 7-5-23 for unresolved gasline location. Emailed again 7-26-23 for direction to proceed with potholing. Emailed again 1-11-24 to see if any new insight.
Cincinnati Bell Telephone (Underground) 221 East 4th Street, Bldg. 121-900 Cincinnati, OH 45201 | Breck Cowan breck.cowan@altafiber.com Plan Reviews to: roadprojects@cinbell.com | 513-565-7187 | Y | 2023-04-21 | 2023-04-21 | 2023-05-22 | 4/25/2023, 4/28/23 | none | confirmed utility intent to use Duke poles to the south. Fishbeck needs to adjust roadway plan sheets to clearly label portion between manholes to be relocated, and portion outside manholes to remain. Owner has also requested to move the bottom of the ditch outside the manhole at the north end. All comments have been incorporated into the plans.
Cincinnati Bell Telephone (Aerial) 209 West 7th Street, Bldg. 121-900 Cincinnati, OH 45202 | Robert Strochinsky, Kevin Clapp Plan Reviews to: roadprojects@cinbell.com | 513-565-6014 | Y | 2023-04-21 | 2023-04-21 |  |  | See Stage 1 | No impacts, no response.
Cincinnati Stormwater Management Utility 4747 Spring Grove Avenue Cincinnati, OH 45232 | Nick Christopfel Plan Reviews to: Nick.Christopfel@cincinnati-oh.gov | 513-591-7783 | Y | 2023-04-21 | 2023-04-21 |  | 2023-04-24 | Project is well outside the Cincinnati Stormwater Management Utility limits. | No impacts.
Greater Cincinnati Water Works 4747 Spring Grove Avenue Cincinnati, OH 45232 | Mike Cossins Michael.Cossins@gcww.cincinnati-oh.gov | 513-591-5056 | Y | 2023-04-21 | 2023-04-21 | 8/24/2023, 1-11-24 |  | none | Emailed again -11-24 for confirmation.
Metropolitan Sewer District 1600 Gest Street Cincinnati, OH 45204 | Robert Franklin Plan Reviews to: MSDUtilityReview@cincinnati-oh.gov | 513-244-1300 | Y | 2023-04-21 | 2023-04-21 |  | 2023-04-21 | Letter stating the sewers shown in the plans are shown correctly. | No conflict
Duke Energy Electric (Distribution) 2010 Dana Avenue Cincinnati, OH 45207 | Chris Tepe chris.tepe@duke-energy.com | 513-514-8209 | Y | 2023-04-21 | 2023-04-21 | 2023-08-24 | 2023-08-28 | Cincinnati Bell has been approved to attach to the poles in Duke's system. | No further action required.
Duke Energy Electric (Transmission) 139 East 4th Street, Room 552A Cincinnati, OH 45202 | Tim Meyer Tim.Meyer@duke-energy.com | 513-287-1266 | Y | 2023-04-21 | 2023-04-21 |  | 2023-04-24 | none | no transmission lines in the project location
Duke Energy Electric (Gas) 139 East 4th Street, Room 460A Cincinnati, OH 45202 | Mark Branscum, Andy McNichols mark.branscum@duke-energy.com Plan Reviews to: OH/KYHousebill@duke-energy.com | 513-287-2517 | Y | 2023-04-21 | 2023-04-21 | 2023-08-24 | 2023-08-29 | See Stage 1 | Duke is good with having the guardrail post locations adjusted in the field per utility location, as described in the plan general notes.

## Stage 3 Submittal
HAM-74-13.35 PID 110563
OUPS Stage 3 Project Submittal Checklist Form
2007-11-29
#REF!
Utilities Contacted by OUPS | Utility Contact | Utility Contact Number | Cover Letter | Stage 3 Design Package | Date Submitted to Utility | Date of Fishbeck Follow Up | Date of Response from Utility | Information Received from Utility | Notes
BP Pipelines (North America) Inc. Land & ROW Department 30 South Wacker Drive, Suite 900 Chicago, IL 60606 | Matt Rairigh matt.rairigh@bp.com Plan Reviews to: bppipelinesrow@bp.com | 312-766-2430 | Yes | Yes | 2024-02-12 |  | 2024-03-14 | BP has concerns with available cover over existin gasline. | Fishbeck realigned the ditch to provide atleast the existing cover over the gasline. Emailed realignment of ditch on 3-22-24 for BP and ODOT approval. BP inquiring in concrete protection could be covered, which explained is not a reimbursable cost by ODOT.
Cincinnati Bell Telephone (Underground) 221 East 4th Street, Bldg. 121-900 Cincinnati, OH 45201 | Breck Cowan breck.cowan@altafiber.com Plan Reviews to: roadprojects@cinbell.com | 513-565-7187 | Yes | Yes | 2024-02-12 |  | 2024-02-28 | Good with information as shown.
Cincinnati Bell Telephone (Aerial) 209 West 7th Street, Bldg. 121-900 Cincinnati, OH 45202 | Robert Strochinsky, Kevin Clapp Plan Reviews to: roadprojects@cinbell.com | 513-565-6014 | Yes | Yes | 2024-02-12 | 2024-02-13 | 2024-02-13 |  | Discussions on impacts to aerial line and pole at Sta. 22+25, 23' LT on going with Duke and Altafiber. Discussed with Kevin Clapp (altafiber) on 2-13-24 and anticipated to be a Duke pole and service. Duke will relocate the service pole to STA 22+26, 38' LT. Spectrum is on the pole as well. District, Duke, Altafiber, Fishbeck had call on 2-16-24 to discuss project schedule and feasibility of Altafiber relocation. District to continune coordination with Altafiber. Altafiber waiting on ODOT permit as per 4-4-24.
Cincinnati Stormwater Management Utility 4747 Spring Grove Avenue Cincinnati, OH 45232 | Nick Christopfel Plan Reviews to: Nick.Christopfel@cincinnati-oh.gov | 513-591-7783 | Yes | Yes | 2024-02-12 |  | 2024-02-16 | No infrastructure and not within projects limits.
Greater Cincinnati Water Works 4747 Spring Grove Avenue Cincinnati, OH 45232 | Mike Cossins Michael.Cossins@gcww.cincinnati-oh.gov | 513-591-5056 | Yes | Yes | 2024-02-12
Metropolitan Sewer District 1600 Gest Street Cincinnati, OH 45204 | Robert Franklin Plan Reviews to: MSDUtilityReview@cincinnati-oh.gov | 513-244-1300 | Yes | Yes | 2024-02-12 |  | 2024-02-14 | Acceptance letter from MSD, no impacts
Duke Energy Electric (Distribution) 2010 Dana Avenue Cincinnati, OH 45207 | Chris Tepe chris.tepe@duke-energy.com | 513-514-8209 | Yes | Yes | 2024-02-12 | 2024-02-13 | 2024-02-13 |  | Discussions on impacts to aerial line and pole at Sta. 22+25, 23' LT on going with Duke and Altafiber. Discussed with Kevin Clapp (altafiber) on 2-13-24 and anticipated to be a Duke pole and service. Duke will relocate the service pole to STA 22+26, 38' LT. District, Duke, Altafiber, Fishbeck had call on 2-16-24 to discuss project schedule and feasibility of Altafiber relocation. District to continune coordination with Altafiber. Duke work complete as per 4-3-24.
Duke Energy Electric (Transmission) 139 East 4th Street, Room 552A Cincinnati, OH 45202 | Tim Meyer Tim.Meyer@duke-energy.com | 513-287-1266 | Yes | Yes | 2024-02-12 |  |  |  | no transmission lines in the project location
Duke Energy Electric (Gas) 139 East 4th Street, Room 460A Cincinnati, OH 45202 | Mark Branscum, Andy McNichols mark.branscum@duke-energy.com Plan Reviews to: OH/KYHousebill@duke-energy.com | 513-287-2517 | Yes | Yes | 2024-02-12 | 2024-02-13 | 2024-02-13 |  | no change in status.