## Sheet1
WORK WINDOW
LOCATION | DESCRIPTION OF CRITICAL WORK | CALENDAR DAYS TO COMPLETE | DISINCENTIVE $ PER DAY | WORK WINDOW
|  |  |  | START | END
HAM-52-3663 | LONG TERM LANE CLOSURE | 14 | 600 | CONTRACT SIGNED DATE | CONTRACT COMPLETION DATE
| ALL IN-STREAM WORK | 60 | 600 | 2027-06-15 | 2027-08-15
HAM-275-3781 | ALL IN-STREAM WORK | 60 | 600 | 2027-06-15 | 2027-08-15