## 20151
Clough Pike & Newtwn Rd Intersection Improvements HAM-CR 358-0.94 (PID 118484) Stage 2 Construction Cost Estimate
ITEM | UNIT | UNIT PRICE | QTY | COST
ROADWAY
Clearing & Grubbing | LS | 20000 | 1 | 20000 |  |  |  |  | Area Inside Construction Limits (-areas over rivers, railroads, etc) - pavement salvage area
Guardrail Removed | FT | 3.4835 | 175 | 609.6142
Excavation | CY | 25.1862 | 2045 | 51505.7381 |  |  | KM-corridor-Corridor Reports-Component Quantities |  | Volume from the model
Embankment | CY | 23.5476 | 950 | 22370.1915 |  |  |  |  | addition of all grading components in model. (backslope, ditch, finished grade, foreslope, graded shoulder, green space.
Guardrail, Type MGS | FT | 24.1548 | 250 | 6038.695
Anchor Assembly, MGS Type E | EA | 2694.1419 | 3 | 8082.4256
5' Concrete Walk | SF | 7 | 15900 | 111300
Curb Ramp, Type B1 | SF | 36.8038 | 360 | 13249.35 | 2 curb ramps at the intersection |  | Front: EOP
Fence, Misc.: Wood Fence | FT | 70 | 440 | 30800 | Sheet 12 + Sheet 15 | 120.329+315.37=435.699
EROSION CONTROL | [8 empty] | Total length measured from BP.
Seeding & Mulching | SY | 1.5363 | 4800 | 7374.144 |  | 21041.58 | 2337.9533 | Construction Limit - Pavement | equal mainline pavement quantity.
Temporary Erosion Control | EACH | 1 | 30000 | 30000
DRAINAGE
12" Conduit, Type B | FT | 116.7586 | 50 | 5837.928 | 1 | 46.987
15'' Conduit, Type B | FT | 130.3764 | 110 | 14341.4084 | 2 | 109.267
15" Conduit, Type C | FT | 108.4743 | 90 | 9762.6897 | 2 segments | 87.231
Catch Basin, No. 2-2B | EA | 2729.186 | 2 | 5458.3721
6" Base Pipe | FT | 11.1666 | 1500 | 16749.855
Concrete Masonry | CY | 2494.5733 | 23 | 57375.1857
Conduit, Type A, Concrete Box Culvert, 4'x4' | FT | 650 | 22 | 14300
Conduit, Type A, Concrete Box Culvert, 48''x52'' | FT | 700 | 8 | 5600
PAVEMENT
Pavement, Full Depth | SY | 95 | 1235 | 117325 | 95.46 | 1.5 | in |  | Eric
Pavement, Mill and Fill | SY | 30 | 2150 | 64500 | 133.63 | 1.75 | in
Pavement, Driveway | SY | 150 | 140 | 21000 | 212.97 | 2 driveways, remeasure the area
TRAFFIC CONTROL
Pavement Marking | LUMP | 10000 | 1 | 10000
Signing | LUMP | 10000 | 1 | 10000
INCIDENTALS
Mobilization | LUMP |  | 1 | 20000
Construction Layout Stakes & Surveying | LUMP | 0.6273% | 653580.5973 | 4100.0026
Maintaining Traffic | LUMP |  | 1 | 50000 |  |  |  |  | project length /5280
Design Contingency | LUMP | 16.7% | 653580.5973 | 109151.9989
Inflation Contingency (From ODOT Inflation Calculator) |  | 13.9% | 836832.5988 | 116319.7312 |  |  |  |  | Get from Matt
TOTAL |  |  | 953152.33 | [5 empty] | measure from BP
assume 24 months
from C&MS 624
0.5% of construction budget
3% of construction cost
30%

## Notes
Quantity Calculations and Estimate Notes
| Pavement Cost |  | Qty/SQ YD |  | $/ | 73.13 | $/SQ YD
| 441 | Surface | 0.035 | CY | 250 | 8.75
| 407 | Tack Coat | 0.055 | Gal | 3 | 0.165
| 441 | Intermediate | 0.05 | CY | 250 | 12.5
| 407 | Tack Coat | 0.055 | Gal | 3 | 0.165
| 301 | Asphalt Base | 0.19 | CY | 200 | 38
| 304 | Aggregate Base | 0.17 | CY | 65 | 11.05
| 204 | Subgrade Compaction | 1 | SY | 2.5 | 2.5
Prices based on King Ave Bid Tabs
| 254 | Planing | 1 | SY | 4 | 4
| Pavement Cost |  | Qty/SQ YD |  | $/ | 57.915 | $/SQ YD
| 441 | Surface | 0.035 | CY | 250 | 8.75
| 407 | Tack Coat | 0.055 | Gal | 3 | 0.165
| 441 | Intermediate | 0.05 | CY | 250 | 12.5
| 304 | Aggregate Base | 0.25 | CY | 65 | 16.25
| 204 | Subgrade Compaction | 1 | SY | 2.5 | 2.5
| Subgrade Stabilization |  |  |  |  | 17.75
| 204 | Excavation | 0.4 | SY | 16 | 6.4
| 206 | Cement | 0.035 | Ton | 150 | 5.25 | $/SQ YD
| 206 | Cement Stabilized Subgrade | 1 | SY | 5 | 5
| 206 | Curing Coat | 1 | SY | 1 | 1
| 204 | Proof Rolling | 0.0005 | Hr | 200 | 0.1
| Subgrade Stabilization |  |  |  |  | 31.4
| 204 | Excavation | 0.4 | CY | 16 | 6.4
| 204 | Granular Material, Type C | 0.4 | CY | 55 | 22
| 206 | Geotextile Fabric | 1 | SY | 3 | 3
| Signal Modification |  |  | 88850
| Stop Bar Radar | 7000 | 4 | 28000
| Strain Pole | 12000 | 2 | 24000
| Signal Heads | 1500 | 13 | 19500
| Signal Support Foundation | 4000 | 2 | 8000
| Messenger Wire | 5 | 200 | 1000
| Signal Cable, 7C | 3 | 2000 | 6000
| Pushbutton | 350 | 1 | 350
| Pull Box | 1000 | 2 | 2000