## Utility Log
O.U.P.S 1-800-362-2764 |  | COMPANY ID: |  |  |  | PROJECT: HAM-CR-358-0.94 |  | PID: 118484 |  |  |  | Last Updated By: | Last Updated Date:
Project Managers: |  | TICKETS 8/18/2023 : A323000603-00A, A323000576-00A |  |  |  | Project files: 113602_BU001 | [5 empty] | Qiaochu Chen (QC) | 2025-07-16 | Project Limits:
Utility Company | Telephone | Contact | Project Notification Notice (Emailed by ODOT or Consultant) | OUPS Request Utility Plans | Received Utility Plans or Positive Response | Sent Stage 1 Plans | Received Comments | Sent Stage 2 Plans | Received Comments | Sent Stage 3 Plans | Received Comments | FINAL TRACINGS SENT | Received Comments | Remarks | UG or OH
Name and Address | No. | Name
Duke Energy | (513) 508-9609 | Shane Erhart |  | 2023-08-18 | 2023-08-21 | 2024-01-17 | 2024-01-17 | 2024-08-05 |  | 2024-12-20 |  |  |  | 1/17/2024 Shane responded stating Duke Energy did not anticipate any relocations. | OH
Electric Distribution
2010 Dana Avenue
Cincinnati, Oh 45207
Duke Energy | (513) 614-8648 | Richard Hack |  | 2023-08-18 | 2023-08-21 | 2024-01-17 | 2024-01-18 | 2024-08-05 |  | 2025-01-13 | 2025-02-11 |  |  | 1/18/2024 Mark responded with additional GIS maps. 1/24/2024 Brian responded with concern of the clearance of the gas line between station 74+00 to 76+25 and 77+50 to 80+25. He also provided the diameter of the gas line within the two station ranges aforementioned should be both 6'' instead of 8'' and 10'', which have been updated in the project plan drawings. 2/11/2025 Brian provided the test hole results of the gas line south of Clough from STA. 72+78 to Sta. 78+45. Plans have been updated to show the accurate location of the gas line. Need to set up a call with Duke to discuss relocation plan. 6/16/2025 Meeting with ODOT, Anderson, Stantec and Duke Gas. Duke Gas is designing relocation plans for the gas line running up Newtown Road. As well as for a portion of the gas line that runs parallel to Clough Pike just east of Newtown Road. | UG
Gas | [6 empty] | 2024-01-24 | 2024-10-08
139 East Fourth St, P.O. Box 960, Room 460A |  | Mark Branscum
Cincinnati, Oh 45202
Brian Hollman
AltaFiber | (513) 565-7187 | Breck Cowan |  | 2023-08-18 | 2023-08-21 | 2024-01-17 | 2024-01-25 | 2024-08-05 |  | 2025-01-13 | 2025-01-13 |  |  | 1/25/2024 Breck responded that Altafiber records did not indicate any underground facilities in the area. - 1/10/2025 Breck confirmed again that no conflicts with their UG facilities. 1/26/2024 Robert responded with concerns of the relocations of the conflicted telecom poles on north side of Clough Pike at Clough Newtown intersection. 1/13/2025 Robert Walters responded that he's in the process of developing the relocation plan, but indicated that it would be a long process to downsize the old copper cables and migrate the customer to fiber. | OH
Telephone | [6 empty] | 2024-01-26
221 East Fourth St, BLDG 121-900 |  | Robert Walters (OH facilities)
Cincinnati, Oh 45202
MSD | (513) 557-7108 | Rob Franklin |  | 2023-08-18 | 2023-08-30 | 2024-01-17 | 2024-01-18 | 2024-08-05 | 2024-08-06 | 2024-12-20 | 2025-01-10 |  |  | 1/18/2024 Rob responded with comments to add "manhole adjusted to grade" note. 8/6/2024 Rob responded with comments to show the sanitary line crossing at some locations along Clough and adding a missing private sanitary line at the clough newtown intersection. 1/10/2025 Rob responded that MSD accepted the Stage 3 Plan. | UG
Santiary
1600 Gest Street
Cincinnati, Oh 45242
Charter Communications | (513) 386-5499 | Kent Rieger |  | 2023-08-18 |  | 2024-01-17 |  | 2024-08-05 |  | 2025-01-08 | 2025-01-08 |  |  | 1/8/2025 Jim confirmed that the telecome poles north of Clough do not belong to Charter Communication, and request Stantec to send project info concerning Charter Communications/Spectrum to DL-Southern-Ohio-Outside-Plant@charter.com | OH
Cable |  | Jim O'Reilly (Spectrum)
11252 Cornell Park Drive
Cincinnati, Oh 45242
Verizon Communications | (330) 253-8267 | Allan Guest |  | 2023-08-18 | 2023-08-18 | 2024-01-17 |  | 2024-08-05 |  | 2025-01-08 |  |  |  | 4/21/2025 Cynthia confirmed that they were not on the utility poles on the north side of Clough Pike. That they were on the utility poles on the south side of the Clough Pike that are not in conflict with the project. | UG
Telecom
120 Ravine St. |  | Cynthia Martinez |  | 2025-01-10: 2025-04-21
Akron, Ohio 44303
Greater Cincinnati Water Works | (513) 557-5799 | Jon Hunseder |  | 2023-08-18 |  | 2024-01-17 | 2024-01-29 | 2024-08-05 | 2024-08-26 | 2024-12-20 | 2024-12-26 |  |  | 1/29/2024 Earl responded with existing water plans to incorporate into the plans. Stated no concern between the water line and the proposed sidewalk. Showed concern with the proposed cut along Newtown road at the intersection of Clough Pike and the existing water line. 8/26/2024 Earl responded with concerns about the catch basin at Sta. 20+62 on west side of Newtown Road being too close to the water main and the vertical clearance might not enough from the water main. He requested a CAD for him to create a relocation plan.(Proposed as "to be removed" in Stage 3) - 12/20/2024: Proposed catch basin has been removed in the Stage 3 Plan, concern eliminited. Another concern Earl had was the vertical clearance of the proposed 18" Type B storm (D4) at the intersection from the water main laterally crossing Clough Pike at 76+38. - 12/20/2024: CAD files sent to GCWW along with Stage 3 Plan. 12/26/2024 Earl expressed a new concern about the proposed curb south of Clough and west of Newtown, which is running directly on top of the water main. - Concerns eliminated, no new curb proposed by Stantec. 1/9/2025 Call with Mike at GCWW. Discussed concerns with water line impacts along the south side of clough and at the storm crossing at Newtown. GCWW to design relocation plan for storm crossing at intersection of newtown, to be non performed during construction if enough clearance is between existing water and proposed storm. Working with geotechs for alternate subgrade stabilization on south side of clough to avoid water line impacts. 1/30/2025 - GCWW provided the finalized relocation plans and estimate of the water main at the Clough Newtown intersection underneath the proposed storm. 6/16/2025 - GCWW, ODOT, Anderson, Stantec had a virtual meeting to resolve waterline impact concerns. GCWW unable to confirm depth of waterline or perform test holes. Anderson to get test holes on water line. | UG
Water |  |  |  | 2024-08-05: 2024-12-20; 2025-01-10: 2025-01-30
1600 Gest St |  | Earl Bratfish
Cincinnati, Ohio 45204

## Impacts & Potential Conflicts
PID # 113602
HAM-Elstun Connection Phase 2
Utility Crossing / Conflict Locations
Assumed Utility Depths (if less than 18" of separation or utility required clearance violation MUST verify with utility or relocation must occur!
Depths are based upon project experience within D6. | [8 empty] | UTILITY TYPE KEY: | Utility
Water |  |  | 4' |  |  |  | 2025-07-16 |  | T | Telephone
Sanitary Sewer |  |  | N/A -Actual | [5 empty] | C | Cable
Storm Sewer |  |  | N/A-Actual | [5 empty] | FO | Fiber Optic
Telephone, Cable |  |  | 3' | [5 empty] | FODB | Fiber Optic Duct Bank
Fiber Optic, Electrical |  |  | 3' | [5 empty] | E | Electric
GAS |  |  | 3' | [5 empty] | EDB | Electric Duct Bank
GAS PIPELINE |  |  | 4' | [5 empty] | ST | Storm
[9 empty] | SAN | Sanitary
[9 empty] | W | Water
[9 empty] | G | Gas
[9 empty] | GHP | Gas High Pressure
[9 empty] | GPL | Gas Pipeline
[9 empty] | L OR ITS | ODOT OWNED
Ref. No. | Sheet No. | Starting Station | Offset & (RT or LT) | Ending Station | Offset & (RT or LT) | Length | Conflict Location Description | Possible Conflict with what? | # of inches of separation between Existing Utility and proposed work | Is the utility within their own easement? (Y OR N) | Utility Type- (See Key Above for Reference) | If Electric - What is Voltage of line? | Utility Owner | Conflict Resolution | Resolved by what date | Utility Clear Date (sale - 60)
Water
W-1 | 14 | 20+00 | 25' LT | 21+00 | 25' LT | 100 | Intersection of Clough Pike and Newtown road | Vertical clearance with proposed cut and exisiting water line. |  | N | W |  | Greater Cincinnati Water Works
[7 empty] | Clough Rd STA. 76+11.50 to MH3 and catch basin north of STA 76+30.80 | Storm crosses water main. Catch basin just north of Sta. 76+30.80 is too close to water main, invert is too shallow. |  |  | W/ST |  | Greater Cincinnati Water Works
Telecom
T-1 | 13 | 73+45 | 35' LT | 75+95 | 35' LT | 250 | North side of Clough Pike | Horizontal clearance with proposed pavement and existing utility poles. |  | N | T |  | Altafiber
MSD
[7 empty] | Clough Pike between STA 52+00 and 53+00 | Utility separation | 18" vertical, 10' horizontal |  |  |  | MSD