## PE to Stage 3
Squad Bravo Project Management Checklist/Workflow from Scope Complete to Stage 3 Complete
[5 empty] | Stg 3: | 2025-07-01 | Designer: | MVC
|  | Project: | HOL SR 179 3.900 |  | PPSF to CO: | Not in Ellis | Checker: |  |  |  | <--- Ray to Include in Preliminary Deliverables??
|  | PID: | 111085 |  | Award: | 2026-01-01 | Reviewer:
[6 empty] | Date Completed | Notes
Gather Project Information and Obtain Work to be Performed with Project
Review ELLIS information for the following:
| X | Location(s) of work |  |  |  | 2014-12-30 | Notes go here
| N/A | Need for Legislation |  |  |  | enter date here | Notes go here
| X | State Job Number |  |  |  | 2014-12-30 | Notes go here
| N/A | Federal Agreement Number (FAN) |  |  |  | enter date here | Notes go here
| X | Plan Splits |  |  |  | 2014-12-30 | Notes go here
| X | Check time line to next resurf project |  |  |  | enter date here | have paul check the next sch'd resurf proj, send him an email.
| See Notes | Check Schedule and Send email about schedule constraints |  |  |  | enter date here | At a minimum verify Stage 1, Env. Doc Appv'd, ROW Clear, Stage 3 and Plan file dates.
This would include beam rolling schedules, ROW and/or Environmental timelines.
|  | Field Review Project (take photos & measurements) |  |  |  | enter date here
|  | Update Construction Cost Estimate |  |  |  | enter date here | Include Contingency and Inflation
|  | Complete Cost of Engineering |  |  |  | enter date here
--- >> | See Notes | Check FEMA Floodzone - Should already be started by DEC. |  |  |  |  | Floodzone A
--- >> |  | Submit Floodplain Coordination - Initiation Letter (Copy Tom Stratton) |  |  |  |  | Only send if required. See I:\common\SEI WorkFolder\Design\Hydraulics\Floodplain Information
| X | Request Field Survey by IOC (or Email) to Jon Penix |  |  |  |  | Survey Complete
Include copy of necessary plan sheets (if avail.)
Include copy of R/W plan sheets (if avail.)
| N/A | Request Soil Borings |  |  |  | enter date here | Notes go here
After Field Survey is Completed
| X | Request field review by DURT. (xc Jason Beranek) |  |  |  | enter date here | Notes go here
| X | Request Ex. R/W from Steve Lucas |  |  |  | enter date here | Notes go here
| X | Use SHIFT Program to Calculate Design Designation |  |  |  | 2020-04-14 | Use 12 years for Repairs/Overlays and 20 Years for Rehabs/Replacement
| X | Design Pavement |  |  |  | 2022-12-07 | Notes go here
| N/A | If RxR involvement, contact Scott Warner |  |  |  | enter date here | Detour
|  | Develop MOTAA requied for Path 3, 4 & 5 projects |  |  |  | enter date here
Complete PE Review |  | HOL SR 179 3.900 | PID | 111085 |  |  | Supersquad PM Checklist
| X | Start Title Sheet and complete Design Designation
| X | Layout horizontal alignment (or check it based on what Jon Penix provided)
| X | Layout proposed profile
| X | Proposed Typical Section
Design Lane Width (surface only not full pavement structure)
| X | Design Shoulder Width (surface only not full pavement structure)
|  | Design Cross Slope, or full superelevation rate | [7 empty] | ???
| X | Proposed Approach Slab section
| X | Existing Typical Section
| X | Design pavement and transitions in plan view (only dimension odd transitions)
| X | Prepare prelim P&P sheets
| X | Design Transverse Section
| N/A | Design Phase Construction Details
| X | Discuss MOT scheme with Dist. Traffic Engineer |  |  |  | 2022-12-02 | If detour is determined, Send email asking CJV to coordinate with Schools and local EMS.
| X | Prepare Preliminary Site Plan
| X | Have Ray complete GCAT/GCam crash analysis
|  | Fill out DE form (All fields except superelevation) |  |  |  | enter date here | Notes go on the DE form
(I:\common\squad bravo\Design-exception-form.xlsm)
|  | Submit Plan to Squad Leader for Complete Preliminary Engineering Design Check. |  |  |  | enter date here | Notes go here
Squad Leader or PE to begin DE forms online
|  | Checker to fill out as much of bridge review checklist as possible |  |  |  | enter date here | Notes go here
Paper Copies |  | Prepare IOCs and Copies for submission to the following: |  |  |  | enter date here | Use 14-21 day turn around time
0 |  | Paul Herman | Pavement Buildup (via Email) |  |  | enter date here | Notes go here
0 |  | Waseem Khalifa | Scope Conformance (via Email) |  |  | enter date here | Notes go here
0 |  | Tom Stratton | Environmental (See Below) (via Email) |  |  | enter date here | Notes go here
0 |  | Jeremy Cessna | Utilities (via email link) |  |  | enter date here | Notes go here
0 | < - Total Paper Copies Needed
|  | Update DocReview portion of Ellis with the above information |  |  |  | enter date here | Notes go here
Update 'Minor Project Preliminary Engineering Study - Submitted' date in Ellis & mark 'Compl' Update 'Minor Project Preliminary Engineering Study - Approved' when comments are returned
Complete Stage 1 Design |  | HOL SR 179 3.900 | PID | 111085 | Due: | 2023-12-02 | Supersquad PM Checklist
|  | Analyze any crash patterns found with GCAT/GCAM tool (see CJV or Jason B.) for low cost solutions |  |  |  | enter date here | Notes go on the DE form
|  | Complete DE form (Including superelevation and all remaining items) |  |  |  | enter date here | Notes go on the DE form
|  | If DE Required - Submit DE to Kathy King & add a comment in Ellis |  |  |  | enter date here | Typical Ellis Comment may be "PE/DE approved by Squad Leader and Supervisor. DE submitted on xx.xx.xx."
| N/A | Request Legislation (If Needed) |  |  |  | enter date here | Notes go here
| No | Include Safety Edge? |  |  |  | enter date here | Notes go here
|  | Review scope for detailed list of work to be completed |  |  |  | enter date here | Notes go here
|  | Submit Plan to Squad Leader for Complete Stage 1 Design Check. |  |  |  | enter date here | Notes go here
---->>> |  | Update Estimate (send to: program manager, planning engineer and squad leader) |  |  |  | enter date here | Notes go here
|  | Checker to fill out as much of bridge review checklist as possible |  |  |  | enter date here | Notes go here
Paper Copies |  | Prepare IOCs and Copies for submission to the following: |  |  |  | enter date here | Notes go here |  | Per Phone call on 9/30/13 send all Stage 1 reviews to Jerred G. & he will distribute according to work load.
1 |  |  | Structure |  |  | enter date here | Notes go here
|  |  | Roadway & MOT |  |  | enter date here | Notes go here
0 |  | Cody Notz | Geotechnical (Via Email) |  |  | enter date here | Notes go here |  | County Managers
|  | Jerred Giauque | MOT / Constructability |  |  | enter date here | If Detour, ask construction to verify number of days need for detour. |  | Belmont | Dave Schafer
|  | Steve Lucas | ROW |  |  | enter date here | Notes go here |  | Carroll | Vince Carter
0 |  | Tom Stratton | Environmental (See Below) (via Email) |  |  | enter date here | Notes go here |  | Columbiana | Scott Jenkins
0 |  | Jeremy Cessna | Utilities (via email link) |  |  | enter date here | Notes go here |  | Harrison | JD Marlett
0 |  |  | County Manager (Via Email) |  |  | enter date here | Notes go here |  | Holmes | Darrell Hood
1 | < - Total Paper Copies Needed | [7 empty] | Jefferson | Ty Justice
[9 empty] | Tuscarawas | Dave Glazer
--- >> |  | Complete Floodplain Coordination (Copy Tom Stratton) |  |  |  |  | See I:\common\SEI WorkFolder\Design\Hydraulics\Floodplain Information
|  | Update DocReview portion of Ellis with the above information |  |  |  | enter date here | Notes go here
|  | Update 'Stage 1 Plans - Submitted' date in Ellis and mark it 'Completed'. Update 'Stage 1 Plans - Complete' date to the date you asked for comments on the IOC. |  |  |  |  | Notes go here
After Stage 1 is Returned
Update and mark as completed 'Stage 1 Plans - Complete' date in Ellis after Roadway & Structure comments are returned
If project is installing a Type A conduit, submit LD-33 to County Engineer and give them 60 days to review
Provide disposition of comments to reviewers if a comment was not addressed
Complete Stage 2 Design |  | HOL SR 179 3.900 | PID | 111085 | Due: | 2024-09-01 | Supersquad PM Checklist
MOT Notes and Quantities
Roadway Notes and Quantities
Pavement Quantities
Remaining Structure Notes and Details
Signs and other Traffic Control
Note: Essentially everything except the General Summary and Structure quantities.
Exceptions as per Squad Leader:
Notes for this section and things to not include get listed here
|  | If RxR involvement, contact Scott Warner |  |  |  | enter date here | Notes go here
|  | Check on Status of Legislation |  |  |  | enter date here | Notes go here
|  | Request Centerline Staking |  |  |  | enter date here | Notes go here
|  | Perform Post Construction BMP analysis and design (or submit to OHE for design) prior to continuing to Stage 2. |  |  |  |  | subject expert in co if needed dave riley (copy becky humphries) both of OHE.
|  | Review scope for detailed list of work to be completed |  |  |  | enter date here | Notes go here
|  | Perform Field Review of project to check for work required outside of scope |  |  |  | enter date here | Notes go here
|  | Submit Plan to Squad Leader for Complete Stage 2 Design Check. |  |  |  | enter date here | Notes go here
---->>> |  | Update Estimate (send to: program manager, planning engineer and squad leader) |  |  |  | enter date here | Notes go here
|  | Checker to fill out as much of bridge review checklist as possible |  |  |  | enter date here | Notes go here
Paper Copies |  | Prepare IOCs and Copies for submission to the following: |  |  |  | enter date here | Notes go here
1 |  |  | Structure |  |  | enter date here | Notes go here
|  |  | Roadway & MOT |  |  | enter date here | Notes go here
0 |  | Cody Notz | Geotechnical (Via Email) |  |  | enter date here | Notes go here
|  | Todd Moore | MOT / Constructability |  |  | enter date here | Notes go here
|  | Steve Lucas | ROW |  |  | enter date here | Notes go here
0 |  | Tom Stratton | Environmental (See Below) (Via Email) |  |  | enter date here | Notes go here
0 |  | Jeremy Cessna | Utilities (via email link) |  |  | enter date here | Notes go here
Note: Inform DURT they are final tracings less quantities.
0 |  |  | County Manager via Email |  |  | enter date here | Notes go here
1 | < - Total Paper Copies Needed
|  | Update DocReview portion of Ellis with the above information |  |  |  | enter date here | Notes go here
|  | Update 'Stage 2 Plans - Submitted' date in Ellis and mark it 'Completed'. Update 'Stage 2 Plans - Complete' date to the date you asked for comments on the IOC. |  |  |  |  | Notes go here
|  | Request Load Rating Report |  |  |  | enter date here | Notes go here
After Stage 2 is Returned
Complete revisions or address comments
|  | Complete NOI Maps and Form |  |  |  |  | Notes go here
Update and mark as completed 'Stage 2 Plans - Complete' date in Ellis after Roadway & Structure comments are returned
Provide disposition of comments to reviewers if a comment was not addressed
Complete Stage 3 Design |  | HOL SR 179 3.900 | PID | 111085 | Due: | 2025-06-01 | Supersquad PM Checklist
|  | Verify Need for Airway/Highway Clearance |  |  |  | enter date here | Notes go here
General Summary (Seed file is: I:\ODOTstd\V8istd\Cadig\Excel Standard Sheets\GENSUM_VBA_Trnsport.xls )
Structure Quantity Calculations
|  | Plan Certification of Roadway Quantities |  |  |  | enter date here | Notes go here
|  | Plan Certification of Structure Quantities |  |  |  | enter date here | Notes go here
|  | If RxR involvement, contact Scott Warner |  |  |  | enter date here | Notes go here
|  | Check on Status of Legislation |  |  |  | enter date here | Notes go here
|  | Check on Status of ER Documentation |  |  |  | enter date here | Notes go here
|  | Review scope for detailed list of work to be completed |  |  |  | enter date here | Notes go here
|  | Submit Plan to Squad Leader for Complete Stage 3 Design Check. |  |  |  | enter date here | Notes go here
---->>> |  | Update Estimate (send to: program manager, planning engineer and squad leader) |  |  |  | enter date here | Notes go here
|  | Checker to fill out as much of bridge review checklist as possible |  |  |  | enter date here | Notes go here
Paper Copies |  | Prepare IOCs and Copies for submission to the following: |  |  |  | enter date here | Notes go here
1 |  |  | Structures |  |  | enter date here | Notes go here
|  |  | Roadway |  |  | enter date here | Notes go here
|  | Todd Moore | Construction Reviewer |  |  | enter date here | Inform Construction if there are in-stream work restrictions.
Construction Email/IOC to include a request to confirm the Construction Duration from Construction Duration Tool. An Email confimation is required to be sent in with the Plan Package.
|  | Steve Lucas | Real Estate |  |  | enter date here | Notes go here
0 |  | Tom Stratton | Environmental (via Email) |  |  | enter date here | Notes go here
0 |  | Cody Notz | Geotech (Via Email) |  |  | enter date here | Notes go here
1 | < - Total Paper Copies Needed
|  | Update DocReview portion of Ellis with the above information |  |  |  | enter date here | Notes go here
Update 'Stage 3 Plans - Submitted' date in Ellis and mark it 'Completed'. Update 'Stage 3 Plans - Complete' date to the date you asked for comments on the IOC.
Complete revisions or address comments
Update and mark as completed 'Stage 3 Plans - Complete' date in Ellis after Roadway & Structure comments are returned
Provide disposition of comments to reviewers if a comment was not addressed
Formulas:
enter date here = IF(VLOOKUP(D4,[1]ProjectInfo!$A3:AD5001,4,FALSE)<1000,"Not in Ellis",VLOOKUP(D4,[1]ProjectInfo!$A3:AD5001,4,FALSE)-30)

## ScoopSheet (hidden)
Proj.: | HOL SR 179 3.900
PID: | 111085 |  | Squad Bravo Workers: | Crisi and Ray and Whoever Else
Work Type: |  | Bridge Preservation
Date to Next Submission:
Status:
Scope and Individual Work Items:
Misc. Proj. Man. Notes and Outstanding Items:
Critical Tasks or Work Items:
c:\users\mclark3\appdata\local\bentley\projectwise\workingdir\ohiodot-pw.bentley.com_ohiodot-pw-02\michael.clark@dot.ohio.gov\d0512215\[111085_PM_Workflow_Checklist.xlsx]PE to Stage 3