ITEM 614 - MAINTAINING TRAFFIC:

ALL TRAFFIC CONTROL DEVICES SHALL BE FURNISHED, ERECTED, MAINTAINED, AND REMOVED BY THE CONTRACTOR IN ACCORDANCE WITH THE OHIO MANUAL OF UNIFORM TRAFFIC CONTROL DEVICES (CURRENT EDITION).  COPIES ARE AVAILABLE FROM,

THE OHIO DEPARTMENT OF TRANSPORTATION

BUREAU OF TRAFFIC,

1980 WEST BROAD STREET

COLUMBUS, OHIO 43223

THE CONTRACTOR SHALL NOT ORDER MATERIALS OR PERFORM WORK LISTED IN THE GENERAL SUMMARY FOR ITEMS DESIGNATED BY PLAN NOTE TO BE USED "AS DIRECTED BY THE ENGINEER" UNLESS AUTHORIZED BY THE ENGINEER.

CONSTRUCTION OPERATIONS SHALL NOT BEGIN UNTIL ALL TRAFFIC CONTROL IS IN PLACE AND APPROVED BY ODOT PERSONNEL.  THE CONSTRUCTION INSPECTOR SHALL APPROVE ALL TEMPORARY TRAFFIC CONTROL DEVICES FOR CONDITION AND LOCATION BEFORE THE CONTRACTOR WILL BE ALLOWED TO BEGIN WORK.  IF THE CONTRACTOR DOES NOT COMPLY WITH THE STANDARDS, HIS PERMIT SHALL BE REVOKED AND ALL WORK SHALL BE TERMINATED.

ALL WORK AND TRAFFIC CONTROL DEVICES SHALL BE IN ACCORDANCE WITH 614 AND OTHER APPLICABLE PORTIONS OF THE SPECIFICATIONS, AS WELL AS THE OHIO MANUAL OF UNIFORM TRAFFIC CONTROL DEVICES.  PAYMENT FOR ALL LABOR, EQUIPMENT, AND MATERIALS SHALL BE INCLUDED IN THE LUMP SUM CONTRACT PRICE FOR 614, MAINTAINING TRAFFIC, UNLESS SEPARATELY ITEMIZED IN THE PLAN.

ITEM 614, MAINTENANCE OF TRAFFIC:

BELOW IS A SUMMARY OF THE MOT REQUIREMENTS FOR THIS PROJECT:

* FULL CLOSURE WITH DETOUR FOR NO MORE THAN 12 CONSECUTIVE CALENDAR DAYS SHALL BE PERMITTED TO COMPLETE WORK IN PHASE 1. PHASE 1 CONSISTS OF WORK IS BETWEEN SLM 4.70 – SLM 5.69 EASTBOUND.

* FULL CLOSURE WITH DETOUR FOR NO MORE THAN 12 CONSECUTIVE CALENDAR DAYS SHALL BE PERMITTED TO COMPLETE WORK IN PHASE 2. PHASE 2 CONSISTS OF WORK BETWEEN SLM 6.05– SLM 7.14 WESTBOUND.

* FULL CLOSURE WITH DETOUR FOR NO MORE THAN 25 CONSECUTIVE CALENDAR DAYS SHALL BE PERMITTED TO COMPLETE WORK IN PHASE 3. PHASE 3 CONSISTS OF WORK BETWEEN SLM 7.59 TO SR-746 (SLM 9.035)

* FULL CLOSURE WITH DETOUR FOR NO MORE THAN 7 CONSECUTIVE CALENDAR DAYS SHALL BE PERMITTED TO COMPLETE WORK IN PHASE 4. PHASE 4 CONSISTS OF WORK BETWEEN SR-746 TO MORROW COUNTY LINE (SLM 9.287)

WORK IN PHASES 1, 2, 3 AND 4 SHALL BE COMPLETED UNDER A FULL CLOSURE WITH DETOUR SIGNAGE AS SHOWN ON SHEETS 8-11. SHEET 8-11 SHOWS THE PLACEMENT OF ROAD CLOSED BARRICADES FOR EACH PHASE. THE CONTRACTOR IS RESTRICTED TO WHEN PHASE 4 WORK SHALL STARTED OR SHALL BE COMPLETED, SEE BELOW FOR MORE INFORMATION.

PHASE 4 WORK AND SUBSEQUENT DETOUR SHALL BE COORDINATED WITH ADJACENT ODOT PROJECT: MRW-229/529-4.00/0.00 PID:105534, PROJECT ENGINEER: DENNIS WADE & CONTRACTOR: SHELLY & SANDS, INC. THE WORK SHALL BEGIN DIRECTLY AFTER THE COMPLETION/END OF THEIR DETOURS WHICH IS REQUIRED COMPLETE BRIDGE WORK ON S-529 OR SHALL BE COORDINATED IN A MANNER TO END DIRECTLY PRIOR TO THE BEGIN OF PROJECTS, MRW-529 DETOUR. NO DAYS SHALL ELAPSE BETWEEN THE DETOUR REQUIRED TO COMPLETE THE BRIDGE WORK ON MRW-229-529-4.00/0.00 AND THE DETOUR REQUIRED TO COMPLETED OR BEGIN PHASE 4 WORK. THE GOAL IS TO AVOID ANY UNNECESSARY TIME PERIODS BETWEEN CLOSURE AND OPENING OF THE ROUTE BETWEEN PROJECTS THAT WOULD CAUSE ANY CONFUSION TO THE GENERAL PUBLIC.

THE CONTRACTOR SHALL LIMIT DOWNTIME BETWEEN PHASES TO 5 DAYS MAXIMUM.

public outreach and notification (Road CLOSURE)

The contractor shall be responsible for contacting the District 6 Public Information Office VIA EMAIL At d06.pio@dot.ohio.gov  to coordinate efforts to notify all local County, State and Federal emergency services, school districts and adjacent residents and businesses of the upcoming closure. Advance notification shall occur no later than twenty-one  (21) days prior to closing the road. If, subsequent to the advance notification, the start date is changed, then a new seven (7) day notification will be required. The road cannot be closed unless prior notification has been accomplished. The same parties shall be notified when the closure has concluded and the road is back open to traffic. all notifications shall be made utilizing the template provided by the District 6 public information office.

ITEM 614, Maintaining traffic (notice of closure sign)

Notice of Closure signs, W20-H13, shall be erected by the Contractor prior to the scheduled road or ramp closure in accordnace with the notice of closure time table below.[at the approval of the engineer, portable changeable message signs may be used in lieu of the standard flatsheet sign for closure durations of less than 1 week.]

The signs shall be erected on the right-hand side of the road/ramp facing traffic. They shall be placed so as not to interfere with the visibility of any other traffic control signs. On roadways, they should be erected at OR NEAR the point of closure. The signs may be erected anywhere on ramps as long as they are visible to the motorists using the ramp. On entrance ramps, the sign shall be erected well in advance of the merge area to avoid distracting motorists.

| Notice of Closure Sign Time Table |  |  |  |
| --- | --- | --- | --- |
| Item | Duration of Closure | Sign Display to Public | Notification due to District 6 Communications Office |
| Ramp & Road Closures | >= 2 weeks | 14 calendar days prior to closure | 21 calendar days prior to closure |
|  | > 12 hours & < 2 weeks | 7 calendar days prior to closure | 14 calendar days prior to closure |
|  | < 12 hours | 2 business days prior to closure | 4 business days prior to closure |

THE SIGN SHALL DISPLAY THE DATE OF THE CLOSURE IN MMM-DD FORMAT AND THE NUMBER OF DAYS OF THE CLOSURE. THE LAST LINE OF THE W20-H13 SIGN SHALL DISPLAY THE PHONE NUMBER OF THE District 6 public information construction line, (740)833-8268, WHICH A MOTORIST MAY CALL FOR ADDITIONAL INFORMATION.

Notification of Traffic Restrictions:

Throughout the duration of the project, the contractor shall notify the project engineer in writing of all traffic restrictions and upcoming maintenance of traffic changes. The contractor shall ensure the written notification is submitted in a timely manner to allow the project engineer to meet the required time frames set forth in the table below to inform Special Hauling Permits Section (Hauling.Permits@dot.ohio.gov) and the District Public Information Office (PIO). This notification shall be received by the project engineer prior to the physical setup of any applicable signs or message boards.

Information should include but is not limited to all construction activities that impact or interfere with traffic

Notification of Traffic Restrictions (Cont’d):

and shall list the specific location, type of work, road status, date and time of restriction, duration of restriction, number of lanes maintained, number of lanes closed, minimum vertical clearance, minimum width of drivable pavement, detour routes if applicable, and any other information requested by the project engineer.

| Notification Time Frame Table |  |  |  |
| --- | --- | --- | --- |
| Item | Duration of Closure | Notification due to District 6 Communications Office | Sign Displayed to Public |
| Ramp & Road Closures | >= 2 weeks | 21 calendar days prior to closure | 14 calendar days prior to closure |
|  | > 12 hours & < 2 weeks | 14 calendar days prior to closure | 7 calendar days prior to closure |
|  | < 12 hours | 4 business days prior to closure | 2 business days prior to closure |
| Lane Closures & Restrictions | >= 2 weeks | 14 calendar days prior to closure |  |
|  | < 2 weeks | 5 business days prior to closure |  |
| Start of Construction & Traffic Pattern Changes | N/A | 14 calendar days prior to implementation |  |

Any unforeseen conditions not specified in the plans requiring traffic restrictions shall also be reported to the project engineer using the Notification Time Frame Table.

Lanes Open During Holidays And Special Events:

No work shall be performed and the same number of lanes as were available at the start of the project shall be open to traffic during the following designated holidays and events:

HOLIDAYS

Christmas		Fourth of July

New Year’s Eve	Labor Day

Memorial Day	Thanksgiving

The period of time that the lanes are to be open depends on the day of the week on which the holiday falls.  The following schedule shall be used to determine this period:

| Day of holiday | Time all lanes must be open to traffic |
| --- | --- |
| Sunday | 12:00 Noon Friday through 6:00 AM Monday |
| Monday | 12:00 Noon Friday through 6:00 AM Tuesday |
| Tuesday | 12:00 Noon Monday through 6:00 AM Wednesday |
| Wednesday | 12:00 Noon Tuesday through 6:00 AM Thursday |
| Thursday | 12:00 Noon Wednesday through 6:00 AM Friday |
| Thanksgiving | 5:00 AM wednesday through 6:00 AM Monday |
| Friday | 12:00 Noon Thursday through 6:00 AM Monday |
| Saturday | 12:00 Noon Friday through 6:00 AM Monday |

SPECIAL EVENTS:

IRONMAN OHIO 70.3 – LANE OR SHOULDER CLOSURES ARE NOT PERMITTED DURING the IRON MAN OHIO DURING THE EVENT OR THE WEEK PRECEDING IT ON THE FOLLOWING ROUTES:

sr 529 BETWEEN SR 98 AND SR 746

SR 98 BETWEEN US 23 AND SR 309

Lanes Open During Holidays And Special Events (CONT’D):

THE CONTRACTOR SHALL NOT WORK WITHIN THE INTERSECTION OF SR 529 AND SR 98 DURING THIS EVENT.

No extensions of time shall be granted for delays in material deliveries, unless such delays are industry wide, or for labor strikes, unless such strikes are area wide.

Should the contractor fail to meet any of these requirements, the Contractor shall be assessed a disincentive in the amount of $100 for each minute the above described lane closure restrictions are violated.

USE OF STANDARD DRAWINGS:

FOR THE PURPOSE OF THIS PROJECT, "MOVING OPERATION" SHALL BE LIMITED TO PAVEMENT MARKING STRIPING.

IT MAY BE NECESSARY TO EXTEND THE ADVANCE WARNING AND BUFFER ZONES BEYOND THE MINIMUM DISTANCES SHOWN ON THE STANDARD DRAWINGS.  THIS MAY BE DUE TO HORIZONTAL ALIGNMENT, VERTICAL ALIGNMENT, RAMP LOCATIONS, OR OTHER SIGHT OBSTRUCTIONS.  LOCATIONS OF THE TAPER ZONES MAY BE ADJUSTED AS DIRECTED BY

THE ENGINEER, BUT TAPER LENGTHS MUST MEET THE MINIMUM STANDARDS.  TAPERS SHOULD BE PLACED IN TANGENT SECTIONS WHENEVER POSSIBLE.  ADDITIONAL YIELD SIGNS MAY BE REQUIRED FOR RAMPS WITHIN 1,000 FEET OF A WORK ZONE.  PAYMENT SHALL BE INCLUDED IN THE LUMP SUM CONTRACT PRICE FOR ITEM 614 - MAINTAINING TRAFFIC.

TRUCK MOUNTED ATTENUATOR (TMA) – TWO LANE ROADS:

WHEN WORKING IN A CLOSED LANE OR SHOULDER ON A TWO-LANE HIGHWAY WITHOUT TEMPORARY OR PERMANENT TRAFFIC BARRIERS SEPARATING THE WORK AREA FROM THE TRAVELED LANE, A TRUCK MOUNTED ATTENUATOR (TMA) SHALL BE PROVIDED TO PROTECT EACH WORK AREA IN ACCORDANCE WITH OMUTCD TYPICAL APPLICATION (TA) 4, TA-6 AND TA-17, ALONG WITH STANDARD CONSTRUCTION DRAWING (SCD) MT-97.10. THE TMA SHALL BE PLACED IN SUCH A WAY TO ADEQUATELY PROTECT THE WORKERS INSIDE THE WORK ZONE. THE TMA IS NOT INTENDED TO BE USED AS OR SUBSTITUTED FOR THE FLAGGERS AND/OR WARNING SIGNS AND DEVICES. FURNISH A TMA THAT IS NCHRP-350 (MANUFACTURED PRIOR TO 1/1/20) OR MASH TL-3 COMPLIANT. THE COST FOR PROVIDING THE TMA SHALL INCLUDE ALL MATERIAL, LABOR, EQUIPMENT, AND HARDWARE REPLACEMENT AND IS TO BE INCLUDED IN THE LUMP SUM BID PRICE FOR ITEM 614 – MAINTAINING TRAFFIC.

USE OF WEIGHTED CHANNELIZERS:

THE WEIGHTED CHANNELIZERS MAY BE USED IN ACCORDANCE WITH THIS SECTION.  THE WEIGHTED CHANNELIZERS SHALL BE PREDOMINANTLY ORANGE IN COLOR AND SHALL BE MADE OF LIGHTWEIGHT, FLEXIBLE, AND DEFORMABLE MATERIAL.  THEY SHALL BE AT LEAST 42 INCHES IN HEIGHT WITH A WEIGHTED BASE.  THEY MAY HAVE A HANDLE OR LIFTING DEVICE, WHICH EXTENDS ABOVE THE 42" MINIMUM HEIGHT.

THE MARKINGS ON THE WEIGHTED CHANNELIZERS SHALL BE HORIZONTAL, CIRCUMFERENTIAL, ALTERNATING ORANGE AND WHITE RETRO REFLECTIVE STRIPES 6 INCHES WIDE.  EACH WEIGHTED CHANNELIZER SHALL HAVE A MINIMUM OF TWO ORANGE AND TWO WHITE STRIPES.  ANY NON-RETRO REFLECTIVE SPACES BETWEEN THE HORIZONTAL ORANGE AND WHITE STRIPES SHALL NOT EXCEED 2 INCHES WIDE.  THE WEIGHTED CHANNELIZERS SHALL HAVE A 4-INCH MINIMUM WIDTH, REGARDLESS OF ORIENTATION.

USE OF WEIGHTED CHANNELIZERS ON FREEWAYS AND MULTILANE HIGHWAYS SHALL BE LIMITED TO SHORT-TERM OPERATION FOR EITHER DAY OR NIGHT.  UPON COMPLETION OF WORK, THE WEIGHTED CHANNELIZERS SHALL BE REMOVED.  THE WEIGHTED CHANNELIZERS MAY AGAIN BE PLACED ON THE HIGHWAY WHEN THE WORK IS TO RESUME ON THE FOLLOWING DAY OR NIGHT.  ANY LANE CLOSURE USING CHANNELIZATION DEVICES, EXPECTED TO REMAIN FOR MORE THAN TWELVE HOURS, SHALL REQUIRE THE USE OF DRUMS OR BARRIERS.  WORK IS TO RESUME ON THE FOLLOWING DAY OR NIGHT.

USE OF WEIGHTED CHANNELIZERS:

WHEN USED AT NIGHT, WEIGHTED CHANNELIZERS SHALL ONLY BE PLACED IN THE TANGENT AREA.  THE TANGENT AREA IS DEFINED AS THE AREA AFTER THE TRANSITION TAPER WHERE THE WORK TAKES PLACE.  DRUMS SHALL BE USED IN THE TRANSITION TAPERS FOR

NIGHT OPERATIONS.  MAXIMUM SPACING OF THE WEIGHTED CHANNELIZERS SHALL BE 40 FEET.

STEPS SHOULD BE TAKEN TO ENSURE THAT THE WEIGHTED CHANNELIZERS WILL NOT BE BLOWN OVER OR DISPLACED BY WIND OR MOVING TRAFFIC.  BALLASTS SHOULD NOT PRESENT A HAZARD IF THE WEIGHTED CHANNELIZERS ARE INADVERTENTLY STRUCK, NOR SHOULD THEY AFFECT THE VISIBILITY OF THE WEIGHTED CHANNELIZERS.  ALL BALLASTS USED SHOULD BE IN ACCORDANCE WITH THE MANUFACTURER'S SPECIFICATIONS.

WORK SITE LIGHTING:

FLOODLIGHTING OF THE WORK SITE FOR OPERATIONS CONDUCTED DURING NIGHTTIME PERIODS SHALL BE ACCOMPLISHED SO THAT THE LIGHTS DO NOT CAUSE GLARE TO THE DRIVERS ON THE ROADWAY.  TO ENSURE THE ADEQUACY OF THE FLOODLIGHT PLACEMENT, THE CONTRACTOR, AND THE ENGINEER SHALL DRIVE THROUGH THE WORK SITE EACH NIGHT WHEN THE LIGHTING IS IN PLACE AND OPERATIVE PRIOR TO COMMENCING ANY WORK.  IF GLARE IS DETECTED, THE LIGHT PLACEMENT AND SHIELDING SHALL BE ADJUSTED TO THE SATISFACTION OF THE ENGINEER BEFORE WORK PROCEEDS.  PAYMENT FOR ALL LABOR, EQUIPMENT, AND MATERIALS SHALL BE INCLUDED IN THE LUMP SUM CONTRACT PRICE FOR ITEM 614, MAINTAINING TRAFFIC.

ITEM 614 - DETOUR SIGNing

Size and placement of detour signs (M4-9) should follow the requirements of the OMUTCD Section 6F.03, section 2a.11 and Table 6F.01.

detour signing shall provide drivers adequate time to clearly read the signs and make the proper decisions at each required turning movement.  The designated detour route shall be signed in accordance with the requirements below:

- Approximately 1500 feet prior to tip of the painted gore at an interchange when exiting a high speed (45 mph or higher) facility.

- At or near the existing sign in the gore of an interchange ramp.

- At or near the first existing lane assignment sign on an interchange exit ramp.

- At or near the existing lane assignment sign or existing route marker at the end of an exit ramp.

- Approximately 500 feet prior to a required turn at an intersection not controlled by a stop sign (for 45 mph or higher only).

- At or near the existing lane assignment sign or existing route marker at an intersection.

- Every two miles along a tangent section between turning movements outside a city.

- Every two blocks along a tangent section between turning movements within a city.

- At any other intersection or decision point where the detour route is contrary to the normal, expected turning maneuver or otherwise unclear.

Detour signs shall be placed, when possible, next to but not blocking existing route markers or lane assignment signs.  Detour signs shall not obscure or be obscured by other existing or temporary signs.

ITEM 614 - DETOUR SIGNing(CONT’D):

Detour signs shall be erected and/or uncovered prior to the road or ramp being closed to traffic but no earlier than four hours prior to the closure. Detour signs shall be covered and/or removed no later than four hours following the road or ramp re-opening to traffic.

Payment for accepted quantities will be made at the contract unit price. Payment shall be for all materials, labor, incidentals and equipment for furnishing, proper sign placement and sizing, timely erecting and/or uncovering of signs, maintaining signs, and timely covering and/or removing signs and supports.

The following estimated quantities have been carried to the General Summary.

Item 614 - Detour Signing                          = LUMP SUM

DESIGNATED LOCAL DETOUR ROUTE

IN ADDITION TO THE OFFICIAL, SIGNED DETOUR ROUTE, A LOCAL ROUTE HAS BEEN DETERMINED TO BE THE SECONDARY, UNSIGNED DETOUR ROUTE OR “DESIGNATED LOCAL DETOUR ROUTE.” THIS ROUTE IS SHOWN ON SHEET NO.9-10. DURING THE TIME THAT TRAFFIC IS DETOURED, THE CONTRACTOR SHALL MAINTAIN THIS ROUTE IN A CONDITION WHICH IS REASONABLY SMOOTH AND FREE FROM HOLES, RUTS, RIDGES, BUMPS, DUST AND STANDING WATER. ONCE THE DETOUR IS REMOVED AND TRAFFIC RETURNED TO ITS NORMAL PATTERN, THE DESIGNATED LOCAL DETOUR ROUTE SHALL BE RESTORED TO A CONDITION THAT IS EQUIVALENT TO THAT WHICH EXISTED PRIOR TO ITS USE FOR THIS PURPOSE. ALL SUCH WORK SHALL BE PERFORMED WHEN AND AS DETERMINED BY THE ENGINEER.

THE FOLLOWING ESTIMATED QUANTITIES ARE PROVIDED FOR USE AS DETERMINED BY THE ENGINEER TO MAINTAIN AND SUBSEQUENTLY RESTORE THE DESIGNATED LOCAL DETOUR ROUTE.

ITEM 441, ASPHALT CONCRETE SURFACE COURSE, TYPE 1, (448) PG 64-22		______					   350   CU. YD.

ITEM 407, TACK COAT						238 GAL.

ITEM 614, ASPHALT CONCRETE FOR MAINTAINING TRAFFIC 			______50 CU. YD.

ITEM 617, COMPACTED AGGREGATE, TYPE A 			20  CU. YD.

ITEM 617, WATER							___1 M. GAL.

ITEM 642, CENTER LINE, TYPE 1					1 MILE

ITEM 614, LAW ENFORCEMENT OFFICER (WITH PATROL CAR) FOR ASSISTANCE DURING CONSTRUCTION OPERATIONS

USE OF LAW ENFORCEMENT OFFICERS (LEOS) BY CONTRACTORS OTHER THAN THE USES SPECIFIED BELOW WILL NOT BE PERMITTED AT PROJECT COST. LEOS SHOULD NOT BE USED WHERE THE OMUTCD INTENDS THAT FLAGGERS BE USED.

IN ADDITION TO THE REQUIREMENTS OF C&MS 614 AND THE OMUTCD, A UNIFORMED LEO WITH AN OFFICIAL PATROL CAR (CAR WITH TOP-MOUNTED EMERGENCY FLASHING LIGHTS AND COMPLETE MARKINGS OF THE APPROPRIATE LAW ENFORCEMENT AGENCY) SHALL BE PROVIDED FOR THE FOLLOWING TRAFFIC CONTROL TASKS:

- DURING THE ENTIRE ADVANCE PREPARATION AND CLOSURE SEQUENCE WHERE COMPLETE BLOCKAGE OF TRAFFIC IS REQUIRED.

- DURING A TRAFFIC SIGNAL INSTALLATION WHEN IMPACTING THE NORMAL FUNCTION OF THE SIGNAL OR THE FLOW OF TRAFFIC, OR WHEN TRAFFIC NEEDS TO BE DIRECTED THROUGH AN ENERGIZED TRAFFIC SIGNAL CONTRARY TO THE SIGNAL DISPLAY (E.G., DIRECTING MOTORISTS THROUGH A RED LIGHT).

ITEM 614, LAW ENFORCEMENT OFFICER (WITH PATROL CAR) FOR ASSISTANCE DURING CONSTRUCTION OPERATIONS (CONT’D):

IN ADDITION TO THE REQUIREMENT OF C&MS 614 AND THE OMUTCD, A UNIFORMED LEO WITH AN OFFICIAL PATROL CAR (CAR WITH TOP-MOUNTED EMERGENCY FLASHING LIGHTS AND COMPLETE MARKINGS OF THE APPROPRIATE LAW ENFORCEMENT AGENCY) SHOULD BE PROVIDED FOR THE FOLLOWING TRAFFIC CONTROL TASKS AS APPROVED BY THE ENGINEER:

- FOR LANE CLOSURES: DURING INITIAL SET-UP PERIODS, TEAR DOWN PERIODS, SUBSTANTIAL SHIFTS OF A CLOSURE POINT OR WHEN NEW LANE CLOSURE ARRANGEMENTS ARE INITIATED FOR LONG-TERM LANE CLOSURES/SHIFTS (FOR THE FIRST AND LAST DAY OF MAJOR CHANGES IN TRAFFIC CONTROL SETUP).

IN GENERAL, LEOS SHOULD BE POSITIONED IN ADVANCE OF AND ON THE SAME SIDE AS THE LANE RESTRICTION OR AT THE POINT OF ROAD CLOSURE, AND TO MANUALLY CONTROL TRAFFIC MOVEMENTS THROUGH SIGNALIZED INTERSECTIONS IN WORK ZONES.

LEOS SHOULD NOT FORGO THEIR TRAFFIC CONTROL RESPONSIBILITIES TO APPREHEND MOTORISTS FOR ROUTINE TRAFFIC VIOLATIONS. HOWEVER, IF A MOTORIST’S ACTIONS ARE CONSIDERED TO BE RECKLESS, THEN PURSUIT OF THE MOTORIST IS APPROPRIATE.

THE LEOS WORK AT THE DIRECTION OF THE CONTRACTOR. THE CONTRACTOR IS RESPONSIBLE FOR SECURING THE SERVICES OF THE LEOS WITH THE APPROPRIATE AGENCIES AND COMMUNICATING THE INTENTIONS OF THE PLANS WITH RESPECT TO DUTIES OF THE LEOS. THE ENGINEER SHALL HAVE FINAL CONTROL OVER THE LEOS’ DUTIES AND PLACEMENT, AND WILL RESOLVE ANY ISSUES THAT MAY ARISE BETWEEN THE TWO PARTIES.

ENSURE PROVIDED LEOS HAVE BEEN TRAINED APPROPRIATE TO THE JOB DECISIONS THEY ARE REQUIRED TO MAKE WHILE ON THE PROJECT, IN ACCORDANCE WITH C&MS 614.03.

THE LEO SHALL REPORT IN TO THE CONTRACTOR PRIOR TO THE START OF THE SHIFT, IN ORDER TO RECEIVE INSTRUCTIONS REGARDING SPECIFIC WORK ASSIGNMENTS DURING HIS/HER SHIFT.

THE LEO IS EXPECTED TO STAY AT THE PROJECT SITE FOR THE ENTIRE DURATION OF HIS/HER SHIFT. THE LEO SHALL REPORT TO THE CONTRACTOR AT THE END OF HIS/HER SHIFT. SHOULD IT BE NECESSARY TO LEAVE THE PROJECT SITE, THE LEO SHALL NOTIFY THE ENGINEER. THE CONTRACTOR SHALL PROVIDE THE LEO WITH A TWO-WAY COMMUNICATION DEVICE WHICH SHALL BE RETURNED TO THE CONTRACTOR AT THE END OF HIS/HER SHIFT.

LEOS (WITH PATROL CAR) REQUIRED BY THE TRAFFIC MAINTENANCE TASKS ABOVE SHALL BE PAID FOR ON A UNIT PRICE (HOURLY) BASIS UNDER ITEM 614, LAW ENFORCEMENT OFFICER (WITH PATROL CAR) FOR ASSISTANCE. THE FOLLOWING ESTIMATED QUANTITIES HAVE BEEN CARRIED TO THE GENERAL SUMMARY.

ITEM 614, LAW ENFORCEMENT OFFICER WITH PATROL CAR FOR ASSISTANCE 48 HOURS

THE HOURS PAID SHALL INCLUDE ANY MINIMUM SHOW-UP TIME REQUIRED BY THE LAW ENFORCEMENT AGENCY INVOLVED.

ANY ADDITIONAL COSTS (ADMINISTRATIVE OR OTHERWISE) INCURRED BY THE CONTRACTOR TO OBTAIN THE SERVICES OF AN LEO ARE INCLUDED WITH THE BID UNIT PRICE FOR ITEM 614, LAW ENFORCEMENT OFFICER WITH PATROL CAR FOR ASSISTANCE.

ITEM 614 - WORK ZONE MARKING SIGN, AS PER PLAN:

THE FOLLOWING WORK ZONE MARKING SIGNS HAVE BEEN PROVIDED TO BE USED IN AREAS WHERE PAVEMENT REPAIR MATERIAL COMPROMISES THE VISIBILITY OF THE EXISTING PAVEMENT MARKING. THE SIGN TYPES LISTED BELOW ARE TO BE CONSIDERED CONTINGENCY ITEMS AND SHALL BE USED AS DIRECTED BY THE ENGINEER.

|  |  | R4-1-18 |
| --- | --- | --- |
|  |  | NO |
| LOC | ROUTE | EDGE |
|  |  | LINES |
|  |  | EACH |
| 1 | MAR-739 | 10 |
|  | TOTAL | 10 |

THE FOLLOWING QUANTITY HAS BEEN PROVIDED AND THE TOTAL HAS BEEN CARRIED TO THE GENERAL SUMMARY.

ITEM 614 - WORK ZONE MARKING SIGN, AS PER PLAN     = 10 EACH

DROP-OFFS IN WORK ZONES:

THE DROP-OFF ADJACENT TO THE TRAVEL LANE SHALL MEET THE CRITERIA OUTLINED IN STANDARD DRAWING MT-101.90. NO ADDITIONAL COMPENSATION SHALL BE MADE FOR MATERIALS, LABOR OR EQUIPMENT NECESSARY TO MEET THE REQUIREMENTS OF MT-101.90.

COORDINATION WITH ADJACENT PROJECTS

THE CONTRACTOR SHALL COORDINATE WORK WITH ODOT and THE CONTRACTORS ON THE ADJACENT PROJECTS. mrw-229/529-4.00/0.00 pid:105534. COORDINATION shall be made to prevent CONFLICTING ADVANCE WARNING SIGNS, conflicting detour routes, overlaping/conflicting lane closures, and to ensure that a minimum distance of 2 miles between adjacent lane closures is maintained. THIS IS NOT AN EXHAUSTIVE LIST OF COORDINATION ITEMS THAT MAY NEED TO BE RESOLVED BETWEEN PROJECTS. the department reserves the right to decide which project’s activities take precedence. Projects that have activities delayed due to conflicts will consider this an excusable, non-compensable delay per 108.06.B. On Projects that have activities delayed due to conflicts where the contractor failed to meet the notification requirements, the delays Shall not be considered excusable or compensable.

Attendance at Department ordered traffic coordination meetings between adjacent projects shall be considered mandatory for each project’s superintendent and Worksite Traffic Supervisor (WTS)*, and incidental to the Lump Sum Maintenance of Traffic payment item 614.

*IF REQUIRED BY THE PROJECT

tHE CONTRACTOR SHALL NOT DETOUR ANY TRAFFIC BETWEEN JUNE 10 – JULY 31 FOR TWO 7-CONSECUTIVE DAY PERIODS DURING WHICH PROJECT MRW-229/529-4.00/0.00 SHALL HAVE THEIR DETOUR IN PLACE UTILIZING SR-529. THE CONTRACTOR SHALL COORDINATE WITH PROJECT ENGINEER: dONALD STOVER, 740-513-9246.

ACCESS TO PRIVATE PROPERTY

ACCESS TO DRIVES SHALL BE MAINTAINED VIA EXISTING PAVEMENT, TEMPORARY PAVEMENT OR ITEM 304. In the event that a drive cannot be maintained and a closure is needed the contractor will coordinate with the property owner to minimize the impact to the owner.

COMMERCIAL PROPERTY WITH MULTIPLE DRIVES MAY HAVE ONE DRIVE CLOSED WHEN WORKING IN THE AREA OF THE DRIVE. COMMERCIAL PROPERTY WITH ONLY ONE DRIVEWAY OR DRIVEWAYS WITH ONE DIRECTION traffic USE WILL BE CONSTRUCTED PART WIDTH. the contractor will coordinate with the property owner to minimize the impact to the owner.

ACCESS TO PRIVATE PROPERTY (CONT’D):

MAINTAIN ACCESS TO RESIDENTIAL PROPERTIES AT ALL TIMES. WHEN A RESIDENTIAL DRIVE IS CLOSED FOR CONSTRUCTION, MAINTAIN ALTERNATE ACCESS TO THE PROPERTY. IT MAY BE REQUIRED FOR THE CONTRACTOR TO MAINTAIN ONE PASSABLE LANE WITHIN A CLOSURE IN ORDER FOR VEHICLES TO ACCESS RESIDENCY WITH A VEHICLE.

Unless called out in the plans the CONTRACTOR will COORDINATED any closures with PROPERTY OWNERS and be responsible for any and all property use agreements for alternative access.

SUCCESSFULLY NOTIFY THE OCCUPANTS/OWNERS OF COMMERCIAL OR RESIDENTIAL DRIVES TO BE CLOSED AND COORDINATE THE CLOSURE AT LEAST 48 HOURS BEFORE THE CLOSURE BEGINS (SIMPLY LEAVING A WRITTEN NOTICE OR PHONE MESSAGE IS NOT SUFFICIENT). COORDINATE ALTERNATE ACCESS TO RESIDENTIAL PROPERTIES WITH THE OWNER/OCCUPANT.

CLOSURE COORDINATION WITH SCHOOLS:

THE CONTRACTOR SHALL BE RESPONSIBLE FOR COORDINATING CLOSURES WITH SCHOOLS.