## Project 1
Survey Progress Checklist |  |  | RW Project? N | Survey Deliverables Due: 12-15-2023
CRS: | PAU-637-12.26 |  | PID: | 119864 | Coord Sys: PAU OCCS
Completed | Project Details | Completed By | Date Completed | Notes/Comments | other
a | OWNER ADDRESS LIST
a | ODOT Parcel Number Map created | RD | 2023-09-19
a | Owner List compiled | RD | 2023-09-19
a | PM contacted & Letter Sent | RD | 2023-09-25
a | COORD SYSTEM, SEED FILES TEMPLATES & DESIGN FILES |  |  | REMEMBER: Seed files may need generated FOR EACH COUNTY if the project has locations in different counties.
a | DTY file replaced | N/A | N/A
a | Seed Files corrected & desc/comments updated | RD | 2023-09-21 | VBA has been changed to true in FB and BR
a | Templates copied to Reports Folder: ie. Survey Progress Tracker, Survey Parameters, Mon Tables, Survey Certs, Surveyor's Project Notes, RW staking complete report (RW only projects), etc. | RD | 2023-09-19 | Mon Tables / Cervey Certs have not been copied over
a | Initial design files created (FB, BR, BK) & desc/comments updated **Follow naming conventions for single and multi-site PIDs | RD | 2023-09-21 | List Files created: (119864_FB001, 119864_BK001, & 119864_BR001)
a | RESEARCH (Hard copy & .pdf) |  |  | ALL RESEARCH NEEDS SAVED INTO THE PROJECT DIRECTORY AT THE BEGINNING OF THE PROJECT (ie. Deeds, reference surveys,plans,emails etc. need to have digital copies available in project directory. Scan items not obtained electronically )
a | Auditor/GIS
a | Property Cards | RD | 2023-09-19
a | Tax Map | RD | 2023-09-20
Engineer/GIS
a | Surveys | RD | 2023-09-20
a | Road Records | not available | on website
a | RW widths on County Rd/Twp Rd | not available | on website
a | Section corner/Stone Records | RD | 2023-09-20
Recorder
a | Deeds | RD | 2023-09-21 | **Could not find deed for parcel 12. I put 3 mortgages in PW which show legal. I just said it was NOT FOUND.
Easements (Lisa-RW)(Survey Non-RW)
Health Dept- septic/water well info
a | DNR - well and gas well logs | RD | 2023-09-27 | ODNR Water Wells (ohiodnr.gov) https://gis.ohiodnr.gov/MapViewer/?config=oilgaswells
a | Sanborn Maps | N/A | N/A | About this Collection ¦ Sanborn Maps ¦ Digital Collections ¦ Library of Congress (loc.gov)
Existing R/W and Construction Plans
a | OHROW (Statewide RW Plans & Mon) | RD | 2023-09-20 | ArcGIS Web Application (state.oh.us)
a | Plan Vault (Statewide Const.) | N/A | N/A | ArcGIS Web Application (state.oh.us) **There were plans, but not relavent
a | D1 Plan Vault (Const.) | RD | 2023-09-20
a | D1 RW Plan Vault | RD | 2023-09-20
Old ODOT Surveys and Field Notes
a | Survey Archives(scanned field notes 1950's-present) | RD | 2023-09-20 | \\d01fs2\Survey_Notes \\d01fs2\Survey_Notes\Stones
a | S:Field (old project .dgns ect. | RD | 2023-09-20 | ..\_Field
Atrium Cabinets
a | RR val maps(some scanned-see link) | N/A | N/A | ..\_RAILROADS
a | Canal Maps | N/A | N/A
a | Random County RW take plans | RD | Did NOT find
a | Color coded RW width maps(top right) and RW printout | RD | 2023-09-27 | ..\_RW BINDER SCAN JAN 2021_ AND ROAD RW INFO
a | Field Books and Index (Circa 1920's-1950's) | RD | Did NOT find | ..\_SURVEY FIELD BOOKS
a | R/W Width Binder | RD | 2023-09-27 | ..\_RW BINDER SCAN JAN 2021_ AND ROAD RW INFO
a | UTILITIES FOR SURVEY |  |  | ALL UTILITY INFO NEEDS SAVED INTO THE PROJECT DIRECTORY (ie. save emails, Newton and any utility plans to project directory) REMEMBER LINKS EXPIRE-COPY MAPS, PICTURES, NEWTON AS PDF!!!
a | OUPS-Plans ordered | GD | 2023-10-23
a | OUPS-Field markings ordered | GD | 2023-10-23 | No Utilities run through project site
a | NEWTON PDF saved to project folder | N/A | N/A
a | OUPS-Field markings collected | N/A | N/A
a | FIELD WORK
a | HORZ CONTROL - 3 CP's minimum
a | Set | RD/GD | 2023-11-06
a | Collected | RD/GD | 2023-11-06
a | BENCHMARKS
a | Set | RD/GD | 2023-11-06
a | Leveled | RD/GD | 2023-11-06
a | CENTERLINE & BOUNDARY MONS
a | recovered | RD/GD | 2023-11-06
a | collected | RD/GD | 2023-11-06
a | UTILITIES
a | OUPS markings | N/a | N/A
a | Observed evidence | N/A | N/A
a | GENERAL TOPO ITEMS
a | General Topo and features | RD/GD/DE | 11/6/23 - 11/7/23
a | BRIDGE TOPO ITEMS
a | Conventional and Scan completed | N/A | N/A
DESIGN FILES
| FB- Ex. Topo 3D |  |  | ONLY TOPO (SV), BM AND CP POINTS DOWNLOADED TO THIS DESIGN FILE. Remember multiple FB.dgns may need created if a multi-site PID Make sure to add a DESCRIPTION for the .dgn (Ie. "EX. Topo Survey C-R-S" or "EX Topo Survey and EX. Bridge Survey C-R-S"
REMEMBER: 1) Field pics need downloaded with CSV's to "Images/Field" folder(turn on icon decorator to see pic locations) 2) Do Utilites/Redraw to write SV Name,SV Elev and SV Description levels 3) Do Annotate Elements to wiite attributes to SV_Text level SEE LOGANS "HOW TO" for these steps.
Field Book folders to create:
a | C-R-S EX Topo (contains all existing ground topo items) (ie ALL-65-1.34 EX Topo) | RD | 2023-09-21
a | C-R-S EX Brdge (contains all Ex. Bridge Deck items) (ie ALL-65-1.34 EX Bridge) | RD | 2023-09-21
a | C-R-S EX Drainage (contains all Ex. Drainageitems) (ie ALL-65-1.34 EX Drainage) | RD | 2023-09-21
a | Terrain model created | GD | 2023-11-20
a | .XML of FINAL terrain created(name should match the terrain as named in the .dgn) | GD | 2023-11-20
a | Ex. CB'S/piping shown/labeled (unless in BD) | GD
a | Benchmarks-(downloaded, labeled and described) | GD
a | Control Points-(downloaded, ELEV UPDATED TO LEVELED ELEV, labeled and described) | GD
a | OHWM | N/A | N/A
a | UG & OH Utilities shown-line directions corrected | N/A | N/A
Project Specific notes (warnings, misc items etc (make notes on DEFAULT LEVEL)
Survey Parameters/RW/Bearing-Base/Utility Word Document edited
a | .PDF's prepared for field check | GD | 2023-11-21
| BK- Ex. Centerlines 2D |  |  | Create a different BK for each centerline needed unless they do not intersect. Make sure to add a DESCRIPTION for the .dgn (ie. Ex. CL RW SR 114 by Survey (LB), Ex. CL RW TR 55 by Survey (SM) No points set in or downloaded to this design file. No preliminary cl scratch items doen in this .dgn (do calcs in BR)
a | Centerline SR637 created | RD | 2023-11-09 | add BK file name here
a | Centerline SR/TR/CR/xxx created | N/A | N/A | add BK file name here
a | blank for additonal CL's | N/A | N/A | add BK file name here
a | blank for additonal CL's | N/A | N/A | add BK file name here
a | blank for additonal CL's | N/A | N/A | add BK file name here
a | blank for additonal CL's | N/A | N/A | add BK file name here
a | .PDF of each FINAL c/l alignment created (.pdf name should match exactly to the cl name in the .dgn | RD | 2023-11-14
a | .XML of each FINAL c/l alignment created (.xml name should match exactly to the cl name in the .dgn | RD | 2023-11-14
a | .PDF of each STA/OFFSET Reports | RD | 2023-11-24 | ie. Project contol/BM offsets to C/L; Ex. Mons. and R/W Mons. to C/L etc.
a | BR- Ex. R/W and Property lines2D |  |  | ALL Survey Monuments(MN) get download to this design file (except CP and BM points). Make sure to add a DESCRIPTION for the .dgn (ie. Ex. RW limits of SR 114 by survey (SM))
a | Field Book folders to Create:
a | C-R-S Ex. Monuments (contains all existing boundary/cl/rw related monuments as collected in the field) | RD | 2023-09-21
a | C-R-S Ex. R/W & CL (contains RX & CLX & PX points) | RD | 2023-09-21
a | C-R-S PROPOSED R/W & CL (contains RP & CLP points) (only pertains to projects with new RW needed)(This fb folder is created in the BR001/101/201 etc. by survey at points set by referencing in the proposed RW file (ie BR001/102/202 etc)???? We Need to further discuss how this process will go | N/A | N/A |  | 1900-01-22
a | C-R-S SEARCH POINTS (create when needed) | RD | 2022-09-21
a | C-R-S AS-SET (only pertains to projects with new RW needed)(created for record as-staked location of RW pins that were set) | N/A | N/A
a | Ex. R/W depicted | RD | 2023-11-20
a | Ex. Property lines Calculated/Depicted | RD | 2023-11-13
a | ODOT Parcel Number Map created | RD | 2023-09-19
a | Ownership/TP/Acres labeled | RD | 2023-09-25 | **Parcel 12 needs deed book, page added. Haven't found deed
a | Sec/Twp-Range/Township/County labeled | RD | 2023-09-25
a | Section Corners & other critical monuments described/labeled | RD | 2023-11-13
a | Corporation Limits Shown | N/A | N/A
a | BD- Ex. Drainage- for large projects/Modeling | N/A | N/A
a | CBs and Pipes modeled/drawn | N/A | N/A
a | BE, .tin and .gpk (SS4/10 only) | N/A | N/A
TYPICAL LEVELS TO USE: Notes that need to be seen=Default ; Ref. Surveys and Deed Descriptions=Scratch 10 ; Rough Property line Calcs/notes = Scratch 5 ; Rough Centerline Calcs/notes= Scratch 3
SURVEY DELIVERABLE REMINDER CHECKLIST REVIEWED
PROJECT EMAILED TO SOM FOR FIELD CHECK/REVIEW
PROJECT FIELD CHECK/REVIEW COMPLETE
SURVEY DELIVERABLES EMAILED TO PROJECT ENGINEER
POINTS SAVED TO MONUMENT DATABASE
SURVEY DELIVERABLES SAVED TO S:DRIVE
R/W MONUMENTED (Only for projects with R/W)
PAPER FILE SCANNED TO SURVEY ARCHIVE
type lower case "a" to produce checkmark
ver 6-6-2023
LEGAL DESCRIPTIONS (ONLY FOR RW PROJECTS)
Legal description & closure folders created under 300/Survey/Office Data
Preliminary Legals created
Legals reviewed by ODOT
Legals submitted for County Review
Legals approved by County
Final legals completed
signed/sealed and scanned
Combined .pdf copied to Real Estate Folder
ADDITIONAL SURVEY/PROJECT NOTES: