## Utility Log
O.U.P.S 1-800-362-2764 |  | COMPANY ID: 66732 |  |  |  | PROJECT: LEXINGTON |  | PID: 117965 | N/A |  |  | Last Updated By: RNK | Last Updated On: 9/21/2023
PM: NATE LANG, P.E. |  | OUPS TICKET (5/3/219): A31990892-00A, A31990892-01A, A3199089500A, A31990895-01A | [10 empty] | Project Limits: . | STARTING AT THE 7 ELEVEN ON US 42, GO 1350 FEET EAST TO THE FAR SIDE OF CASTOR ROAD. 50 FEET OFF EACH SIDE OF THE PAVEMENT
Utility Company | Telephone | Contact | Project Notification Notice (Emailed by ODOT or Consultant) | OUPS Request Utility Plans | Received Utility Plans or Positive Response | Sent Stage 1 Plans | Received Comments | Sent Stage 2 Plans | Received Comments | Sent Stage 3 Plans | Received Comments | FINAL TRACINGS SENT | Received Comments | Remarks | UG or OH
Name and Address | No. | Name
AEP - OHIO |  |  |  | 2023-07-18 | 2023-08-01 |  |  |  |  | 2025-02-10 | 2025-02-12 |  |  | PDFs Provided: Power Line Map - A319900895 Clarke Saunders: No conflicts, no UG within the construction area. | UG
700 MORRISON RD | 614.883.6802 | BRENT GATES
GAHANNA, OH 43230 |  | bmgates@aep.com
614.552.1801
BRIGHTSPEED |  |  |  | 2023-07-18 | 2023-08-01 |  |  |  |  | 2025-02-10 |  |  |  | Excavation Sight Clear Project coordination assigned to Anthony Williams. Map received showing location of facilities. Though no reponse was received, no potential conflicts are anticipated based on the facilities map. | UG
1120 SOUTH TYRON STREET, SUITE 700 | 918.282.3457 | Anthony Williams
CHARLOTTE, NC 28203 |  | anthony.williams1@brightspeed.com
Nate Klaiber
COLUMBIA GAS |  |  |  | 2023-07-18 | 2023-07-19 |  |  |  |  | 2025-02-10 | 2025-02-11 |  |  | PDFs Provided: Gas Line Map - A319900895 Nate Klaiber: No conflicts. Onging project on Mill Street, expected to be completed end of Feb 2025 | UG
1021 NORTH MAIN STREET | 419.348.9110 | MR. MITCHELL SWEETING
MANSFIELD, OHIO 44903 |  | msweeting@NiSource.com
419.348.9110 | 419.631.4468 | MR. TYLER HEMINGER
theminger@NiSource.com
MR. NATE KLAIBER
Nklaiber@nisource.com
also include:

## Utility Address
Title | First Name | Last Name | Title | Company | Address 1 | Address 2 | City | State | Zip
Mr.
Ms.
Mr.
Mr.
Mr.
Mr.
Mr.
Mr.
Please send a copy of the plans when we are closer to completion, ok to put mail box in driveway if maintained during winter

## Pending
Mountview Road
Utility Crossing / Conflict Locations
Assumed Utility Depths (if less than 18" of separation or utility required clearance violation MUST verify with utility or relocation must occur!
Depths are based upon project experience within D6. | [8 empty] | UTILITY TYPE KEY: | Utility
Water |  |  | 4' |  |  |  | 2019-09-26 |  | T | Telephone
Sanitary Sewer |  |  | N/A -Actual | [5 empty] | C | Cable
Storm Sewer |  |  | N/A-Actual | [5 empty] | FO | Fiber Optic
Telephone, Cable |  |  | 2.5' | [5 empty] | FODB | Fiber Optic Duct Bank
Fiber Optic, Electrical |  |  | 3' | [5 empty] | E | Electric
GAS |  |  | 3' | [5 empty] | EDB | Electric Duct Bank
GAS PIPELINE |  |  | 4' | [5 empty] | ST | Storm
[9 empty] | SA | Sanitary
[9 empty] | W | Water
[9 empty] | G | Gas
[9 empty] | GHP | Gas High Pressure
[9 empty] | GPL | Gas Pipeline
[9 empty] | L OR ITS | ODOT OWNED
Ref. No. | Sheet No. | Starting Station | Offset & (RT or LT) | Ending Station | Offset & (RT or LT) | Length | Conflict Location Description | Possible Conflict with what? | # of inches of separation between Existing Utility and proposed work | Is the utility within their own easement? (Y OR N) | Utility Type- (See Key Above for Reference) | If Electric - What is Voltage of line? | Utility Owner | Conflict Resolution | Resolved by what date | Utility Clear Date (sale - 60)
WATER (W- _)
STORM SEWER (ST- _)
TELEPHONE/CABLE/FIBER OPTIC (T-C-FO-FODB)
ELECTRIC (E- _, EDB- _)
GAS (G- _, GHP- _, GPL-_)