## E 9TH
Revision Date:
2010-04-12
EAST 9TH STREET
The facilities tabulated below are located inside the proposed E 9th Street ROW. Construction of the new roadway may impact these facilities.
Roadway from Canal Road to Commercial Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowable? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
4” Gas | Active | Across | 11 + 32 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
8” Gas | Active | Across | 11 + 33 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
12" Combined Sewer | Active | Parallel | SOUTH | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
24" Combined Sewer | Active | Across | 11 + 62 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
6” Water | Active | Across | 11 + 65 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Communications | Active | Across | 11 + 67 | ATT | PRIVATE | City | City | MAYBE | NO | HIGH | YES | ATT |  |  |  |  | 34
6” Water | Active | Across | 11 + 98 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
24" Combined Sewer | Active | Across | 12 + 11 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
Communications | Active | Across | 12 + 15 | ATT | PRIVATE | City | City | YES | NO | HIGH | YES | ATT |  |  |  |  | 67
Unidentified Facility | Active | Across | 12 + 15 | UNKNOWN | PRIVATE | City | City | YES | NO | HIGH | YES | UNKNOWN
8" Gas | Active | Across | 12 + 38 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG
6” Gas | Active | Across | 12 + 40 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG
Roadway from Commercial Road to GCRTA Crossing
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowable? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
12" Water | Active | Across | 16 + 34 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
?" Combined Sewer | Active | Across | 16 + XX | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT
Electric conduit | Active | Across | 16 + 48 | CEI | PRIVATE | City | City | YES | NO | HIGH | YES | CEI
Communications | Abandoned | Across | 19 + 83 | SPRINT | PRIVATE | Private | City | YES | NO | NEUTRAL | YES | SPRINT |  |  |  |  | 34
8” Water | Active | Across | 22 + 04 | CWD | PUBLIC | Private | City | YES | CONTRACT | NEUTRAL | YES | DBT
GCRTA Crossing (to Broadway Avenue)*
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowable? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Communications | Active | Across | 24 + 56 | VERIZON | PRIVATE | Easement | Easement | NO | YES | HIGH | YES | VERIZON |  |  |  |  | 34
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
*Railroad drainage, signal, communication and cantenary facilities are located within the GCRTA corridor.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## COMMERCIAL
Revision Date:
2010-04-12
COMMERCIAL ROAD
The facilities tabulated below are located inside the proposed Commercial Road ROW.
Roadway from E 9th Street to Existing Commercial Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowable? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
8" Gas*** | Active | Across |  | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
6” Gas*** | Active | Across |  | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
Unidentified Facility*** | Active | Across |  | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN
Communications*** | Active | Parallel | East | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
Horizon Tunnel** | Active | Across | 13 + 50 | CEI | PRIVATE | Easement | Easement | NO | YES | HIGH | NO | NOT ALLOW
12” Water | Active | Parallel | West | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
24" Combined Sewer | Active | Parallel | CL | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Communications*** | Active | Parallel |  | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
Unidentified Facility*** | Active | Parallel |  | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN
8" Gas*** | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
6” Gas*** | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
Roadway from Proposed Commercial Road to Central Viaduct Way
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowable? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
12" Water*** | Active | Parallel | South/West | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Electric conduit | Active | Parallel | North | CPP | PUBLIC | City | City | NO | YES | HIGH | NO | NOT ALLOW
128 KV Conductor** | Active | Parallel | North | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW
128 KV Conductor** | Active | Parallel | North | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW
36" Combined Sewer*** | Active | Parallel | CL | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
8" Gas*** | Active | Parallel | North/East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
6" Gas*** | Active | Parallel | North/East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
Communications*** | Active | Parallel | CL | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
Unidentified Facility** | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
* Utility facilities located under existing Minkon Street.
** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road. This facility may not be relocated or impacted in any way. Load constraints are defined in existing easement documents.
*** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## CENTRAL VIADUCT WAY
Revision Date:
2010-04-12
CENTRAL VIADUCT WAY
The facilities tabulated below are located inside the proposed Central Viaduct Way ROW.
Commercial Road to Carnegie Avenue***
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowable? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Electric conduit* | Active | Parallel | West | CPP | PUBLIC | City | City | MAYBE | YES | NEUTRAL | YES | UNKNOWN
Communications* | Active | Parallel | West | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
Communications* | Active | Parallel | West | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
18" Combined Sewer* | Active | Parallel | West | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
12” Water* | Active | CL |  | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
8" Gas* | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
6” Gas* | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
Electric conduit* | Active | Parallel | East | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI
Electric conduit* | Active | Parallel | East | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI
128 KV Conductor** | Active | Parallel | East | CEI | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
128 KV Conductor** | Active | Parallel | East | CEI | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
Communications* | Active | Parallel | East | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
Unidentified Facility* | Active | Across | 104 + 75 | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN
Unidentified Facility* | Active | Across | 104 + 75 | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN
Communications* | Active | Across | 105 + 50 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
*Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road.
** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road. This facility may not be relocated or impacted in any way. Load constraints are defined in existing easement documents.
***Most of the above facilities are also present at the intersection with Carnegie Avenue.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## E 14TH
Revision Date:
2010-04-12
EAST 14TH STREET
The facilities tabulated below are located inside the proposed E 14th Street ROW.
Broadway Avenue to Orange Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowable? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
2" Communications* | Active | Across | 10 + 80 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
12" Water* | Active | Across | 11 + 25 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Communications* | Active | Across | 11 + 30 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
Communications* | Active | Across | 11 + 35 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
8" Water* | Active | Across | 11 + 40 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
24" Combined Sewer* | Active | Across | 11 + 50 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
8” Gas* | Active | Across | 11 + 95 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
8" Water** | Active | Parallel | East | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
2" Communications** | Active | Parallel | East | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
8” Gas** | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
8" Water** | Active | Across | 13 + 60 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
8” Gas** | Active | Across | 13 + 85 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
Communications** | Active | Across | 13 + 95 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
Unidentified Facility*** | Active | Across | 14 + 05 | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN
24" Combined Sewer*** | Active | Across | 14 + 25 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Electric*** | Active | Across | 14 + 25 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI
20" Gas*** | Active | Across | 14 + 40 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
* Utility facilities located under existing Broadway Avenue. AT&T conduit banks under existing Broadway Avenue cannot be relocated.
** Utility facilities located under existing E 14th Street. AT&T conduit banks under existing Broadway Avenue cannot be relocated.
*** Utility facilities located under existing Orange Avenue.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## BROADWAY
Revision Date:
2010-04-12
BROADWAY AVENUE
The facilities tabulated below are located inside the proposed Broadway Avenue ROW.
Roadway from E 9th Street to E 14th Street
No immediately identified potential conflicts.
Roadway from E 14th Street to existing Broadway Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowable? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
2" Communications* | Active | Across | 15 + 00 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
12" Water* | Active | Across | 15 + 00 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Communications* | Active | Across | 15 + 00 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
Communications* | Active | Parallel | North | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
Communications* | Active | Parallel | North | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
12" Water* | Active | Parallel | North | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
Electric* | Active | Parallel | North | CPP | PUBLIC | City | City | MAYBE | YES | NEUTRAL | YES | UNKNOWN
Combined Sewer* | Active | Parallel | North | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
8" Water* | Active | Parallel | South | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
2" Communications* | Active | Parallel | South | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW
Unidentified Facility* | Active | Parallel | South | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
* Utility facilities located under existing Broadway Avenue. AT&T conduit banks under existing Broadway Avenue cannot be relocated.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## BROADWAY WALL
Revision Date:
2010-04-12
BROADWAY AVENUE RETAINING WALL
Facility Crossing under Proposed Wall
No immediately identified underground utility conflicts, however, potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.

## DRIVES
Revision Date:
2010-04-12
COMMERCIAL ROAD HILL DRIVEWAYS
The facilities tabulated below are located inside existing ROW as indicated in the notes.
Drive "A"
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowable? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Electric* | Active | Across | 51 + 50 | CEI | PRIVATE | Private | Private | MAYBE | YES | NEUTRAL | YES | CEI
Combined Sewer* | Active | Across | 51 + 50 | CWPC | PUBLIC | Private | Private | MAYBE | YES | NEUTRAL | YES | DBT
Drive "B"
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowable? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
6" Gas** | Active | Across | 41 + 60 | DEOG | PRIVATE | City | Private | MAYBE | NO | NEUTRAL | YES | DEOG
8" Gas** | Active | Across | 41 + 60 | DEOG | PRIVATE | City | Private | MAYBE | NO | NEUTRAL | YES | DEOG
Drive "C"
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowable? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Combined Sewer* | Active | Across | 60 + 25 | CWPC | PUBLIC | City | City | MAYBE | YES | NEUTRAL | YES | DBT
12" Water* | Active | Across | 60 + 25 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT
6" Gas** | Active | Across | 60 + 25 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
8" Gas** | Active | Across | 60 + 25 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
Drive "D"
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowable? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
8" Water | Active | Across | 70 + 90 | CWD | PUBLIC | Private | Private | YES | CONTRACT | HIGH | YES | DBT
Communications | Active | Across | 71 + 00 | VERIZON | PRIVATE | Private | Private | YES | YES | HIGH | YES | VERIZON
Communications | Active | Across | 71 + 90 | VERIZON | PRIVATE | Private | Private | YES | YES | HIGH | YES | VERIZON
Drive "E"
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowable? | Relocated By | Timing | Start Date | Duration (mo.) | End Date
Communications*** | Active | Across | 80 + 00 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ADELPHIA
128 KV Conductor** | Active | Across | 80 + 00 | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW
128 KV Conductor** | Active | Across | 80 + 25 | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW
Electric conduit | Active | Across | 80 + 30 | CPP | PUBLIC | City | City | MAYBE | YES | NEUTRAL | YES | UNKNOWN
8" Gas*** | Active | Across | 80 + 50 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG
6" Gas*** | Active | Across | 80 + 50 | DEOG | PRIVATE | City | City | MAYBE | YES | NEUTRAL | YES | DEOG
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
* Utility facilities located under existing Minkon Street.
** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road. This facility may not be relocated or impacted in any way. Load constraints are defined in existing easement documents.
Blank spaces under "Relocation Information" in the matrix indicates information to be determined by the DBT.

## LISTS
Location | Utility | Schedule | Duration | Property |  |  | Status
North | ATT | Advance | 0 months | ODOT | YES | HIGH | Active
South | DEOG | DB Contract | 3 months | City | NO | LOW | Abandoned
East | CEI | Unknown | 6 months | Private | MAYBE | NEUTRAL
West | CWD | Not Required | 9 months | Easement | CONTRACT
CL | NEORSD |  | 12 months |  | ABANDON
Across | ODOT |  | 15 months
Parallel | UNKNOWN |  | 18 months
| DBT |  | 21 months
| NOT REQ'D |  | 24 months
CPP
ADELPHIA
DOMINION
MCI
CWPC
DOMTEL
VERIZON
SPRINT
NOT ALLOW
The facilities tabulated below are located inside the proposed Commercial Road ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Central Viaduct Way ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed E 14th Street ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Broadway Avenue ROW. Construction of the new roadway may or may not impact these facilities.