## E 9TH
Revision Date:
2009-11-23
EAST 9TH STREET
The facilities tabulated below are located inside the proposed E 9th Street ROW. Construction of the new roadway may impact these facilities.
Roadway from Canal Road to Commercial Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
4” Gas | Active | Across | 11 + 32 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
8” Gas | Active | Across | 11 + 33 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
12" Combined Sewer | Active | Parallel | SOUTH | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
24" Combined Sewer | Active | Across | 11 + 62 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
6” Water | Active | Across | 11 + 65 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 11 + 67 | ATT | PRIVATE | City | City | MAYBE | NO | HIGH | YES | ATT | Unknown | 0 months | 2010-01-01 | 34
6” Water | Active | Across | 11 + 98 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
24" Combined Sewer | Active | Across | 12 + 11 | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 12 + 15 | ATT | PRIVATE | City | City | YES | NO | HIGH | YES | ATT | Unknown | 0 months | 2010-01-01 | 67
Unidentified Facility | Active | Across | 12 + 15 | UNKNOWN | PRIVATE | City | City | YES | NO | HIGH | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
8" Gas | Active | Across | 12 + 38 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
6” Gas | Active | Across | 12 + 40 | DEOG | PRIVATE | City | City | YES | NO | HIGH | YES | DEOG | Unknown | 0 months | 2010-01-01
Roadway from Commercial Road to GCRTA Crossing
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
12" Water | Active | Across | 16 + 34 | CWD | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
?" Combined Sewer | Active | Across | 16 + XX | CWPC | PUBLIC | City | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 16 + 48 | CEI | PRIVATE | City | City | YES | NO | HIGH | YES | CEI | Unknown | 0 months | 2010-01-01
Communications | Abandoned | Across | 19 + 83 | SPRINT | PRIVATE | Private | City | YES | NO | NEUTRAL | YES | SPRINT | Unknown | 0 months | 2010-01-01 | 34
8” Water | Active | Across | 22 + 04 | CWD | PUBLIC | Private | City | YES | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
GCRTA Crossing (to Broadway Avenue)*
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Communications | Active | Across | 24 + 56 | VERIZON | PRIVATE | Easement | Easement | NO | YES | HIGH | YES | VERIZON | Unknown | 0 months | 2010-01-01 | 34
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
*Railroad drainage, signal, communication and cantenary facilities are located within the GCRTA corridor.

## COMMERCIAL
Revision Date:
0
COMMERCIAL ROAD
The facilities tabulated below are located inside the proposed Commercial Road ROW.
Roadway from E 9th Street to Existing Commercial Road
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
8" Gas*** | Active | Across |  | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
6” Gas*** | Active | Across |  | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Unidentified Facility*** | Active | Across |  | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
Communications*** | Active | Parallel | East | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Horizon Tunnel** | Active | Across | 13 + 50 | CEI | PRIVATE | Easement | Easement | NO | YES | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
12” Water | Active | Parallel | West | CWD | PUBLIC | Private | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
24" Combined Sewer | Active | Parallel | CL | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Communications*** | Active | Parallel |  | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Unidentified Facility*** | Active | Parallel |  | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
8" Gas*** | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
6” Gas*** | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Roadway from Proposed Commercial Road to Central Viaduct Way
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
12" Water*** | Active | Parallel | South/West | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Parallel | North | CPP | PUBLIC | City | City | NO | YES | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
128 KV Conductor** | Active | Parallel | North | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
128 KV Conductor** | Active | Parallel | North | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
36" Combined Sewer*** | Active | Parallel | CL | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
8" Gas*** | Active | Parallel | North/East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
6" Gas*** | Active | Parallel | North/East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Communications*** | Active | Parallel | CL | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Unidentified Facility** | Active | Parallel | East | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
* Utility facilities located under existing Minkon Street.
** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road. This facility may not be relocated or impacted in any way. Load constraints are defined in existing easement documents.
*** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road.

## CENTRAL VIADUCT WAY
Revision Date:
2009-11-23
CENTRAL VIADUCT WAY
The facilities tabulated below are located inside the proposed Central Viaduct Way ROW.
Commercial Road to Carnegie Avenue***
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Electric conduit* | Active | Parallel | West | CPP | PUBLIC | City | City | MAYBE | YES | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
Communications* | Active | Parallel | West | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Communications* | Active | Parallel | West | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
18" Combined Sewer* | Active | Parallel | West | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
12” Water* | Active | CL |  | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
8" Gas* | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
6” Gas* | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Electric conduit* | Active | Parallel | East | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Electric conduit* | Active | Parallel | East | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
128 KV Conductor** | Active | Parallel | East | CEI | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
128 KV Conductor** | Active | Parallel | East | CEI | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
Communications* | Active | Parallel | East | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Unidentified Facility* | Active | Across | 104 + 75 | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
Unidentified Facility* | Active | Across | 104 + 75 | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
Communications* | Active | Across | 105 + 50 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ATT | Unknown | 0 months | 2010-01-01
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
*Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road.
** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road. This facility may not be relocated or impacted in any way. Load constraints are defined in existing easement documents.
***Most of the above facilities are also present at the intersection with Carnegie Avenue.

## E 14TH
Revision Date:
2009-11-23
EAST 14TH STREET
The facilities tabulated below are located inside the proposed E 14th Street ROW.
Broadway Avenue to Orange Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
2" Communications* | Active | Across | 10 + 80 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
12" Water* | Active | Across | 11 + 25 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Communications* | Active | Across | 11 + 30 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
Communications* | Active | Across | 11 + 35 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
8" Water* | Active | Across | 11 + 40 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
24" Combined Sewer* | Active | Across | 11 + 50 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
8” Gas* | Active | Across | 11 + 95 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
8" Water** | Active | Parallel | East | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
2" Communications** | Active | Parallel | East | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
8” Gas** | Active | Parallel | East | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
8" Water** | Active | Across | 13 + 60 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
8” Gas** | Active | Across | 13 + 85 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Communications** | Active | Across | 13 + 95 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
Unidentified Facility*** | Active | Across | 14 + 05 | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
24" Combined Sewer*** | Active | Across | 14 + 25 | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Electric*** | Active | Across | 14 + 25 | CEI | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
20" Gas*** | Active | Across | 14 + 40 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
* Utility facilities located under existing Broadway Avenue. AT&T conduit banks under existing Broadway Avenue cannot be relocated.
** Utility facilities located under existing E 14th Street. AT&T conduit banks under existing Broadway Avenue cannot be relocated.
*** Utility facilities located under existing Orange Avenue.

## BROADWAY
Revision Date:
2009-11-23
BROADWAY AVENUE
The facilities tabulated below are located inside the proposed Broadway Avenue ROW.
Roadway from E 9th Street to E 14th Street
No immediately identified potential conflicts.
Roadway from E 14th Street to existing Broadway Avenue
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
2" Communications* | Active | Across | 15 + 00 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
12" Water* | Active | Across | 15 + 00 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Communications* | Active | Across | 15 + 00 | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
Communications* | Active | Parallel | North | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
Communications* | Active | Parallel | North | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
12" Water* | Active | Parallel | North | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Electric* | Active | Parallel | North | CPP | PUBLIC | City | City | MAYBE | YES | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
Combined Sewer* | Active | Parallel | North | CWPC | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
8" Water* | Active | Parallel | South | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
2" Communications* | Active | Parallel | South | ATT | PRIVATE | City | City | NO | NO | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
Unidentified Facility* | Active | Parallel | South | UNKNOWN | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
* Utility facilities located under existing Broadway Avenue. AT&T conduit banks under existing Broadway Avenue cannot be relocated.

## BROADWAY WALL
Revision Date:
2009-11-23
BROADWAY AVENUE RETAINING WALL
Facility Crossing under Proposed Wall
No immediately identified underground utility conflicts, however, potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.

## DRIVES
Revision Date:
2009-11-23
COMMERCIAL ROAD HILL DRIVEWAYS
The facilities tabulated below are located inside existing ROW as indicated in the notes.
Drive "A"
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Electric* | Active | Across | 51 + 50 | CEI | PRIVATE | Private | Private | MAYBE | YES | NEUTRAL | YES | CEI | Unknown | 0 months | 2010-01-01
Combined Sewer* | Active | Across | 51 + 50 | CWPC | PUBLIC | Private | Private | MAYBE | YES | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
Drive "B"
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
6" Gas** | Active | Across | 41 + 60 | DEOG | PRIVATE | City | Private | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
8" Gas** | Active | Across | 41 + 60 | DEOG | PRIVATE | City | Private | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Drive "C"
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Combined Sewer* | Active | Across | 60 + 25 | CWPC | PUBLIC | City | City | MAYBE | YES | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
12" Water* | Active | Across | 60 + 25 | CWD | PUBLIC | City | City | MAYBE | CONTRACT | NEUTRAL | YES | DBT | Unknown | 0 months | 2010-01-01
6" Gas** | Active | Across | 60 + 25 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
8" Gas** | Active | Across | 60 + 25 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Drive "D"
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
8" Water | Active | Across | 70 + 90 | CWD | PUBLIC | Private | Private | YES | CONTRACT | HIGH | YES | DBT | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 71 + 00 | VERIZON | PRIVATE | Private | Private | YES | YES | HIGH | YES | VERIZON | Unknown | 0 months | 2010-01-01
Communications | Active | Across | 71 + 90 | VERIZON | PRIVATE | Private | Private | YES | YES | HIGH | YES | VERIZON | Unknown | 0 months | 2010-01-01
Drive "E"
Facility | Active Status | Location |  | Facility Ownership |  | Property Ownership |  | Facility Impacted | Compensable Status | Priority |  |  | Relocation Information
|  | Position | Station | Owner | Type | Existing | Proposed |  |  |  | Allowed? | Relocated By | Timing | Duration | Schedule
Communications*** | Active | Across | 80 + 00 | ATT | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | ADELPHIA | Unknown | 0 months | 2010-01-01
128 KV Conductor** | Active | Across | 80 + 00 | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
128 KV Conductor** | Active | Across | 80 + 25 | CEI | PRIVATE | City | City | NO | YES | HIGH | NO | NOT ALLOW | Unknown | 0 months | 2010-01-01
Electric conduit | Active | Across | 80 + 30 | CPP | PUBLIC | City | City | MAYBE | YES | NEUTRAL | YES | UNKNOWN | Unknown | 0 months | 2010-01-01
8" Gas*** | Active | Across | 80 + 50 | DEOG | PRIVATE | City | City | MAYBE | NO | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
6" Gas*** | Active | Across | 80 + 50 | DEOG | PRIVATE | City | City | MAYBE | YES | NEUTRAL | YES | DEOG | Unknown | 0 months | 2010-01-01
Other potential conflicts may include existing storm, sanitary and combined sewers; overhead power and lighting lines; utility service connections and other above and underground facilities.
* Utility facilities located under existing Minkon Street.
** Utility facilities located under existing Commercial Road. Facility position varies with actual location on Commercial Road. This facility may not be relocated or impacted in any way. Load constraints are defined in existing easement documents.

## LISTS
Location | Utility | Schedule | Duration | Property |  |  | Status
North | ATT | Advance | 0 months | ODOT | YES | HIGH | Active
South | DEOG | DB Contract | 3 months | City | NO | LOW | Abandoned
East | CEI | Unknown | 6 months | Private | MAYBE | NEUTRAL
West | CWD | Not Required | 9 months | Easement | CONTRACT
CL | NEORSD |  | 12 months |  | ABANDON
Across | ODOT |  | 15 months
Parallel | UNKNOWN |  | 18 months
| DBT |  | 21 months
| NOT REQ'D |  | 24 months
CPP
ADELPHIA
DOMINION
MCI
CWPC
DOMTEL
VERIZON
SPRINT
NOT ALLOW
The facilities tabulated below are located inside the proposed Commercial Road ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Central Viaduct Way ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed E 14th Street ROW. Construction of the new roadway may or may not impact these facilities.
The facilities tabulated below are located inside the proposed Broadway Avenue ROW. Construction of the new roadway may or may not impact these facilities.