## Slide 1: WOO-93592 Potential errors and omissions
Mike Benton, P.E. Project Engineer
David Geckle, P.E. District Bridge Engineer

## Slide 2: Luc-75-0029l structure details
Twelve span, multi-unit, prestressed concrete I-beam bridge with composite reinforced concrete deck on stub abutments and cap-and-column piers that carries I-75 Southbound over the Maumee River in Toledo, OH
  Total length = 1948.66’
  Roadway width = Varies (72’-0” Minimum)
  Loading = HL-93 with 60 PSF Future Wearing Surface

## Slide 3: Issue

## Slide 4: Dispute resolution
Proposal Note 108 – Dispute Resolution Board Process
  Advisory Recommendation Process (verbal recommendation)

## Slide 5: issue
Reinforcing steel dimensions for S5149 epoxy coated reinforcing steel did not allow for sufficient cover on inside face of exterior parapet.
Details from plan sheets 1424 & 1426 of 1792

## Slide 6: Plan dimensions
Detail from plan sheet 1428 of 1792

## Slide 7: Bridge design manual, 2007

## Slide 8: Reinforcing list for luc-75-0029l

## Slide 9: calculated clearance
Design does not meet 2” minimum concrete cover as required in BDM 301.5.7.

## Slide 10: Actual field clearance
Design does not meet 2” minimum concrete cover as required in BDM 301.5.7.

## Slide 11: Dispute resolution board
Advisory Recommendation
  Oral Opinion - Contractor has no responsibility for any costs associated with insufficient clearance

## Slide 12: correspondence
Email from AECOM on 6/6/23:
  “AECOM agrees, the bar should have been 18” tall, let us know what additional you need from us with the repair.”
Email from AECOM on 7/6/23:
  “AECOM maintains that we provided a buildable design with 1.25” cover over the bars in question.”

## Slide 13: Initial Repair recommendation from aecom

## Slide 14: subsequent Repair recommendation from aecom

## Slide 15: final accepted Repair recommendation

## Slide 16: Barrier condition (while performing repair work)

## Slide 17: Cost for repair
ODOT’s Cost to Complete Repair
  Epoxy-Urethane Sealer Removal/Prep - $13,400 (Estimated)
  Installation of Fiber Wrap - $141,882
  Re-application of Epoxy-Urethane Sealer - $10,110 (Estimated)
  Maintenance of Traffic - $57,000 (Estimated)
  Total (Estimated) - $222,392

## Slide 18: Questions