August 19, 2019

October 16 2019

Updated Schedule

MAH-170-4.35 PID 103854

Agreement No. 31105

1. **Schedule**

The following is the proposed schedule for Part 2/Modification #1 of the project.

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone** | **Date** | **District Cmts 5/30/2019** | **District Cmts 10-15-2019** |
| Stage 1 Plan submitted | 6/30/2019 |  |  |
| Begin scoping Part 2 | 6/3/2019 |  |  |
| Stage 1 Plans approved | 3/24/2020 |  |  |
| Environmental field studies – Ex ESA Phase 1 | Fall 2019 |  |  |
| Compliance & Preliminary ROW plans | 2/24/2020 |  |  |
| Approved Preliminary ROW plans | 3/24/2020 |  |  |
| 404/401 Permits Submitted to Agencies | 2/1/2020 |  |  |
| Environmental Document Approved | 4/1/2020 | FYI – no stage 3 work until enviro doc approved |  |
| Final R/W Plans Submitted | 7/24/2020 |  |  |
| Stage 2 Plans - Submitted | 7/24/2020 |  |  |
| Stage 2 Plans - Complete | 8/24/2020 |  |  |
| Final R/W Plans - Approved | 8/24/2020 |  |  |
| R/W Authorized | 7/17/2020 |  | Change to 9-24-2020 |
| Stage 3 Plans - Submitted | 1/8/2021 |  |  |
| Stage 3 Plans - Complete | 2/8/2021 |  |  |
| R/W Acquisition Complete | 12/17/2021 | Need to keep an eye on time frame for utility relocation | Change to 2-1-2022 |
| Final Tracings - Submitted | 12/1/2021 |  |  |
| Final Tracings - Approved | 2/1/2022 | Please make sure tracings are submitted 2 months before final tracings approved date | Change to 4-1-2022 |
| District R/W Certification | 6/17/2022 | Typically 2 weeks before plan package to C/O |  |
| Plan Package Received in C.O. | 7/2/2022 | Hold date shown in ellis |  |
| Sale | 10/1/2022 | Hold date shown in ellis |  |
| Award | 10/1/2022 | Hold date shown in ellis |  |
| Estimated Begin Construction | TBD | Discussing fall start, ellis date is April 2023 |  |
| Estimated End Construction | TBD | 2 seasons |  |

 \*Dependent on impacts discovered in Stage 1.