## 100% Review Disposition
FRA-161-15.80
Stage 3 Backcheck - 4th Review Comments
[6 empty] | RESPONSE LEGEND | [6 empty] | COLUMN F: RESPONSES FOR ACTION REQ'D
City of Columbus Project #: | [5 empty] | A: AGREE FULLY, revised per comment | [6 empty] | A: AGREE FULLY revised per comment.
[6 empty] | B: AGREE PARTLY, EXCEPTIONS NOTED | [6 empty] | B: AGREE PARTLY, EXCEPTIONS NOTED.
ODOT PID #: | 117607 |  |  |  |  | C: DISAGREE FULLY, REASONS NOTED | [6 empty] | C: DISAGREE FULLY. REASONS NOTED.
[6 empty] | D: COMMENT HAS BEEN SUPERSEDED BY DESIGN DEVELOPMENT | [6 empty] | D: COMMENT HAS BEEN SUPERSEDED BY DESIGN DEVELOPMENT.
Date: | Note to consultant: Comment completed and verified by Jeff Hackenbracht -6-06-2024 |  |  |  |  | E: QUESTION ONLY. ANSWER PROVIDED | [6 empty] | E: QUESTION ONLY. ANSWER PROVIDED.
[6 empty] | F: NO ACTION REQUIRED | [6 empty] | F: NO ACTION REQUIRED
NO. | SHEET NO | Color Code (Hide Column) | COLOR | COMMENTS | COMMENT BY | ACTION REQ'D A,B,C, D,E,F | QUESTIONS/RESPONSE TO CITY | NEEDS CLARIFICATION FROM CITY | CURRENT STATUS (OPEN/CLOSED) | VALIDATED? | FIELD VERIFICATION REQUIRED? | TABLES UPDATED IN CAD FILE? | OTHER NOTES
PLANS
1 | 58 | #00B4F3 | #N/A | Are these elevations correct? | dahill | E | Elevations were provided by SAM. Please refer to the utility note for the complete results of their investigation.
2 | 4 | #004080 | #N/A | There is no 100-year Floodplain line on this side. | rmvansickle | A | Complied.
3 | 4 | #004080 | #N/A | The Floodway line is the line I have marked blue. Please correct it. | rmvansickle | A | Complied.
4 | 49 | #004080 | #N/A | Repeat Comment. Just Floodway through here. | rmvansickle | A | Complied.
5 | 49 | #004080 | #N/A | Floodway isn't this line. It is the next line to the left. | rmvansickle | A | Complied.
6 | 49 | #004080 | #N/A | Repeat Comment. Only Floodway here. | rmvansickle | A | Complied.
7 | 49 | #004080 | #N/A | Only Floodway here. No 100-year Floodplain line here. | rmvansickle | A | Complied.
8 | 1 | #004080 | #N/A | Please see minor floodplain comments & questions on p. 4 & 49. Renee VanSickle, 5-29-2024. | rmvansickle | A | Complied.
9 | 58 | #00B4F3 | #N/A | The required 3'-0" minimum horizontal separation is not being met here. It is evident that you are centering the maximum sized panel over the existing 12" water main in an attempt to provide as much horizontal separation that the current alignment can provide. However you are only providing approximately 9"-11" of horizontal clearance (out-to-out), which is not sufficient. Please revisit your current design and alignment to meet this separation requirement. Please verify & revise accordingly. | dahill | A | Complied by revising the alignment to provide the required 3'-0" min horizontal separation.
Drainage Report
10 | 1 | #00FF00 | Bright Green | Sign and Seal |  | A | Complied

## ColorCodes
#00FF00 | Bright Green
#008000 | Green
#003300 | Dark Green
#800000 | Brown
#993366 | Violet
#800080 | Violet
#C0C0C0 | Gray
#FFFF00 | Yellow
#333300 | Brown
#FF9900 | Orange
#FFCC00 | Yellow
#666699 | Purple
#808000 | Olive
#FF6600 | Orange
#00CCFF | Light Blue
#FFCC99 | Peach
#993300 | Brown
#FFFF99 | Yellow
#99CC00 | Lime
#FF00FF | Pink
#FFFFFF | White
#999999 | Gray
#808080 | Gray
#008080 | Turquoise
#99CCFF | Light blue
#33CCCC | Light Blue
#3366FF | Blue
#003366 | Dark Blue
#CC99FF | Purple
#CCFFFF | Light Blue
#00FFFF | Light Blue
#FF99CC | Pink
#CCFFCC | Teal
#339966 | Green
#333333 | Dark Gray
#FF0000 | Red
#000000 | Black
#333399 | Purple
#000080 | Dark Blue
#0000FF | Blue
#45BFED | Light Blue
#44BFED | Light Blue
N/A