## 100% Review Disposition
FRA-161-15.80 Noise Walls
STAGE 2 - REVIEW COMMENTS
[6 empty] | RESPONSE LEGEND | [6 empty] | COLUMN F: RESPONSES FOR ACTION REQ'D
City of Columbus Project #: | 3973 E |  |  |  |  | A: AGREE FULLY, revised per comment | [6 empty] | A: AGREE FULLY revised per comment.
[6 empty] | B: AGREE PARTLY, EXCEPTIONS NOTED | [6 empty] | B: AGREE PARTLY, EXCEPTIONS NOTED.
ODOT PID #: | 117607 |  |  |  |  | C: DISAGREE FULLY, REASONS NOTED | [6 empty] | C: DISAGREE FULLY. REASONS NOTED.
[6 empty] | D: COMMENT HAS BEEN SUPERSEDED BY DESIGN DEVELOPMENT | [6 empty] | D: COMMENT HAS BEEN SUPERSEDED BY DESIGN DEVELOPMENT.
Date: | Note to consultant: Comment Responses checked by Jeff Hackenbracht on 3-27-2024 |  |  |  |  | E: QUESTION ONLY. ANSWER PROVIDED | [6 empty] | E: QUESTION ONLY. ANSWER PROVIDED.
[6 empty] | F: NO ACTION REQUIRED | [6 empty] | F: NO ACTION REQUIRED
NO. | SHEET NO | Color Code (Hide Column) | COLOR | COMMENTS | COMMENT BY | ACTION REQ'D A,B,C, D,E,F | QUESTIONS/RESPONSE TO CITY | NEEDS CLARIFICATION FROM CITY | CURRENT STATUS (OPEN/CLOSED) | VALIDATED? | FIELD VERIFICATION REQUIRED? | TABLES UPDATED IN CAD FILE? | OTHER NOTES
1 | 18 | #FFFF00 | #N/A | CIRCUIT 848, LEG C FUTURE EX. LIGHTING IN EX. CONDUIT | sawolfe | A: AGREE FULLY, revised per comment | JDH - Complied
2 | 18 | #FFFF00 | #N/A | T | sawolfe | F: NO ACTION REQUIRED
3 | 18 | #FFFF00 | #N/A | OF MEDIAN BARRIER REPLACED PER SCD HL-20.13) | sawolfe | A: AGREE FULLY, revised per comment | JDH - Complied
4 | 18 | #FFFF00 | #N/A | FUTURE EX. LIGHT POLE 848-C6 | sawolfe | F: NO ACTION REQUIRED
5 | 18 | #FFFF00 | #N/A |  | sawolfe
6 | 18 | #FFFF00 | Yellow |  | sawolfe
7 | 18 | #FFFF00 | Yellow |  | sawolfe
8 | 18 | #FF0000 | Red | COMMENT FOR ENTIRE PLAN. ANY LIGHTING (BE IT FUTRE EXISTING OR WHATEVER) THAT IS NOT BEING DISTURBED SHOULD HAVE A "DND" CALLOUT FOR CLARIFICATION OF DISPOSTION. ALL LOCATIONS AND CALLOUTS | sawolfe | A: AGREE FULLY, revised per comment | JDH - Complied
9 | 27 | #FF0000 | Red | THIS IS NOT AN OVERHEAD LINE SEE DETAIL FROM 161 PID 116322 | sawolfe | A: AGREE FULLY, revised per comment | JDH - Complied
10 | 27 | #FF0000 | Red |  | sawolfe
11 | 35 | #FF0000 | Red | LEG CALLOUT INCORRECT. REF PID 116322 FOR CORRECT CALLOUTS | sawolfe | A: AGREE FULLY, revised per comment | JDH - Complied
12 | 35 | #FFFF00 | Yellow | FUTURE EX. LIGHTING CIRCUIT 849, LEG C | sawolfe
13 | 35 | #FF0000 | Red |  | sawolfe
14 | 10 | #FF0000 | Red |  | sawolfe
15 | 10 | #FF0000 | Red | THESE ARE AVAILABLE ON THE INTERNET...PROVIDE ACTUAL ADDRESS | sawolfe | A: AGREE FULLY, revised per comment | JDH - Complied
16 | 1 | #FF0000 | Red |  | sawolfe
17 | 10 | #FF0000 | Red |  | klrhynehardt
18 | 10 | #FF0000 | Red | OK | klrhynehardt | F: NO ACTION REQUIRED
19 | 10 | #FF0000 | Red | https://www.columbus.gov/WorkArea/DownloadAsset.aspx?id=2147503200 | klrhynehardt | A: AGREE FULLY, revised per comment | JDH - Complied
20 | 10 | #FF0000 | Red | The actual address to the new MIS-01 is shown... | klrhynehardt | A: AGREE FULLY, revised per comment | JDH - Complied
21 | 1 | #FF0000 | Red |  | klrhynehardt
22 | 28 | #00B4F3 | #N/A | Please refer to comment made above. | dahill
23 | 226 | #00B4F3 | #N/A | Please show the Existing 16" Water Main & 30" Casing Pipe per the available Plan of Record. Also, please refer to the comments made on Sheet #28 and revise accordingly. | dahill | A: AGREE FULLY | JDH - Complied
24 | 42 | #00B4F3 | #N/A | We appear to have sufficient horizontal clearance here. However, please follow the horizontal separation requirements stated on sheet 28 to a assure proper separation is maintained. Please revise accordingly. | dahill | A: AGREE FULLY | JDH - ARCADIS RESPONSE: WE ARE WORKING WITH A SUE CONSULTANT NAMED "SAM" WHO IS IN THE PROCESS OF POTHOLING THIS WATER LINE. AS SOON AS WE GET THE EXACT LOCATION OF THE WATER LINE WE WILL REEVALUATE THE CLEARANCE AND PROVIDE THIS INFORMATION FOR YOUR FURTHER REVIEW AND COMMENT. PLEASE NOTE THAT WE WILL COMPLY WITH THE CLEARANCE REQUIREMENT, BUT WANT TO WAIT FOR THE POTHOLE INFORMATION TO MAKE SURE WE ARE MEETING YOUR POLICY.
25 | 28 | #00B4F3 | #N/A | Please provide a minimum of 3'-0" of Horizontal Separation (out-to-out) between the existing 30" casing pipe and any proposed 30" drilled shaft/foundation. You may fabricate a note to this requirement. Please revise accordingly. | dahill | A: AGREE FULLY | JDH - ARCADIS RESPONSE: WE ARE WORKING WITH A SUE CONSULTANT NAMED "SAM" WHO IS IN THE PROCESS OF POTHOLING THIS WATER LINE. AS SOON AS WE GET THE EXACT LOCATION OF THE WATER LINE WE WILL REEVALUATE THE CLEARANCE AND PROVIDE THIS INFORMATION FOR YOUR FURTHER REVIEW AND COMMENT. PLEASE NOTE THAT WE WILL COMPLY WITH THE CLEARANCE REQUIREMENT, BUT WANT TO WAIT FOR THE POTHOLE INFORMATION TO MAKE SURE WE ARE MEETING YOUR POLICY.
26 | 195 | #00B4F3 | #N/A | Please refer to comments made on Sheet 28 & 226 & revise if required. | dahill | A: AGREE FULLY | JDH - ARCADIS RESPONSE: WE ARE WORKING WITH A SUE CONSULTANT NAMED "SAM" WHO IS IN THE PROCESS OF POTHOLING THIS WATER LINE. AS SOON AS WE GET THE EXACT LOCATION OF THE WATER LINE WE WILL REEVALUATE THE CLEARANCE AND PROVIDE THIS INFORMATION FOR YOUR FURTHER REVIEW AND COMMENT. PLEASE NOTE THAT WE WILL COMPLY WITH THE CLEARANCE REQUIREMENT, BUT WANT TO WAIT FOR THE POTHOLE INFORMATION TO MAKE SURE WE ARE MEETING YOUR POLICY.
27 | 11 | #00B4F3 | #N/A | Please add the following note: A minimum of 3 feet of horizontal clearance (out to out) shall be maintained between all existing water mains and foundations for poles, pull boxes, push button pedestals, and any other miscellaneous electrical structure. | dahill | A: AGREE FULLY, revised per comment | JDH - Complied
28 | 1 | #FF0000 | Red |  | dahill
29 | 1 | #FFFF00 | Yellow |  | rmvansickle
30 | 1 | #FFFF00 | Yellow |  | rmvansickle
31 | 1 | #FFFF00 | Yellow |  | rmvansickle
32 | 1 | #FFFF00 | Yellow |  | rmvansickle
33 | 1 | #FFFF00 | Yellow |  | rmvansickle
34 | 3 | #FF80C0 | #N/A |  | rmvansickle
35 | 3 | #FF80C0 | #N/A |  | rmvansickle
36 | 3 | #FF80C0 | #N/A |  | rmvansickle
37 | 3 | #FF80C0 | #N/A |  | rmvansickle
38 | 3 | #FF80C0 | #N/A |  | rmvansickle
39 | 3 | #FF8040 | #N/A |  | rmvansickle
40 | 3 | #FF8040 | #N/A |  | rmvansickle
41 | 3 | #FF8040 | #N/A |  | rmvansickle
42 | 3 | #FF8040 | #N/A |  | rmvansickle
43 | 3 | #FF8040 | #N/A |  | rmvansickle
44 | 3 | #FF0000 | Red |  | rmvansickle
45 | 3 | #FF0000 | Red |  | rmvansickle
46 | 3 | #FF0000 | Red |  | rmvansickle
47 | 3 | #004080 | #N/A | No such thing as the 100-year Floodway. It is just Floodway. | rmvansickle | A: AGREE FULLY, revised per comment | JDH - Complied
48 | 3 | #FF0000 | Red |  | rmvansickle
49 | 3 | #80FFFF | #N/A | - | rmvansickle
50 | 3 | #80FFFF | #N/A | / | rmvansickle
51 | 3 | #80FFFF | #N/A | l | rmvansickle
52 | 3 | #80FFFF | #N/A | _ | rmvansickle
53 | 3 | #FF0000 | Red |  | rmvansickle
54 | 3 | #FF0000 | Red |  | rmvansickle
55 | 3 | #FF0000 | Red |  | rmvansickle
68 | 3 | #FF0000 | Red |  | rmvansickle
69 | 3 | #FF0000 | Red |  | rmvansickle
70 | 3 | #FF0000 | Red |  | rmvansickle
71 | 3 | #FF8040 | #N/A |  | rmvansickle
72 | 3 | #FF8040 | #N/A | , | rmvansickle
73 | 3 | #FF8040 | #N/A | , | rmvansickle
74 | 3 | #FF8040 | #N/A | - | rmvansickle
75 | 3 | #FFFF00 | Yellow |  | rmvansickle
76 | 3 | #FFFF00 | Yellow |  | rmvansickle
77 | 3 | #FFFF00 | Yellow |  | rmvansickle
78 | 3 | #FFFF00 | Yellow |  | rmvansickle
79 | 3 | #FFFF00 | Yellow |  | rmvansickle
80 | 3 | #80FFFF | #N/A |  | rmvansickle
81 | 7 | #00FF00 | Bright Green | STAGE 1 comment refers to barriers blocking 100 yr flows into the LA-ROW. Cannot flood adjacent property. | TLStewart | A: AGREE FULLY | JDH - thank you for the clarification. For this project, we are fortunate that only a couple of locations have the resemblance of concentrated flow. For these locations (Sta 805+52, EC-8) and (Sta1107+90, EC-14) the panels are raised and a swale is provided to allow concentrated flow to enter the R/W ditch and not be blocked. Tied Concrete Block Mat is also provided to prevent erosion. For all other locations, the areas draining towards the wall are minimal and are drained by a 6" aggregate underdrain pipe as detailed in the typical sections shown on this sheet. If further discussion is desired please advise and we will set up a call with ODOT D6 PM Katie Montoya and ODOT D6 Drainage Engineer Jon Adams. Response written by Jeff Hackenbracht (Arcadis) Cell # 614-563-9786.
82 | 7 | #00FF00 | Bright Green | REPEAT STAGE 1 COMMENTS | TLStewart
83 | 7 | #FF0000 | Red |  | TLStewart
84 | 7 | #00FF00 | Bright Green | This is in City of Columbus and therefore project must show good faith effort to comply with COC Stormwater Drainage Manual. | TLStewart | A: AGREE FULLY, revised per comment | JDH-Response: As discussed during a call with the COC on 2-14-2024, and further supplemented by Outfall Details showing that the project drainage areas outfall to waters of the state, ODOT believes it has provided a good faith effort to comply with the COC storm water policy with the BMP provisions provided within the Stage 3 plan set. Please refer to the Project Site Plan (P.29-P.32) for a table providing the type and location of the BMPs. BMP calculations are also provided for review. If further discussion is desired please advise and we will set up a call with ODOT D6 PM Katie Montoya and ODOT D6 Drainage Engineer Jon Adams. Response written by Jeff Hackenbracht (Arcadis) Cell # 614-563-9786.
85 | 21 | #FF0000 | Red |  | TLStewart
86 | 21 | #00FF00 | Bright Green | Where are the details or STD DWG for this outlet. (typical comment) | TLStewart | A: AGREE FULLY, revised per comment | JDH-RESPONSE: THE UD OUTLET DETAILS ARE ODOT SCD DM-1.1. PLEASE SEE THE NEXT TWO PAGES WHICH SHOWS THE DM-1.1 DETAILS. IN ADDITION, PLEASE REFER TO THE CROSS SECTIONS FOR PROFILES OF THE RESPECTIVE UD OUTLETS THROUGHOUT THE PROJECT LIMITS.
87 | 33 | #00FF00 | Bright Green |  | TLStewart
88 | 33 | #00FF00 | Bright Green |  | TLStewart
89 | 33 | #00FF00 | Bright Green | 237/2 | TLStewart | A: AGREE FULLY, revised per comment | JDH - SCPZ limits revised per City Comment
90 | 33 | #00FF00 | Bright Green | Stream Corridor Protection Zone | TLStewart | A: AGREE FULLY, revised per comment | JDH - SCPZ limits revised per City Comment
91 | 33 | #00FF00 | Bright Green | SCPZ is always the larger of the formulas provided. | TLStewart | A: AGREE FULLY, revised per comment | JDH - SCPZ limits revised per City Comment
92 | 33 | #00FF00 | Bright Green |  | TLStewart
93 | 33 | #00FF00 | Bright Green | This is disturbance within the SCPZ & most be mitigated. | TLStewart | A: AGREE FULLY, revised per comment | JDH - COMPLIED AND SPECIFIED NATIVE VEGETATION WITHIN THE SCPZ LIMITS
94 | 33 | #00FF00 | Bright Green |  | TLStewart
95 | 33 | #00FF00 | Bright Green |  | TLStewart
96 | 33 | #00FF00 | Bright Green | 237/2 | TLStewart | A: AGREE FULLY, revised per comment | JDH - Complied
97 | 33 | #00FF00 | Bright Green | SCPZ | TLStewart | A: AGREE FULLY, revised per comment | JDH - Complied
98 | 33 | #00FF00 | Bright Green |  | TLStewart
99 | 33 | #00FF00 | Bright Green |  | TLStewart
100 | 1 | #00FF00 | Bright Green | Need to address NPDES requirements, SWPPP, table of SCP's and their owner's | TLStewart | B: AGREE PARTLY, EXCEPTIONS NOTED | JDH Response: Per ODOT, this project will follow ODOT's policy regarding NPDES which includes a project site plan and applicable SS832 pay items. Please refer to P. 24 (General Summary) and P.29-P.32 (project site plan) for details. If further discussion is desired please advise and we will set up a call with ODOT D6 PM Katie Montoya and ODOT D6 Drainage Engineer Jon Adams. Response written by Jeff Hackenbracht (Arcadis) Cell # 614-563-9786.
101 | 46 | #00FF00 | Bright Green |  | TLStewart
102 | 46 | #00FF00 | Bright Green | Can this be made steeper. 1.0% preferrable | TLStewart | B: AGREE PARTLY, EXCEPTIONS NOTED | JDH - I wasn’t able to find the markup on the sheet. I'm suspecting it has to do with the Uds. Unfortunately the topography is flat so we have developed the best UD slopes possible given the flat terrain.
103 | 210 | #00FF00 | Bright Green | REPEAT STAGE 1 COMMENTS | TLStewart | B: AGREE PARTLY, EXCEPTIONS NOTED | JDH - See next line for response
104 | 210 | #00FF00 | Bright Green | There should be a maintenance plan or contingency within the design. | TLStewart | B: AGREE PARTLY, EXCEPTIONS NOTED | JDH - Per ODOT, this project will follow ODOT's stormwater policy. Please note that since Stage 2 ODOT has directed Arcadis to add 3 additional inlets which will provide contingency against blockage. In addition, ODOT has directed that the window opening inlets shown on this detail sheet be switch to barrier grate inlets if adequate depth is available for an outfall, Please refer to P.226 for a detail of the barrier grate detail. A total of 11 barrier grate inlets and 6 window opening inlets are proposed for this project. The barrier grate inlets are being added partially in response to your comment concern about contingency against blockage. In addition, ODOT has changed the opening of the window inlets to 6" from 4" to provide more contingency against blockage. Updated CDSS calcs have been provided for COC/ODOT review. If further discussion is desired please advise and we will set up a call with ODOT D6 PM Katie Montoya and ODOT D6 Drainage Engineer Jon Adams. Response written by Jeff Hackenbracht (Arcadis) Cell # 614-563-9786.
105 | 210 | #FF0000 | Red |  | TLStewart
106 | 20 | #00FF00 | Bright Green |  | TLStewart
107 | 20 | #FF0000 | Red | 250'-3" | TLStewart | B: AGREE PARTLY, EXCEPTIONS NOTED | JDH - COMPLIED AS FOLLOWS: 1) SET THE SCPZ WIDTH AS BEING THE GREATER OF THE CALCULATED SCPZ WIDTH OR THE FLOODWAY WIDTH. IN THIS CASE THE FLOODWAY WIDTH GOVERNED AND AS A RESULT ARCADIS LABLED THE SCPZ LINES AT THE SAME LOCATION OF THE FLOODWAY LINES. THE FLOODWAY LINES ARE NOT CENTERED ON ROCKY FORK.
108 | 20 | #00FF00 | Bright Green |  | TLStewart
109 | 20 | #00FF00 | Bright Green | SCPZ | TLStewart | B: AGREE PARTLY, EXCEPTIONS NOTED | JDH- see line 108 for reponse
110 | 20 | #00FF00 | Bright Green |  | TLStewart
111 | 20 | #00FF00 | Bright Green | Mitigate disturbance within SCPZ | TLStewart |  | JDH - COMPLIED AND SPECIFIED NATIVE VEGETATION WITHIN THE SCPZ LIMITS
112 | 18 | #00FF00 | Bright Green |  | TLStewart
113 | 18 | #00FF00 | Bright Green |  | TLStewart
114 | 18 | #00FF00 | Bright Green | Mitigate disturbance within SCPZ. 1:1 native vegetation within SCPZ | TLStewart |  | JDH - COMPLIED AND SPECIFIED NATIVE VEGETATION WITHIN THE SCPZ LIMITS
115 | 1 | #FF0000 | Red |  | TLStewart
116 | 1 | #FF0000 | Red |  | TLStewart
117 | 1 | #00FF00 | Bright Green | Will need a note/item for SS 832 if that is how SWPPP is handled | TLStewart | B: AGREE PARTLY, EXCEPTIONS NOTED | JDH Response: Per ODOT, this project will follow ODOT's policy regarding NPDES which includes a project site plan and applicable SS832 pay items. Please refer to P. 24 (General Summary) and P.29-P.32 (project site plan) for details. If further discussion is desired please advise and we will set up a call with ODOT D6 PM Katie Montoya and ODOT D6 Drainage Engineer Jon Adams. Response written by Jeff Hackenbracht (Arcadis) Cell # 614-563-9786.
118 | 10 | #00FF00 | Bright Green | & Stormwater | TLStewart | A: AGREE FULLY, revised per comment | JDH - Complied
119 |  |  | N/A
120 |  |  | N/A
121 |  |  | N/A
122 |  |  | N/A
123 |  |  | N/A
124 |  |  | N/A
125 |  |  | N/A
126 |  |  | N/A
127 |  |  | N/A
128 |  |  | N/A
129 |  |  | N/A
130 |  |  | N/A
131 |  |  | N/A
132 |  |  | N/A
133 |  |  | N/A
134 |  |  | N/A
135 |  |  | N/A
136 |  |  | N/A
137 |  |  | N/A
138 |  |  | N/A
139 |  |  | N/A
140 |  |  | N/A
141 |  |  | N/A
142 |  |  | N/A
143 |  |  | N/A
144 |  |  | N/A
145 |  |  | N/A
146 |  |  | N/A
147 |  |  | N/A
148 |  |  | N/A
149 |  |  | N/A
150 |  |  | N/A
151 |  |  | N/A
152 |  |  | N/A
153 |  |  | N/A
154 |  |  | N/A
155 |  |  | N/A
156 |  |  | N/A
157 |  |  | N/A
158 |  |  | N/A
159 |  |  | N/A
160 |  |  | N/A
161 |  |  | N/A
162 |  |  | N/A
163 |  |  | N/A
164 |  |  | N/A
165 |  |  | N/A
166 |  |  | N/A
167 |  |  | N/A
168 |  |  | N/A
169 |  |  | N/A
170 |  |  | N/A
171 |  |  | N/A
172 |  |  | N/A
173 |  |  | N/A
174 |  |  | N/A
175 |  |  | N/A
176 |  |  | N/A
177 |  |  | N/A
178 |  |  | N/A
179 |  |  | N/A
180 |  |  | N/A
181 |  |  | N/A
182 |  |  | N/A
183 |  |  | N/A
184 |  |  | N/A
185 |  |  | N/A
186 |  |  | N/A
187 |  |  | N/A
188 |  |  | N/A
189 |  |  | N/A
190 |  |  | N/A
191 |  |  | N/A
192 |  |  | N/A
193 |  |  | N/A
194 |  |  | N/A
195 |  |  | N/A
196 |  |  | N/A
197 |  |  | N/A
198 |  |  | N/A
199 |  |  | N/A
200 |  |  | N/A
201 |  |  | N/A
202 |  |  | N/A
203 |  |  | N/A
204 |  |  | N/A
205 |  |  | N/A
206 |  |  | N/A
207 |  |  | N/A
208 |  |  | N/A
209 |  |  | N/A
210 |  |  | N/A
211 |  |  | N/A
212 |  |  | N/A
213 |  |  | N/A
214 |  |  | N/A
215 |  |  | N/A
216 |  |  | N/A
217 |  |  | N/A
218 |  |  | N/A
219 |  |  | N/A
220 |  |  | N/A
221 |  |  | N/A
222 |  |  | N/A
223 |  |  | N/A
224 |  |  | N/A
225 |  |  | N/A
226 |  |  | N/A
227 |  |  | N/A
228 |  |  | N/A
229 |  |  | N/A
230 |  |  | N/A
231 |  |  | N/A
232 |  |  | N/A
233 |  |  | N/A
234 |  |  | N/A
235 |  |  | N/A
236 |  |  | N/A
237 |  |  | N/A
238 |  |  | N/A
239 |  |  | N/A
240 |  |  | N/A
241 |  |  | N/A
242 |  |  | N/A
243 |  |  | N/A
244 |  |  | N/A
245 |  |  | N/A
246 |  |  | N/A
247 |  |  | N/A
248 |  |  | N/A
249 |  |  | N/A
250 |  |  | N/A
251 |  |  | N/A
252 |  |  | N/A
253 |  |  | N/A
254 |  |  | N/A
255 |  |  | N/A
256 |  |  | N/A
257 |  |  | N/A
258 |  |  | N/A
259 |  |  | N/A
260 |  |  | N/A
261 |  |  | N/A
262 |  |  | N/A
263 |  |  | N/A
264 |  |  | N/A
265 |  |  | N/A
266 |  |  | N/A
267 |  |  | N/A
268 |  |  | N/A
269 |  |  | N/A
270 |  |  | N/A
271 |  |  | N/A
272 |  |  | N/A
273 |  |  | N/A
274 |  |  | N/A
275 |  |  | N/A
276 |  |  | N/A
277 |  |  | N/A
278 |  |  | N/A
279 |  |  | N/A
280 |  |  | N/A
281 |  |  | N/A
282 |  |  | N/A
283 |  |  | N/A
284 |  |  | N/A
285 |  |  | N/A
286 |  |  | N/A
287 |  |  | N/A
288 |  |  | N/A
289 |  |  | N/A
290 |  |  | N/A
291 |  |  | N/A
292 |  |  | N/A
293 |  |  | N/A
294 |  |  | N/A
295 |  |  | N/A
296 |  |  | N/A
297 |  |  | N/A
298 |  |  | N/A
299 |  |  | N/A
300 |  |  | N/A
301 |  |  | N/A
302 |  |  | N/A
303 |  |  | N/A
304 |  |  | N/A
305 |  |  | N/A
306 |  |  | N/A
307 |  |  | N/A
308 |  |  | N/A
309 |  |  | N/A
310 |  |  | N/A
311 |  |  | N/A
312 |  |  | N/A
313 |  |  | N/A
314 |  |  | N/A
315 |  |  | N/A
316 |  |  | N/A
317 |  |  | N/A
318 |  |  | N/A
319 |  |  | N/A
320 |  |  | N/A
321 |  |  | N/A
322 |  |  | N/A
323 |  |  | N/A
324 |  |  | N/A
325 |  |  | N/A
326 |  |  | N/A
327 |  |  | N/A
328 |  |  | N/A
329 |  |  | N/A
330 |  |  | N/A
331 |  |  | N/A
332 |  |  | N/A
333 |  |  | N/A
334 |  |  | N/A
335 |  |  | N/A
336 |  |  | N/A
337 |  |  | N/A
338 |  |  | N/A
339 |  |  | N/A
340 |  |  | N/A
341 |  |  | N/A
342 |  |  | N/A
343 |  |  | N/A
344 |  |  | N/A
345 |  |  | N/A
346 |  |  | N/A
347 |  |  | N/A
348 |  |  | N/A
349 |  |  | N/A
350 |  |  | N/A
351 |  |  | N/A
352 |  |  | N/A
353 |  |  | N/A
354 |  |  | N/A
355 |  |  | N/A
356 |  |  | N/A
357 |  |  | N/A
358 |  |  | N/A
359 |  |  | N/A
360 |  |  | N/A
361 |  |  | N/A
362 |  |  | N/A
363 |  |  | N/A
364 |  |  | N/A
365 |  |  | N/A
366 |  |  | N/A
367 |  |  | N/A
368 |  |  | N/A
369 |  |  | N/A
370 |  |  | N/A
371 |  |  | N/A
372 |  |  | N/A
373 |  |  | N/A
374 |  |  | N/A
375 |  |  | N/A
376 |  |  | N/A
377 |  |  | N/A
378 |  |  | N/A
379 |  |  | N/A
380 |  |  | N/A
381 |  |  | N/A
382 |  |  | N/A
383 |  |  | N/A
384 |  |  | N/A
385 |  |  | N/A
386 |  |  | N/A
387 |  |  | N/A
388 |  |  | N/A
389 |  |  | N/A
390 |  |  | N/A
391 |  |  | N/A
392 |  |  | N/A
393 |  |  | N/A
394 |  |  | N/A
395 |  |  | N/A
396 |  |  | N/A
397 |  |  | N/A
398 |  |  | N/A
399 |  |  | N/A
400 |  |  | N/A
401 |  |  | N/A
402 |  |  | N/A
403 |  |  | N/A
404 |  |  | N/A
405 |  |  | N/A
406 |  |  | N/A
407 |  |  | N/A
408 |  |  | N/A
409 |  |  | N/A
410 |  |  | N/A
411 |  |  | N/A
412 |  |  | N/A
413 |  |  | N/A
414 |  |  | N/A
415 |  |  | N/A
416 |  |  | N/A
417 |  |  | N/A
418 |  |  | N/A
419 |  |  | N/A
420 |  |  | N/A
421 |  |  | N/A
422 |  |  | N/A
423 |  |  | N/A
424 |  |  | N/A
425 |  |  | N/A
426 |  |  | N/A
427 |  |  | N/A
428 |  |  | N/A
429 |  |  | N/A
430 |  |  | N/A
431 |  |  | N/A
432 |  |  | N/A
433 |  |  | N/A
434 |  |  | N/A
435 |  |  | N/A
436 |  |  | N/A
437 |  |  | N/A
438 |  |  | N/A
439 |  |  | N/A
440 |  |  | N/A
441 |  |  | N/A
442 |  |  | N/A
443 |  |  | N/A
444 |  |  | N/A
445 |  |  | N/A
446 |  |  | N/A
447 |  |  | N/A
448 |  |  | N/A
449 |  |  | N/A
450 |  |  | N/A
451 |  |  | N/A
452 |  |  | N/A
453 |  |  | N/A
454 |  |  | N/A
455 |  |  | N/A
456 |  |  | N/A
457 |  |  | N/A
458 |  |  | N/A
459 |  |  | N/A
460 |  |  | N/A
461 |  |  | N/A
462 |  |  | N/A
463 |  |  | N/A
464 |  |  | N/A
465 |  |  | N/A
466 |  |  | N/A
467 |  |  | N/A
468 |  |  | N/A
469 |  |  | N/A
470 |  |  | N/A
471 |  |  | N/A
472 |  |  | N/A
473 |  |  | N/A
474 |  |  | N/A
475 |  |  | N/A
476 |  |  | N/A
477 |  |  | N/A
478 |  |  | N/A
479 |  |  | N/A
480 |  |  | N/A
481 |  |  | N/A
482 |  |  | N/A
483 |  |  | N/A
484 |  |  | N/A
485 |  |  | N/A
486 |  |  | N/A
487 |  |  | N/A
488 |  |  | N/A
489 |  |  | N/A
490 |  |  | N/A
491 |  |  | N/A
492 |  |  | N/A
493 |  |  | N/A
494 |  |  | N/A
495 |  |  | N/A
496 |  |  | N/A
497 |  |  | N/A
498 |  |  | N/A
499 |  |  | N/A
500 |  |  | N/A
501 |  |  | N/A
502 |  |  | N/A
503 |  |  | N/A
504 |  |  | N/A
505 |  |  | N/A
506 |  |  | N/A
507 |  |  | N/A
508 |  |  | N/A
509 |  |  | N/A
510 |  |  | N/A
511 |  |  | N/A
512 |  |  | N/A
513 |  |  | N/A
514 |  |  | N/A
515 |  |  | N/A
516 |  |  | N/A
517 |  |  | N/A
518 |  |  | N/A
519 |  |  | N/A
520 |  |  | N/A
521 |  |  | N/A
522 |  |  | N/A
523 |  |  | N/A
524 |  |  | N/A
525 |  |  | N/A
526 |  |  | N/A
527 |  |  | N/A
528 |  |  | N/A
529 |  |  | N/A
530 |  |  | N/A
531 |  |  | N/A
532 |  |  | N/A
533 |  |  | N/A
534 |  |  | N/A
535 |  |  | N/A
536 |  |  | N/A
537 |  |  | N/A
538 |  |  | N/A
539 |  |  | N/A
540 |  |  | N/A
541 |  |  | N/A
542 |  |  | N/A
543 |  |  | N/A
544 |  |  | N/A
545 |  |  | N/A
546 |  |  | N/A
547 |  |  | N/A
548 |  |  | N/A
549 |  |  | N/A
550 |  |  | N/A
551 |  |  | N/A
552 |  |  | N/A
553 |  |  | N/A
554 |  |  | N/A
555 |  |  | N/A
556 |  |  | N/A
557 |  |  | N/A
558 |  |  | N/A
559 |  |  | N/A
560 |  |  | N/A
561 |  |  | N/A
562 |  |  | N/A
563 |  |  | N/A
564 |  |  | N/A
565 |  |  | N/A
566 |  |  | N/A
567 |  |  | N/A
568 |  |  | N/A
569 |  |  | N/A
570 |  |  | N/A
571 |  |  | N/A
572 |  |  | N/A
573 |  |  | N/A
574 |  |  | N/A
575 |  |  | N/A
576 |  |  | N/A
577 |  |  | N/A
578 |  |  | N/A
579 |  |  | N/A
580 |  |  | N/A
581 |  |  | N/A
582 |  |  | N/A
583 |  |  | N/A
584 |  |  | N/A
585 |  |  | N/A
586 |  |  | N/A
587 |  |  | N/A
588 |  |  | N/A
589 |  |  | N/A
590 |  |  | N/A
591 |  |  | N/A
592 |  |  | N/A
593 |  |  | N/A
594 |  |  | N/A
595 |  |  | N/A
596 |  |  | N/A
597 |  |  | N/A
598 |  |  | N/A
599 |  |  | N/A
600 |  |  | N/A
601 |  |  | N/A
602 |  |  | N/A
603 |  |  | N/A
604 |  |  | N/A
605 |  |  | N/A
606 |  |  | N/A
607 |  |  | N/A
608 |  |  | N/A
609 |  |  | N/A
610 |  |  | N/A
611 |  |  | N/A
612 |  |  | N/A
613 |  |  | N/A
614 |  |  | N/A
615 |  |  | N/A
616 |  |  | N/A
617 |  |  | N/A
618 |  |  | N/A
619 |  |  | N/A
620 |  |  | N/A
621 |  |  | N/A
622 |  |  | N/A
623 |  |  | N/A
624 |  |  | N/A
625 |  |  | N/A
626 |  |  | N/A
627 |  |  | N/A
628 |  |  | N/A
629 |  |  | N/A
630 |  |  | N/A
631 |  |  | N/A
632 |  |  | N/A
633 |  |  | N/A
634 |  |  | N/A
635 |  |  | N/A
636 |  |  | N/A
637 |  |  | N/A
638 |  |  | N/A
639 |  |  | N/A
640 |  |  | N/A
641 |  |  | N/A
642 |  |  | N/A
643 |  |  | N/A
644 |  |  | N/A
645 |  |  | N/A
646 |  |  | N/A
647 |  |  | N/A
648 |  |  | N/A
649 |  |  | N/A
650 |  |  | N/A
651 |  |  | N/A
652 |  |  | N/A
653 |  |  | N/A
654 |  |  | N/A
655 |  |  | N/A
656 |  |  | N/A
657 |  |  | N/A
658 |  |  | N/A
659 |  |  | N/A
660 |  |  | N/A
661 |  |  | N/A
662 |  |  | N/A
663 |  |  | N/A
664 |  |  | N/A
665 |  |  | N/A
666 |  |  | N/A
667 |  |  | N/A
668 |  |  | N/A
669 |  |  | N/A
670 |  |  | N/A
671 |  |  | N/A
672 |  |  | N/A
673 |  |  | N/A
674 |  |  | N/A
675 |  |  | N/A
676 |  |  | N/A
677 |  |  | N/A
678 |  |  | N/A
679 |  |  | N/A
680 |  |  | N/A
681 |  |  | N/A
682 |  |  | N/A
683 |  |  | N/A
684 |  |  | N/A
685 |  |  | N/A
686 |  |  | N/A
687 |  |  | N/A
688 |  |  | N/A
689 |  |  | N/A
690 |  |  | N/A
691 |  |  | N/A
692 |  |  | N/A
693 |  |  | N/A
694 |  |  | N/A
695 |  |  | N/A
696 |  |  | N/A
697 |  |  | N/A
698 |  |  | N/A
699 |  |  | N/A
700 |  |  | N/A
701 |  |  | N/A
702 |  |  | N/A
703 |  |  | N/A
704 |  |  | N/A
705 |  |  | N/A
706 |  |  | N/A
707 |  |  | N/A
708 |  |  | N/A
709 |  |  | N/A
710 |  |  | N/A
711 |  |  | N/A
712 |  |  | N/A
713 |  |  | N/A
714 |  |  | N/A
715 |  |  | N/A
716 |  |  | N/A
717 |  |  | N/A
718 |  |  | N/A
719 |  |  | N/A
720 |  |  | N/A
721 |  |  | N/A
722 |  |  | N/A
723 |  |  | N/A
724 |  |  | N/A
725 |  |  | N/A
726 |  |  | N/A
727 |  |  | N/A
728 |  |  | N/A
729 |  |  | N/A
730 |  |  | N/A
731 |  |  | N/A
732 |  |  | N/A
733 |  |  | N/A
734 |  |  | N/A
735 |  |  | N/A
736 |  |  | N/A
737 |  |  | N/A
738 |  |  | N/A
739 |  |  | N/A
740 |  |  | N/A
741 |  |  | N/A
742 |  |  | N/A
743 |  |  | N/A
744 |  |  | N/A
745 |  |  | N/A
746 |  |  | N/A
747 |  |  | N/A
748 |  |  | N/A
749 |  |  | N/A
750 |  |  | N/A
751 |  |  | N/A
752 |  |  | N/A
753 |  |  | N/A
754 |  |  | N/A
755 |  |  | N/A
756 |  |  | N/A
757 |  |  | N/A
758 |  |  | N/A
759 |  |  | N/A
760 |  |  | N/A
761 |  |  | N/A
762 |  |  | N/A
763 |  |  | N/A
764 |  |  | N/A
765 |  |  | N/A
766 |  |  | N/A
767 |  |  | N/A
768 |  |  | N/A
769 |  |  | N/A
770 |  |  | N/A
771 |  |  | N/A
772 |  |  | N/A
773 |  |  | N/A
774 |  |  | N/A
775 |  |  | N/A
776 |  |  | N/A
777 |  |  | N/A
778 |  |  | N/A
779 |  |  | N/A
780 |  |  | N/A
781 |  |  | N/A
782 |  |  | N/A
783 |  |  | N/A
784 |  |  | N/A
785 |  |  | N/A
786 |  |  | N/A
787 |  |  | N/A
788 |  |  | N/A
789 |  |  | N/A
790 |  |  | N/A
791 |  |  | N/A
792 |  |  | N/A
793 |  |  | N/A
794 |  |  | N/A
795 |  |  | N/A
796 |  |  | N/A
797 |  |  | N/A
798 |  |  | N/A
799 |  |  | N/A
800 |  |  | N/A
801 |  |  | N/A
802 |  |  | N/A
803 |  |  | N/A
804 |  |  | N/A
805 |  |  | N/A
806 |  |  | N/A
807 |  |  | N/A
808 |  |  | N/A
809 |  |  | N/A
810 |  |  | N/A
811 |  |  | N/A
812 |  |  | N/A
813 |  |  | N/A
814 |  |  | N/A
815 |  |  | N/A
816 |  |  | N/A
817 |  |  | N/A
818 |  |  | N/A
819 |  |  | N/A
820 |  |  | N/A
821 |  |  | N/A
822 |  |  | N/A
823 |  |  | N/A
824 |  |  | N/A
825 |  |  | N/A
826 |  |  | N/A
827 |  |  | N/A
828 |  |  | N/A
829 |  |  | N/A
830 |  |  | N/A
831 |  |  | N/A
832 |  |  | N/A
833 |  |  | N/A
834 |  |  | N/A
835 |  |  | N/A
836 |  |  | N/A
837 |  |  | N/A
838 |  |  | N/A
839 |  |  | N/A
840 |  |  | N/A
841 |  |  | N/A
842 |  |  | N/A
843 |  |  | N/A
844 |  |  | N/A
845 |  |  | N/A
846 |  |  | N/A
847 |  |  | N/A
848 |  |  | N/A
849 |  |  | N/A
850 |  |  | N/A
851 |  |  | N/A
852 |  |  | N/A
853 |  |  | N/A
854 |  |  | N/A
855 |  |  | N/A
856 |  |  | N/A
857 |  |  | N/A
858 |  |  | N/A
859 |  |  | N/A
860 |  |  | N/A
861 |  |  | N/A
862 |  |  | N/A
863 |  |  | N/A
864 |  |  | N/A
865 |  |  | N/A
866 |  |  | N/A
867 |  |  | N/A
868 |  |  | N/A
869 |  |  | N/A
870 |  |  | N/A
871 |  |  | N/A
872 |  |  | N/A
873 |  |  | N/A
874 |  |  | N/A
875 |  |  | N/A
876 |  |  | N/A
877 |  |  | N/A
878 |  |  | N/A
879 |  |  | N/A
880 |  |  | N/A
881 |  |  | N/A
882 |  |  | N/A
883 |  |  | N/A
884 |  |  | N/A
885 |  |  | N/A
886 |  |  | N/A
887 |  |  | N/A
888 |  |  | N/A
889 |  |  | N/A
890 |  |  | N/A
891 |  |  | N/A
892 |  |  | N/A
893 |  |  | N/A
894 |  |  | N/A
895 |  |  | N/A
896 |  |  | N/A
897 |  |  | N/A
898 |  |  | N/A
899 |  |  | N/A
900 |  |  | N/A
901 |  |  | N/A
902 |  |  | N/A
903 |  |  | N/A
904 |  |  | N/A
905 |  |  | N/A
906 |  |  | N/A
907 |  |  | N/A
908 |  |  | N/A
909 |  |  | N/A
910 |  |  | N/A
911 |  |  | N/A
912 |  |  | N/A
913 |  |  | N/A
914 |  |  | N/A
915 |  |  | N/A
916 |  |  | N/A
917 |  |  | N/A
918 |  |  | N/A
919 |  |  | N/A
920 |  |  | N/A
921 |  |  | N/A
922 |  |  | N/A
923 |  |  | N/A
924 |  |  | N/A
925 |  |  | N/A
926 |  |  | N/A
927 |  |  | N/A
928 |  |  | N/A
929 |  |  | N/A
930 |  |  | N/A
931 |  |  | N/A
932 |  |  | N/A
933 |  |  | N/A
934 |  |  | N/A
935 |  |  | N/A
936 |  |  | N/A
937 |  |  | N/A
938 |  |  | N/A
939 |  |  | N/A
940 |  |  | N/A
941 |  |  | N/A
942 |  |  | N/A
943 |  |  | N/A
944 |  |  | N/A
945 |  |  | N/A
946 |  |  | N/A
947 |  |  | N/A
948 |  |  | N/A
949 |  |  | N/A
950 |  |  | N/A
951 |  |  | N/A
952 |  |  | N/A
953 |  |  | N/A
954 |  |  | N/A
955 |  |  | N/A
956 |  |  | N/A
957 |  |  | N/A
958 |  |  | N/A
959 |  |  | N/A
960 |  |  | N/A
961 |  |  | N/A
962 |  |  | N/A
963 |  |  | N/A
964 |  |  | N/A
965 |  |  | N/A
966 |  |  | N/A
967 |  |  | N/A
968 |  |  | N/A
969 |  |  | N/A
970 |  |  | N/A
971 |  |  | N/A
972 |  |  | N/A
973 |  |  | N/A
974 |  |  | N/A
975 |  |  | N/A
976 |  |  | N/A
977 |  |  | N/A
978 |  |  | N/A
979 |  |  | N/A
980 |  |  | N/A
981 |  |  | N/A
982 |  |  | N/A
983 |  |  | N/A
984 |  |  | N/A
985 |  |  | N/A
986 |  |  | N/A
987 |  |  | N/A
988 |  |  | N/A
989 |  |  | N/A
990 |  |  | N/A
991 |  |  | N/A
992 |  |  | N/A
993 |  |  | N/A
994 |  |  | N/A
995 |  |  | N/A
996 |  |  | N/A
997 |  |  | N/A
998 |  |  | N/A
999 |  |  | N/A
1000 |  |  | N/A
1001 |  |  | N/A
1002 |  |  | N/A
1003 |  |  | N/A
1004 |  |  | N/A
1005 |  |  | N/A
1006 |  |  | N/A
1007 |  |  | N/A
1008 |  |  | N/A
1009 |  |  | N/A
1010 |  |  | N/A
1011 |  |  | N/A
1012 |  |  | N/A
1013 |  |  | N/A
1014 |  |  | N/A
1015 |  |  | N/A
1016 |  |  | N/A
1017 |  |  | N/A
1018 |  |  | N/A
1019 |  |  | N/A
1020 |  |  | N/A
1021 |  |  | N/A
1022 |  |  | N/A
1023 |  |  | N/A
1024 |  |  | N/A
1025 |  |  | N/A
1026 |  |  | N/A
1027 |  |  | N/A
1028 |  |  | N/A
1029 |  |  | N/A
1030 |  |  | N/A
1031 |  |  | N/A
1032 |  |  | N/A
1033 |  |  | N/A
1034 |  |  | N/A
1035 |  |  | N/A
1036 |  |  | N/A
1037 |  |  | N/A
1038 |  |  | N/A

## ColorCodes
#00FF00 | Bright Green
#008000 | Green
#003300 | Dark Green
#800000 | Brown
#993366 | Violet
#800080 | Violet
#C0C0C0 | Gray
#FFFF00 | Yellow
#333300 | Brown
#FF9900 | Orange
#FFCC00 | Yellow
#666699 | Purple
#808000 | Olive
#FF6600 | Orange
#00CCFF | Light Blue
#FFCC99 | Peach
#993300 | Brown
#FFFF99 | Yellow
#99CC00 | Lime
#FF00FF | Pink
#FFFFFF | White
#999999 | Gray
#808080 | Gray
#008080 | Turquoise
#99CCFF | Light blue
#33CCCC | Light Blue
#3366FF | Blue
#003366 | Dark Blue
#CC99FF | Purple
#CCFFFF | Light Blue
#00FFFF | Light Blue
#FF99CC | Pink
#CCFFCC | Teal
#339966 | Green
#333333 | Dark Gray
#FF0000 | Red
#000000 | Black
#333399 | Purple
#000080 | Dark Blue
#0000FF | Blue
#45BFED | Light Blue
#44BFED | Light Blue
N/A