{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":13,"n_cols":8,"rows_kept":13,"cut":false,"hidden":false,"merged":[]}
["Date","To",null,"From",null,"Type of Corresp.","What did it say?","Link"]
["1997-10-24","Gov George Voinovich",null,"R. Gregory Hawk","Lynchburg-Clay Local Schools","letter","the intersection of US 50 & SR 134 is 1/4 mile from the site for the new school buildings.    Concerned with safety b/c of blind spot and heavy truck traffic on highway.  Request for either eliminating the blind spot or installing a stop light.","Link"]
["1997-12-01","R. Gregory Hawk","Lynchburg-Clay Local School District","Jerry Wray","ODOT","letter","thanks for the letter.  We will study and respond later","Link"]
["1997-12-04","Tom Evans","ODOT","Richard Chaffin","ODOT","email","request for survey and profile to see what it would take to bring the sight distance up to current design standard","Link"]
["1998-06-03","Jerry Wray","ODOT","R. Gregory Hawk","Lynchburg-Clay Local Schools","letter","notification that they are planning to build a new high school and elementary school","Link"]
["1998-06-24","R. Gregory Hawk","Lynchburg-Clay Local School District","Jerry Wray","ODOT","letter","D9 must do extensive survey work…they will notify you when it is complete","Link"]
["1999-03-08","John Hagen","ODOT","R. Gregory Hawk","Lynchburg-Clay Local Schools","letter","Request for update on the study, and what ODOT plans to do with the intersection","Link"]
["1999-04-12","R. Gregory Hawk","Lynchburg-Clay Local School District","John Hagen","ODOT","letter","Survey was performed.  ODOT is evaluating the survey.","Link"]
["2000-03-13","Dennis Stapleton","State Representative","John Hagen","ODOT","letter","ODOT listed existing traffic control.  Possible improvements and cost estimates.  Still further investigation needed.  We will put it on the list.  Will notify you when more info is available","Link"]
["2000-05-04","John Hagen","ODOT","Richard Chaffin","ODOT","IOC","Request for approval for Woolpert to look at alternatives…John ok'd 5/5/00","Link"]
["2000-05-04","Dennis Stapleton","State Representative","John Hagen","ODOT","letter","Update on status.  We are hiring Woolpert.","Link"]
["2001-06-11","Doug Buskirk","ODOT","Todd D. Willis","Woolpert","letter","submiting 3 sets of plan&profile, typ. Sections and cost estimates for relocation of approx. 600' of SR 134 at US 50","Link"]
["2002-04-09","R. Gregory Hawk","Lynchburg-Clay Local School District","John Hagen","ODOT","letter","Thanks for requesting status.  We decided to relocate the south leg of SR 134 further to the west.  Estimated $410,000.  Unable to get safety money.  We are trying to find other funding source.","Link"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}