## Sheet1
Sign Code | Sign Legend | Sign Size | Total quantity | Install | Remove
R3-2 |  | 36 | 3 | on the date of the road closure | to be removed with a future project in the spring
R3-1 |  | 36 | 2 | on the date of the road closure | to be removed with a future project in the spring
W16-15P |  | 24 | 2 | 14 days after road closure | 30 days after road closure
W23-2 |  | 48 | 2 | on the date of the road closure | 30 days after road closure
W16-H8P |  | 48 | 2 | on the date of the road closure | 30 days after road closure
W1-2L Mod |  | 48 | 2 | on the date of the road closure | perminant sign, will not be removed
W1-2R Mod |  | 48 | 2 | on the date of the road closure | perminant sign, will not be removed
R4-7B |  | 36 | 1 | on the date of the road closure | perminant sign, will not be removed
R3-H8ca |  | 36 | 1 | 14 days after road closure | perminant sign, will not be removed
R3-H8BK |  | 36 | 1 | 14 days after road closure | perminant sign, will not be removed
R11-3 |  | 66 | 2 | on the date of the road closure | 30 days after the road is closed
R11-2 |  | 48 | 2 | on the date of the road closure | 30 days after the road is closed
W20-H13 | (generic legend, this sign has already been ordered) | 60 | 2 | 14 days before the road will be closed | on the day of the road closure
Custom |  | 60 | 2 | on the date of the road closure | 30 days after the road is closed
W16-2P | (Orange sign w/ Black Text and legend should read "1000 feet") | 24 | 2 | on the date of the road closure | 30 days after the road is closed