## Sheet1
RECOMMENDATIONS
| Item | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012
1 | Grease hanger pins above the upper deck | bar: 2002; 2005; 2008; 2011
2 | Install water barrier or stop at hanger blockouts | bar: 2002
3 | Remove loose concrete from Span 12 floorbeams and patch | bar: 2002
4 | Remove loose concrete from Upper and Lower pier shafts and seal | bar: 2002; 2007; 2012
5 | Remove water from East Station (main tunnel and stairwells) | bar: 2002
6 | Replace architectural lighting bulbs as necessary | bar: 2002; 2004; 2006; 2008; 2010; 2012
7 | Seal asphalt wearing surface over stations; Continue to monitor West Station roof slab for additional leaking, especially at the interface between original roof slab and replaced roof slab at joint locations | bar: 2002
8 | Seal upper deck wearing surface (main steel span) | bar: 2002; 2010
9 | Clean rust staining on concrete and spot seal concrete | bar: 2003; 2007; 2011
10 | Install or replace water barrier or stop at utility boxes | bar: 2003; 2008
11 | Remove debris inside West Abutment Cellular construction | bar: 2003
12 | Remove temporary bracing at column A10 in the West Station | bar: 2003
13 | Spot clean and paint structural steel | bar: 2003; 2008
14 | Remove packrust, clean and paint lower deck railing and repair holed through pipe railing | bar: 2004
15 | Clean out clogged scuppers, downspouts and catch basins | bar: 2004; 2006; 2008; 2010; 2012
16 | Grease hanger pins below the upper deck | bar: 2004; 2007; 2010
17 | Remove debris from top of concrete span arch ribs | bar: 2006
18 | Clean and paint steel curb plates | bar: 2006; 2012
19 | Remove delaminated concrete from Span 11 | bar: 2006
20 | Seal parapet concrete (partial or limits) | bar: 2006; 2012
21 | Blast clean and repaint steel beneath deck joints | bar: 2008
22 | Re-seal arch ribs and columns | bar: 2010
Items to be Completed by Others
23 | Have appropriate agency install cable hangers in south bay for downed utility line | bar: 2002
24 | Have appropriate agency replace corrugated metal housing over electric lines in south bay | bar: 2002
25 | Regrade and stabalize fill slopes and Cuyahoga River channel under Spans 1, 2 & 3 | bar: 2002