## Tower B Special Inspect
SFN 1800930
CUY-6-1456
TOWER B MOVEMENT
Tower B (south) is being monitored for movement to the south (away) from the west approach structure. There is also rotation, therefore readings are recorded for left and right edges of the tower. Readings are also taken at a crack monitor at the center of the tower. There is historical evidence that there has been issues with the substructure at this location.
Date | Left Reading | Center Reading | Right Reading | Days from Start | Days from Prev. | Rate from Start L | Rate from Start C | Rate from Start R | Rate from Prev L | Rate from Prev C | Rate from Prev R | Comments
2006-05-06 | 0 | 0 | 0 | [8 empty] | gauge intsalled
2007-05-09 | NA | 0.35 | NA | 368 | 368 | #VALUE! | 0.00095109 | #VALUE! | #VALUE! | 0.00095109 | #VALUE!
2008-01-01 | NA | NA | NA | 605 | 237 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | B&N Inspection
2009-01-01 | NA | NA | NA | 971 | 366 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | B&N Inspection
2010-09-15 | 3.5 | 1.38 | 2.9375 | 1593 | 622 | 0.0021971 | 0.00086629 | 0.001844 | #VALUE! | #VALUE! | #VALUE! | September
2011-03-28 | NA | 1.46 | NA | 1787 | 194 | #VALUE! | 0.00081701 | #VALUE! | #VALUE! | 0.00041237 | #VALUE! | 2011: March: column interface with deck -new concrete spall-see photos
2011-05-09 | NA | 1.52 | NA | 1829 | 42 | #VALUE! | 0.00083106 | #VALUE! | #VALUE! | 0.0014286 | #VALUE!
2011-09-17 | NA | NA | NA | 1960 | 131 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2012-09-21 | 4.125 | 1.56 | 3.5 | 2330 | 370 | 0.0017704 | 0.00066953 | 0.0015021 | #VALUE! | #VALUE! | #VALUE!
2013-01-07 | 4.25 | 2.11 | NA | 2438 | 108 | 0.0017432 | 0.00086546 | #VALUE! | 0.0011574 | 0.0050926 | #VALUE! | Monitor off scale. Install New gauge
2013-04-16 | 4.5 | 2.125 | 3.875 | 2537 | 99 | 0.0017737 | 0.0008376 | 0.0015274 | 0.0025253 | 0.00015152 | #VALUE! | Install New Gauge new 0 will start with 2.125
2013-09-11 | 4.5 | 2.125 | 3.75 | 2685 | 148 | 0.001676 | 0.00079143 | 0.0013966 | 0 | 0 | -0.00084459
|  |  |  | -38843 | -41528 | 0 | 0 | 0 | 0.00010836 | 5.117e-05 | 9.0301e-05
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
|  |  |  | -38843 | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Note on C7: Youssef Seif: gap calculated from crack monitor reading
Note on C12: Youssef Seif: 1.839 shift from average left and right
Note on C16: Youssef Seif: 2.2525 shift from average left and right
Note on C18: Youssef Seif: Transfer Measurement to transfer from old to new crack monitor. Any new measurement should be in inches added to 2.125 then placed in the cell.