## Gateway Pkg Earthwork Summary
PROJECT - Cleveland Innerbelt - CCG1
ODOT PROJECT # - CUY-90-14.90
PID 77332 / 85531
HNTB PROJECT # - 49633 PA 002
TOTAL
|  | VOLUME | VOLUME | AREA |  | VOLUME
|  | (+) | (-) | PAVEMENT | (-) | BORROW
|  | CUT | FILL | REMOVED | (+) | WASTE
Location - Street |  | (CYS) | (CYS) | (SFT) |  | (CYS)
RampA4 |  | 3587.7925 | 5090.812 | 6461.81 |  | -1503.0195
RampA5 |  | 118.8973 | 1.3438 | 0 |  | 117.5535
ML-90 |  | 76.3433 | 6772.8671 | 0 |  | -6696.5239
ML-90 Temp |  | 1807.0841 | 14962.5541 | 0 |  | -13155.47
Carnegie Ave |  | 2405.5063 | 989.3919 | 73282.94 |  | 1416.1144
Ontario Ave |  | 2036.8876 | 1302.5772 | 79843.42 |  | 734.3104
Orange Ave (Sta. 32+50 to 35+00) |  | 60.7407 | 1.323 | 0 |  | 59.4178
Central Viaduct Way |  | 245.7013 | 1351.0087 | 31640.53 |  | -1105.3074
Commercial (Sta. 17+00 to 19+50) |  | 516.6896 | 39.8096 | 11849.74 |  | 476.88
Commercial - Drive Sta 18 (Sta. 0+50 to 2+50) |  | 1388.6759 | 0.75926 | 0 |  | 1387.9167
Tri-C Parking Lot |  | 1772.5 | 1734.83 | 0 |  | 37.67
Downtown Parking Lot |  | 5828.19 | 122.95 | 7302.31 |  | 5705.24
Tri-C/RampA4 BMP |  | 1801.22 | 13.03 | 8269.17 |  | 1788.19
W. 3rd Street BMP |  | 1472.5 | 18.64 | 0 |  | 1453.86
BMP 143+00 |  | 7928.38 | 4.25 | 0 |  | 7924.13
Broadway Mills Wall & Plaza |  | 1937.51 | 2824.05 | 0 |  | -886.54
|  |  |  | 218649.92 |  | -2245.5781
203E10000 | EXCAVATION |  |  |  |  | 32984.6186 | CYS
203E20000 | EMBANKMENT |  |  |  |  | 35230.1967 | CYS
| STRUCTURE BACKFILL | [5 empty] | CYS
**** Quantity of Structural Backfill for retaining walls has not been calculated. The earthwork quantity should be adjusted once those amounts are known. ****

## Gateway Pkg Cross Sections
PROJECT - Cleveland Innerbelt - CCG1
ODOT PROJECT # - CUY-90-14.90
PID 77332 / 85531
HNTB PROJECT # - 49633 PA 002
*Cut/Fill Factor of 1.00
RampA4 | [5 empty] | Accumulated Section Total
Station | Area Cut (SFT) | Area Fill (SFT) | Pavement Removal (SFT) | Vol Cut (CYS) | Vol Fill (CYS) | Vol Cut (CYS) | Vol Fill (CYS)
59917.36 | 0 | 0 |  | 0 | 0 | 0 | 0
59950 | 204.99 | 0 |  | 123.9051 | 0 | 123.9051 | 0
59977 | 248.53 | 4.68 |  | 226.76 | 2.34 | 350.6651 | 2.34
60000 | 298.71 | 4.17 |  | 233.0837 | 3.7694 | 583.7488 | 6.1094
60026 | 303.42 | 0 |  | 289.9144 | 2.0078 | 873.6632 | 8.1172
60050 | 352.02 | 0 |  | 291.3067 | 0 | 1164.9699 | 8.1172
60100 | 151.38 | 0.9 |  | 466.1111 | 0.83333 | 1631.081 | 8.9506
60150 | 393.24 | 5.18 |  | 504.2778 | 5.6296 | 2135.3588 | 14.5802
60200 | 369 | 0 |  | 705.7778 | 4.7963 | 2841.1365 | 19.3765
60222 | 343.86 | 0 |  | 290.4244 | 0 | 3131.561 | 19.3765
60250 | 127.89 | 0 |  | 244.6111 | 0 | 3376.1721 | 19.3765
60300 | 50.33 | 20.3 |  | 165.0185 | 18.7963 | 3541.1906 | 38.1728
60350 | 0 | 156.55 |  | 46.6019 | 163.75 | 3587.7925 | 201.9228
60400 | 0 | 259.06 |  | 0 | 384.8241 | 3587.7925 | 586.7469
60450 | 0 | 354.9 |  | 0 | 568.4815 | 3587.7925 | 1155.2283
60500 | 0 | 449.29 |  | 0 | 744.6204 | 3587.7925 | 1899.8487
60550 | 0 | 520.87 |  | 0 | 898.2963 | 3587.7925 | 2798.145
60600 | 0 | 564.19 |  | 0 | 1004.6852 | 3587.7925 | 3802.8302
60650 | 0 | 567.8 |  | 0 | 1048.1389 | 3587.7925 | 4850.9691
60672.81 | 0 | 0 | 6461.81 | 0 | 239.8429 | 3587.7925 | 5090.812
Pvmt Removal taken by plan view area in microstation (InnerbeltRoadwayQuantities-Gateway-Earthwork.dgn)
RampA5 | [5 empty] | Accumulated Section Total
Station | Area Cut (SFT) | Area Fill (SFT) | Pavement Removal (SFT) | Vol Cut (CYS) | Vol Fill (CYS) | Vol Cut (CYS) | Vol Fill (CYS)
69885 | 76.8 | 0.68 |  | 0 | 0 | 0 | 0
69900 | 87.01 | 1.03 |  | 45.5028 | 0.475 | 45.5028 | 0.475
69945.55 | 0 | 0 | 0 | 73.3945 | 0.86882 | 118.8973 | 1.3438
I-90 WB | [5 empty] | Accumulated Section Total
Station | Area Cut (SFT) | Area Fill (SFT) | Pavement Removal (SFT) | Vol Cut (CYS) | Vol Fill (CYS) | Vol Cut (CYS) | Vol Fill (CYS)
16687.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16700 | 42.02 | 2906.73 | 42.02 | 10.007 | 692.2324 | 10.007 | 692.2324
16750 | 20.34 | 2513.29 | 20.34 | 57.7407 | 5018.537 | 67.7477 | 5710.7694
16772.82 | 0 | 0 | 0 | 8.5955 | 1062.0977 | 76.3433 | 6772.8671
I-90 WB TEMP | [5 empty] | Accumulated Section Total
Station | Area Cut (SFT) | Area Fill (SFT) | Pavement Removal (SFT) | Vol Cut (CYS) | Vol Fill (CYS) | Vol Cut (CYS) | Vol Fill (CYS)
50591.2 | 0 | 0 |  | 0 | 0 | 0 | 0
50600 | 0 | 1131.16 |  | 0 | 184.3372 | 0 | 184.3372
50650 | 42.61 | 915.29 | 42.61 | 39.4537 | 1894.8611 | 39.4537 | 2079.1983
50700 | 101.55 | 969.55 | 78.63 | 133.4815 | 1745.2222 | 172.9352 | 3824.4205
50750 | 149.31 | 965.44 | 149.31 | 232.2778 | 1791.6574 | 405.213 | 5616.0779
50800 | 147.06 | 930.74 | 147.06 | 274.4167 | 1755.7222 | 679.6296 | 7371.8001
50850 | 154.93 | 933.93 | 154.93 | 279.6204 | 1726.5463 | 959.25 | 9098.3464
50883 | 144.78 | 904.64 | 144.78 | 183.1561 | 1123.5706 | 1142.4061 | 10221.917
50900 | 141.97 | 895.62 | 141.97 | 90.2731 | 566.7485 | 1232.6793 | 10788.6655
50950 | 88.84 | 800.15 | 88.84 | 213.713 | 1570.1574 | 1446.3922 | 12358.8229
51000 | 85.73 | 734.04 | 85.73 | 161.6389 | 1420.5463 | 1608.0311 | 13779.3692
51040 | 117.89 | 543.2 | 106.44 | 150.8296 | 946.1037 | 1758.8607 | 14725.4729
51050 | 112.75 | 583.1 | 112.75 | 42.7111 | 208.5741 | 1801.5719 | 14934.047
51052.64 | 0 | 0 |  | 5.5122 | 28.5071 | 1807.0841 | 14962.5541
Carnegie Ave | [5 empty] | Accumulated Section Total
Station | Area Cut (SFT) | Area Fill (SFT) | Pavement Removal (SFT) | Vol Cut (CYS) | Vol Fill (CYS) | Vol Cut (CYS) | Vol Fill (CYS)
1500 | 73.85 | 53.08 |  | 0 | 0 | 0 | 0
1550 | 84.4 | 212.46 |  | 146.5278 | 245.8704 | 146.5278 | 245.8704
1600 | 108.41 | 104.22 |  | 178.5278 | 293.2222 | 325.0556 | 539.0926
1650 | 124.64 | 2.99 |  | 215.787 | 99.2685 | 540.8426 | 638.3611
1664 | 61.21 | 21.48 |  | 48.1833 | 6.3441 | 589.0259 | 644.7052
1700 | 32.58 | 40.3 |  | 62.5267 | 41.1867 | 651.5526 | 685.8919
1750 | 107.45 | 4.3 |  | 129.6574 | 41.2963 | 781.21 | 727.1881
1780 | 54.89 | 8.44 |  | 90.1889 | 7.0778 | 871.3989 | 734.2659
1800 | 0 | 0 |  | 20.3296 | 3.1259 | 891.7285 | 737.3919
1850 | 38.64 | 2.51 |  | 35.7778 | 2.3241 | 927.5063 | 739.7159
1900 | 67.65 | 5.56 |  | 98.4167 | 7.4722 | 1025.923 | 747.1881
1950 | 72.86 | 70.7 |  | 130.1019 | 70.6111 | 1156.0248 | 817.7993
2000 | 77 | 3 |  | 138.7593 | 68.2407 | 1294.7841 | 886.04
2050 | 79 | 0 |  | 144.4444 | 2.7778 | 1439.2285 | 888.8178
2100 | 78 | 0 |  | 145.3704 | 0 | 1584.5989 | 888.8178
2150 | 60 | 0 |  | 127.7778 | 0 | 1712.3767 | 888.8178
2200 | 41 | 3 |  | 93.5185 | 2.7778 | 1805.8952 | 891.5956
2250 | 82 | 37 |  | 113.8889 | 37.037 | 1919.7841 | 928.6326
2300 | 77 | 0 |  | 147.2222 | 34.2593 | 2067.0063 | 962.8919
2317 | 51 | 0 |  | 40.2963 | 0 | 2107.3026 | 962.8919
2350 | 0 | 0 |  | 31.1667 | 0 | 2138.4693 | 962.8919
2400 | 0 | 0 |  | 0 | 0 | 2138.4693 | 962.8919
2417 | 6 | 0 |  | 1.8889 | 0 | 2140.3581 | 962.8919
2450 | 3 | 0 |  | 5.5 | 0 | 2145.8581 | 962.8919
2500 | 21.03 | 13.44 |  | 22.25 | 12.4444 | 2168.1081 | 975.3363
2550 | 65.12 | 0.87 |  | 79.7685 | 13.25 | 2247.8767 | 988.5863
2600 | 52.56 | 0 |  | 108.963 | 0.80556 | 2356.8396 | 989.3919
2650 | 0 | 0 | 73282.94 | 48.6667 | 0 | 2405.5063 | 989.3919
Pvmt Removal taken by plan view area in microstation (InnerbeltRoadwayQuantities-Gateway-Earthwork.dgn)
Ontario Ave | [5 empty] | Accumulated Section Total
Station | Area Cut (SFT) | Area Fill (SFT) | Pavement Removal (SFT) | Vol Cut (CYS) | Vol Fill (CYS) | Vol Cut (CYS) | Vol Fill (CYS)
2500 | 7.5 | 0.02 |  | 0 | 0 | 0 | 0
2550 | 8.17 | 0 |  | 14.5093 | 0.018519 | 14.5093 | 0.018519
2600 | 10.17 | 0 |  | 16.9815 | 0 | 31.4907 | 0.018519
2650 | 8.68 | 0 |  | 17.4537 | 0 | 48.9444 | 0.018519
2661 | 7.89 | 0.02 |  | 3.3754 | 0.0040741 | 52.3198 | 0.022593
2700 | 6.94 | 0.21 |  | 10.7106 | 0.16611 | 63.0304 | 0.1887
2750 | 26.38 | 0 |  | 30.8519 | 0.19444 | 93.8822 | 0.38315
2800 | 30.36 | 6.66 |  | 52.537 | 6.1667 | 146.4193 | 6.5498
2850 | 26.15 | 11.51 |  | 52.3241 | 16.8241 | 198.7433 | 23.3739
2900 | 68.82 | 19.32 |  | 87.9352 | 28.5463 | 286.6785 | 51.9202
2950 | 50.64 | 25.86 |  | 110.6111 | 41.8333 | 397.2896 | 93.7535
3000 | 71.82 | 62.92 |  | 113.3889 | 82.2037 | 510.6785 | 175.9572
3050 | 110.71 | 118.52 |  | 169.0093 | 168 | 679.6878 | 343.9572
3100 | 66.37 | 18.6 |  | 163.963 | 126.963 | 843.6507 | 470.9202
3150 | 19.86 | 8.33 |  | 79.8426 | 24.9352 | 923.4933 | 495.8554
3165 | 33.31 | 0 |  | 14.7694 | 2.3139 | 938.2628 | 498.1693
3200 | 41.3 | 0 |  | 48.3583 | 0 | 986.6211 | 498.1693
3250 | 15.91 | 7.66 |  | 52.9722 | 7.0926 | 1039.5933 | 505.2619
3300 | 83.44 | 0 |  | 91.9907 | 7.0926 | 1131.5841 | 512.3544
3350 | 98.63 | 5.61 |  | 168.5833 | 5.1944 | 1300.1674 | 517.5489
3393 | 79.9 | 15.01 |  | 142.1628 | 16.4196 | 1442.3302 | 533.9685
3400 | 80.52 | 16.12 |  | 20.7952 | 4.0354 | 1463.1254 | 538.0039
3450 | 52.3 | 30.15 |  | 122.9815 | 42.8426 | 1586.1069 | 580.8465
3500 | 79.36 | 43 |  | 121.9074 | 67.7315 | 1708.0143 | 648.578
3550 | 60.09 | 70.41 |  | 129.1204 | 105.0093 | 1837.1346 | 753.5872
3600 | 44.44 | 87.15 |  | 96.787 | 145.8889 | 1933.9217 | 899.4761
3628 | 32.7 | 87.78 |  | 39.9985 | 90.7044 | 1973.9202 | 990.1806
3650 | 14.6 | 95.49 |  | 19.2704 | 74.6656 | 1993.1906 | 1064.8461
3700 | 1.84 | 19.88 |  | 15.2222 | 106.8241 | 2008.4128 | 1171.6702
3750 | 2 | 12.66 |  | 3.5556 | 30.1296 | 2011.9683 | 1201.7998
3800 | 1.62 | 26.5 |  | 3.3519 | 36.2593 | 2015.3202 | 1238.0591
3850 | 1.71 | 15.63 |  | 3.0833 | 39.0093 | 2018.4035 | 1277.0683
3900 | 3.87 | 5.43 |  | 5.1667 | 19.5 | 2023.5702 | 1296.5683
3938 | 8.9 | 2.01 |  | 8.9863 | 5.2356 | 2032.5565 | 1301.8039
3950 | 10.59 | 1.47 | 79843.42 | 4.3311 | 0.77333 | 2036.8876 | 1302.5772
Pvmt Removal taken by plan view area in microstation (InnerbeltRoadwayQuantities-Gateway-Earthwork.dgn)
ORANGE AVE (Sta. 32+50 to 35+00) | [5 empty] | Accumulated Section Total
Station | Area Cut (SFT) | Area Fill (SFT) | Pavement Removal (SFT) | Vol Cut (CYS) | Vol Fill (CYS) | Vol Cut (CYS) | Vol Fill (CYS)
3250 | 0 | 0 |  | 0 | 0 | 0 | 0
3300 | 8.91 | 0 |  | 8.25 | 0 | 8.25 | 0
3350 | 6.8 | 0.61 |  | 14.5463 | 0.56481 | 22.7963 | 0.56481
3400 | 6.33 | 0.065 |  | 12.1574 | 0.625 | 34.9537 | 1.1898
3450 | 7.16 | 0.0294 |  | 12.4907 | 0.087407 | 47.4444 | 1.2772
3500 | 7.2 | 0.02 | 0 | 13.2963 | 0.045741 | 60.7407 | 1.323
CENTRAL VIADUCT WAY | [5 empty] | Accumulated Section Total
Station | Area Cut (SFT) | Area Fill (SFT) | Pavement Removal (SFT) | Vol Cut (CYS) | Vol Fill (CYS) | Vol Cut (CYS) | Vol Fill (CYS)
10000 | 253.26 | 34.67 |  | 0 | 0 | 0 | 0
10050 | 3.27 | 59.09 |  | 237.5278 | 86.8148 | 237.5278 | 86.8148
10073 | 0.91 | 79.82 |  | 1.7804 | 59.1654 | 239.3081 | 145.9802
10100 | 1.39 | 60.92 |  | 1.15 | 70.37 | 240.4581 | 216.3502
10150 | 0.43 | 53.98 |  | 1.6852 | 106.3889 | 242.1433 | 322.7391
10178 | 0.13 | 55.43 |  | 0.29037 | 56.7311 | 242.4337 | 379.4702
10200 | 0.06 | 55.46 |  | 0.077407 | 45.1774 | 242.5111 | 424.6476
10250 | 0.31 | 66.45 |  | 0.34259 | 112.8796 | 242.8537 | 537.5272
10300 | 0 | 56.6 |  | 0.28704 | 113.9352 | 243.1407 | 651.4624
10350 | 0.0127 | 45.1 |  | 0.011759 | 94.1667 | 243.1525 | 745.6291
10400 | 0 | 177.02 |  | 0.011759 | 205.6667 | 243.1643 | 951.2957
10450 | 0.6 | 117.87 |  | 0.55556 | 273.0463 | 243.7198 | 1224.342
10500 | 1.54 | 18.93 | 31640.53 | 1.9815 | 126.6667 | 245.7013 | 1351.0087
Pvmt Removal taken by plan view area in microstation (InnerbeltRoadwayQuantities-Gateway-Earthwork.dgn)
COMMERCIAL - DRIVE STA 18 (Sta. 0+50 to 2+50) | [5 empty] | Accumulated Section Total
Station | Area Cut (SFT) | Area Fill (SFT) | Pavement Removal (SFT) | Vol Cut (CYS) | Vol Fill (CYS) | Vol Cut (CYS) | Vol Fill (CYS)
50 | 143.97 | 0 |  | 0 | 0 | 0 | 0
100 | 273.81 | 0 |  | 386.8333 | 0 | 386.8333 | 0
150 | 249.4 | 0 |  | 484.4537 | 0 | 871.287 | 0
200 | 130.42 | 0 |  | 351.6852 | 0 | 1222.9722 | 0
250 | 48.54 | 0.82 | 0 | 165.7037 | 0.75926 | 1388.6759 | 0.75926
COMMERCIAL (Sta. 17+00 to 19+50) | [5 empty] | Accumulated Section Total
Station | Area Cut (SFT) | Area Fill (SFT) | Pavement Removal (SFT) | Vol Cut (CYS) | Vol Fill (CYS) | Vol Cut (CYS) | Vol Fill (CYS)
1700 | 0 | 3.14 |  | 0 | 0 | 0 | 0
1750 | 30.83 | 7.89 |  | 28.5463 | 10.213 | 28.5463 | 10.213
1800 | 48.16 | 8.23 |  | 73.1389 | 14.9259 | 101.6852 | 25.1389
1826 | 121.44 | 0 |  | 81.6593 | 3.9626 | 183.3444 | 29.1015
1850 | 94.78 | 0.16 |  | 96.0978 | 0.071111 | 279.4422 | 29.1726
1900 | 62.88 | 0.71 |  | 145.9815 | 0.80556 | 425.4237 | 29.9781
1918 | 58.1 | 1.82 |  | 40.3267 | 0.84333 | 465.7504 | 30.8215
1938 | 37.61 | 7.4 |  | 35.4481 | 3.4148 | 501.1985 | 34.2363
1950 | 32.1 | 17.68 | 11849.74 | 15.4911 | 5.5733 | 516.6896 | 39.8096
Pvmt Removal taken by plan view area in microstation (InnerbeltRoadwayQuantities-Gateway-Earthwork.dgn)
E9th (Sta. 38+00 to 39+00) | [5 empty] | Accumulated Section Total
Station | Area Cut (SFT) | Area Fill (SFT) | Pavement Removal (SFT) | Vol Cut (CYS) | Vol Fill (CYS) | Vol Cut (CYS) | Vol Fill (CYS)
3800 | 0 | 0 |  | 0 | 0 | 0 | 0
3850 | 0 | 0 |  | 0 | 0 | 0 | 0
3900 | 0 | 31.42 | 615.48 | 0 | 29.0926 | 0 | 29.0926
Pvmt Removal taken by plan view area in microstation (InnerbeltRoadwayQuantities-Gateway-Earthwork.dgn)