## Bridge_10 11 (hidden)
DRAWING ISSUE | IMPACT TO DESIGN | ENGINEER OF RECORD | DATE OF CHANGE OR IMAGE OF SEAL/DATE FROM ORIGINAL DOCUMENT
APPROVED FOR CONSTRUCTION | NA | Brian T. Avarello #66619 | Image of Seal from RFC Plans on Title Sheet
RFI 00010 - BL 10 and 11 Shear Connector | No | NA | NA | Mark up sheets!! Examples in folder, marked YES as as-builts
RFI 00018 - BL 10 11 12 Deck Placement | Yes | Brian T. Avarello #66619
RFI 00028 - BL 10 11 Bottom Mat Deck Rebar |  |  |  | Mark up sheets!! Sketch in folder, marked YES as as-builts, no seal
RFI 00040 - BL 7 8 9 10 11 12 Welding SIP Formwork | Yes | Brian T. Avarello #66619 |  | Mark up sheets!! Notes in RFI section, marked YES as as-builts
RFI 00065 - BL 9 10 11 12 Anchored PCB | No | NA | NA | Mark up sheets!! Examples in folder, marked YES as as-builts
RFI 00073 - BL 11 Step 3 Splice Plates | Yes | Tony F. Shkurti #75391
RFI 00128 - Pier Downspout Bracket |  |  |  | Mark up sheets!! Sketch in folder, marked YES as as-builts, sheet 24, no seal
NDC 0003 - BL 10 Vertical Curve | Yes | Kenneth Fertal # 67122
NDC 0004 - BL 10-11 parapets | No | NA | NA | Markup Plan Sheets
NDC 0005 - BL 9 10 11 12 Concrete Seal Limits | No | NA | NA | Markup Plan Sheets
NDC 0006 - BL 9 10 11 12 Deck Slab Chamfer | Yes | Brian T. Avarello #66619
NDC 0007 - BL 9 10 11 12 Crossframe Repair Details | No | NA | NA | Markup Plan Sheets?? Marked yes for as built

## Bridge_12 (hidden)
DRAWING ISSUE | IMPACT TO DESIGN | ENGINEER OF RECORD | DATE OF CHANGE OR IMAGE OF SEAL/DATE FROM ORIGINAL DOCUMENT
APPROVED FOR CONSTRUCTION | NA | Brian T. Avarello #66619 | Image of Seal from RFC Plans on Title Sheet
RFI 00015 - BL 12 Driving Lengths | Yes | Steven T. Hague #67905
RFI 00018 - BL 10 11 12 Deck Placement | Yes | Brian T. Avarello #66619
RFI 00024 - BL 12 Bearings | No | NA | NA | Mark up sheets!! Notes in RFI section, marked YES as as-builts on doc but not RFI log, no seal
RFI 00040 - BL 7 8 9 10 11 12 Welding SIP Formwork | Yes | Brian T. Avarello #66619 |  | Mark up sheets!! Notes in RFI section, marked YES as as-builts
RFI 00041 - BL 12 Step 2 Saw Cut Damage | Yes | Tony F. Shkurti # 75391 |  | Mark up sheets??
RFI 00061 - BL 12 Step 2 Parapet Pour | Yes | Charles A. Cvitkovich #50897
RFI 00065 - BL 9 10 11 12 Anchored PCB | No | NA | NA | Mark up sheets!! Examples in folder, marked YES as as-builts
RFI 00068 - BL 7-12 Pipe Hanger Downspout | No | NA | NA
RFI 00306 - Epoxy-Urethane Conc Sealant BL-7-12 |  |  |  | Mark up sheets!! Marked YES as as-builts, G2, no seal, update color choice from word doc
NDC 0002 - BL 12 Parapet and Deck Elevations |  |  |  | Mark up 17 sheets!! No seal, mark ups in folder
NDC 0003 - BL 10 Vertical Curve | Yes | Kenneth Fertal # 67122
NDC 0005 - BL 9 10 11 12 Concrete Seal Limits | No | NA | NA | Markup Plan Sheets
NDC 0006 - BL 9 10 11 12 Deck Slab Chamfer | Yes | Brian T. Avarello #66619
NDC 0007 - BL 9 10 11 12 Crossframe Repair Details | No | NA | NA | Markup Plan Sheets?? Marked yes for as built

## Bridge_1 (hidden)
DRAWING ISSUE | IMPACT TO DESIGN | ENGINEER OF RECORD | DATE OF CHANGE OR IMAGE OF SEAL/DATE FROM ORIGINAL DOCUMENT
APPROVED FOR CONSTRUCTION | NA | Steven T. Hague #67905 | Image of Seal from RFC Plans on Title Sheet
RFI 00070 - BL1,2,7,8,9 Abut Ext and Seismic Ped Dowel Locations | Yes | Brian T. Avarello #66619 |  | New plans already made
RFI 00156 - BL-1 Saw Cut Line | No | NA | NA | Mark up sheets!! 5,6, 19, 20, and 22/28. marked YES as as-built, no seal or markups
RFI 00300 - BL-1 Beam Seat Elevations | No | NA | NA | Mark up sheets!! 10, 11, 14/28, marked YES as as-built, no seal or markups
NDC 0043 - BL 1 Bearing Dimensions | Yes | Daniel B. Thatcher PE10403985 (IN)

## Bridge_2 (hidden)
DRAWING ISSUE | IMPACT TO DESIGN | ENGINEER OF RECORD | DATE OF CHANGE OR IMAGE OF SEAL/DATE FROM ORIGINAL DOCUMENT
APPROVED FOR CONSTRUCTION | NA | Steven T. Hague #67905 | Image of Seal from RFC Plans on Title Sheet
RFI 00035 - BL 2 7 9 Retrofit Cover Plates Sequence | Yes | Brian T. Avarello #66619
RFI 00036 - BL 2 Rebar Summary | No | NA | NA | Mark up plans for new bars, yes as-built
RFI 00046 - BL 2 Deck Placement | Yes | Hans Hutton #75782
RFI 00054 - BL 2 Battered Pile in Wing Walls | Yes | Brian T. Avarello #66619
RFI 00070 - BL1,2,7,8,9 Abut Ext and Seismic Ped Dowel Locations | Yes | Brian T. Avarello #66619 |  | New plans already made
RFI 00080 - BL2 Step3 D2 Pier Cap Bars | Yes | Brian T. Avarello #66619 |  | Mark up sheets!! 2, 19, 20/35. marked YES as as-built
RFI 00084 - Bridge 2 URB Beam G2 | Yes | Daniel B. Thatcher #76104
RFI 00086 - BL 2 C1 Back Wall Dowels | No | NA | NA | Mark up sheets!! 2, 16/35, marked as As-built, no seal
RFI 00217 - BL-2 Retrofit Plate Drilling Error | Yes | Van W. Robbins # 75987 |  | Mark up sheets!! Note to page 25/35. marked as as-built
NDC 0008 - BL 2 Crossframe Repair Details | No | NA | NA | Markup sheets 2, 21/35, marked as as-built
NDC 0010 - BL 2 7 8 9 Modified Pier Cap Chamfers |  |  |  | Mark up sheets!! Marked YES as as-builts, 2 and 17/38, no seal

## 1510 - Green Bulkhead Wall
SUMMARY OF QUANTITIES
ITEM | DESCRIPTION | TOTAL QUANTITY | UNIT
898E20110 | QC/QA CONCRETE, CLASS QSC1, SUBSTRUCTURE (PIER CAP) | 779 | CU YD
509E10000 | EPOXY COATED REINFORCING STEEL (SUBSTRUCTURE) | 52811 | LBS
507E00200 | STEEL PILES HP 12X53, FURNISHED | 10955 | FT
507E00250 | STEEL PILES HP 12X53, DRIVEN | 10955 | FT
504E11100 | STEEL SHEET PILING, LEFT IN PLACE; MIN. SECTION MODULUS OF 37.73 CUBIC INCHES PER FOOT | 46165 | SF