## Sheet1
DESCRIPTION OF CRITICAL WORK | CALENDAR DAYS TO COMPLETE | DISINCENTIVE $ PER DAY | WORK WINDOW
|  |  | START | END
I-480 EB TO I-77 NB RAMP | 175 | 10900 | 04/01/2025 | 2026-10-15
I-480 WB TO I-77 SB RAMP | 175 | 41800 | 04/01/2025 | 2026-10-15