## Category 1 ($0 - $5M)
Nomination | Project Number | C-R-S | Contractor | ODOT P.E. | Contractor Super | Project Description | Goals Established & Achieved | Key Stakeholders/ Relationships Managed | Challenges / Obstacles | Mitigation Efforts | VECP's | How did Partnering add Value | Additional Information
1A | 24-0464 | FUL-SR 120-14.08 | Vernon Nagel | Alex Laverde | Jason Rickey | - The Metamora bridge project involved the complete removal and replacement of an existing 31-foot reinforced concrete slab constructed in 1957 - A unique aspect of this project was the inclusion of vertical construction, an uncommon element in typical ODOT bridge projects. This involved structural modifications to a local mechanics shop adjacent to the work zone. The building, composed of three bays (A, B, and C) required: •Supporting the roof structure between Bays A & B. •Demolition of Bay A. •Reconstruct the exterior wall between A & B. •All while maintaining uninterrupted business operations. | - The ODOT Fulton County Bridge Replacement Project (24-0464) was carried out with a strong commitment to partnering with the Village of Metamora through open communication, mutual respect, and shared goals - Efforts were made to minimize disruption to residents and businesses by carefully managing traffic, maintaining access, and providing clear public notifications - Safety Goal: Ensure safety for on-site workers, traffic, nearby businesses and patrons. (Toolbox talks, Vibration Monitoring, Church access and detour signing) - Timely Completion Goal: Deliver the project on time with ODOT support for a timely start. Challenges: •VECP approval took over 8 months due to FEMA modeling and documentation issues. •Environmental permit expired on the day of the project award, requiring a revised permit. Revised Waterway Permit was secured by April 25 ,2025 - Reduce disruption to local businesses/ events. •Mikes’ Repair, which faced demolition, was prioritized in scheduling. •Coordination with The Anderson Grain Elevators ensured detour awareness for farm traffic. •Awareness of “Party in the Park” event (June 13 – 15) was factored into planning. | - 20 Subcontractors - Large team structure was essential because the bridge replacement required many areas of technical expertise, strict safety and environmental compliance, and precise scheduling to keep the project on time and within budget. - PM (Alex Laverde) and Inspector (HT5 Matt Lumbrezer) regularly spoke with local business and community to inform project updates and changes. - Pre Con Partnering - Walk and talks with local business and residents. These were face to face conversations that provided updates, addressed concerns and built rapport with the community. - Weekly talks with village council reps - Communicated to the community that the field office maintained an open-door policy. It was common and encouraged – for the mayor, council, business owners and residents to walk in freely. | - The Waterway Permit expired the same day the project was awarded - 10/24/2024 Critical Path Impact: Although the permit was on the critical path, the delay in the Value Engineering (VE) approval created enough float to prevent immediate schedule impact. - VECP Delay and FEMA Modeling Complications Since the VECP was based on the original FEMA design, review could not proceed until the FEMA modeling was corrected. Initial Submission: Conceptual VECP submitted November 11, 2024... Approved to proceed: Granted on July 25, 2025, over eight (8) months later Incomplete Initial Submission: FEMA AE zone compliance, Abutment scour calculations, No-rise certification for the current design On March 19, 2025, the Department identified issues with the original flood zone modeling. On March 20, 2025, a Suspension of Work was issued until the designer could resurvey and rerun the model. The VE coordinator at Central Office left ODOT during this period, causing additional lag in the process. | - Standard ODOT practices such as structured partnering meetings, multi-step dispute resolution procedures, and incentive/disincentive contract clauses helped prevent misunderstandings and align contractor and agency goals | - Enhance constructability and enhance hydraulic performance. The VECP proposed replacing the original three-sided structure with a 57”-11” single-span composite box beam with reinforced concrete deck supported on integral abutments and 36” drilled shafts. Key benefits of the revised design include: •Drilled shaft foundations that avoided underground utilities, minimizing costly relocations. •Reduced impact to adjacent properties and decreased need for temporary shoring. Nomination Form - Guaranteed Minimum Savings (GMS) was $1,011,539.50 - Numerous phone calls between VNI, D2 and CO SME’s helped work though VECP issues | - The bridge was still able to be constructed within the original 120-day closure period - The Project Team demonstrated that Partnering added value by working collaboratively throughout the VECP process to keep the redesign moving forward without impacting the construction schedule - Another lesson learned by VNI and the design team early in the design process was the importance of understanding the timeline associated with a potential Letter of Map Revision (LOMR). The design team worked backward from the hydraulic design requirements to ensure that no water surface elevation change greater than 0.1 feet was introduced... In future projects, LOMR requirements should be among the first items analyzed when completing a full structure redesign, particularly when structure walls are located within a FEMA floodplain. | - No Official Partnering Facilitator - Phil Senn conducted the Official Kick Off Partnering Meeting on March 10, 2025. - Over Time/ Under Budget (Tiue component was due to VECP for FEMA modeling and design/ documentation)… Suspension of Work - No lost time or recordables (3100 man hours) - 0 Early Written Notices - Partnering meetings attached - See DM Creations FB postings via PowerPoint
1B | 24-0051 | Ham-LMST Extension | RB Jergens | Nicholas Hess | Greg Siefring | - Construction of a new 0.34 mile, 10’ wide shared use path connection from the Little Miami Scenic Trail (LMST) near the SR 125/SR32 interchange to Spindlehill Drive. | - (1) ODOT- A profitable project for RB Jergens and quality work provided to the department - Throughout the project the department found that the quality of work performed by the contractor was meeting and in many cases exceeding the contract performance expectations. Communication between the contractor, department, and key stakeholders throughout the project was frequent and effective, leading to the department and contractor providing a better end product to the LPA (Anderson Township) by changing materials to improve future maintenance requirements and lower future maintenance costs to the LPA. - (2) RB Jergens- Fair profit for RB Jerens, Timely Payment by the department, and solving problems at the lowest possible level. The department ensured that RB Jergens was compensated for all work completed throughout the project timely - (3) Environmental - No impacts to the ecosystem and compliance with permits/commitments Good engineering judgement and to minimize the environmental impacts further to the Clough Creek and surrounding ecosystem, the contractor and the department were able to complete the prefabricated truss assembly and installation without installing the TAF - (4) Coordinated Communication - ribbon cutting ceremony held on 11/20/25 onsite to officially open the project to traffic 7 months ahead of schedule | - 15 Subcontractors - Subcontractors had to account for long settlement periods for the fills on both abutments that caused long periods of time when minimal work was able to be completed. Subcontractors were scheduled and completed all their work timely, without being engaged by the prime contractor or the department. | - Spring flooding in 2025 - Cincy received around 3.5" of rain in a 4-day period. This led to significant flooding of the Cincinnati region including the project area. The project in preparation of this rain event moved equipment to the highest ground possible in anticipation of the flooding. Once the rain finished on April 4th the project went to the site to review the stats of the project and discovered the entire project site was underwater. - Duke Energy Gas Line Replacement Project - During the winter of 2024 Duke Energy approached the department about a major gas line replacement project that they had scheduled to complete during the late spring and summer of 2025. RB Jergens and Duke Energy coordinated closely together. Unfortunately, Duke was unable to meet their original contract completion date of June because of a slip. Stop all RB Jergens contract work until October after Duke Energy's finished all their gas line replacement and testing work. - A utility agreement between the utility and department has been established and a change order is being executed to cover the additional costs to the contractors and their subcontractors. - Duke Energy Service Line Strike due to OUPS mislocation (road was opened after 3 hours), Down Guy Wire (The department was able to have a new down guy wire installed and replaced within 2 weeks), Communication Line Strike (Utility tighten line within 1 week), Deficient Drilled Shaft (3 unapproved concrete trucks to the project site leading to the rejection, earthen material had sloughed off and settled inside the rebar cage) | - Before the dispute resolution process, RB Jergens and the Department worked closely to problem solve issues in the field at the lowest level to ensure work could progress with out causing a significant delay to the project. | - There was a single VECP to relocate manhole away from a ramp, removing the need to dig down 30+/- feet to replace a concrete pipe that was deteriorated and install a backflow preventor. - Unfortunately, there were not any savings during the VECP to be realized because the plans included an incorrect pipe size and the contractor had to remove an obstruction from the path of the new pipe to install the contract concrete pipe and backflow preventor. | - Project Team routinely participate in the partnering process to agree to terms on extra work items, schedule changes, and worked through a VECP process to provide the key stakeholders with a better end product. Also, the department, contractor, and LPA were all represented at a ribbon cutting ceremony held for the grand opening of the bike path on 11/20/25 where the local bikers, municipalities, and trustees were in attendance. - The project completed all critical milestones ahead of schedule. The forward and rear abutment fills all settled out and were able to be constructed ahead of the initial scheduled anticipated start time. - The project team was in constant communication throughout the process daily to ensure we stayed ahead of any issues as they came up, discussed future work upcoming, and scheduled inspection needs timely to ensure work could progress without delay | - No Facilitator - No lost time accidents - 0 Early Written Notices - Agreements, Minutes attached with submission. - See Project Photos - Open to Traffic 7 Months Ahead of Schedule despite flooding, drilled shaft issues, and utility conflicts.
1C | 25-0158 | HAM- US 22- 4.807 | JRJ | Scottie Saylor | Mike Ostendorf | - FY25 Urban Paving Project in the City of Norwood on a portion of US 22 (Montgomery Rd). Including ADA Curb Ramp and Sidewalk improvements. | - The goals established were to deliver the best project possible for the State of Ohio/City of Norwood and do so with a safe and well-maintained work environment for the traveling public, successful coordination with the other 2 projects that took place within the same limits without causing impacts to any production, and the result being a quality project that the traveling public/city of Norwood residents can be proud of. - The projects’ main goal was to have substantial work completion/open to traffic in the 2025 calendar year with no impacts to any of the 3 projects that were present in the work zone (Including our own project). | - 5 Subcontractors - The City of Norwood was the key stakeholder on this project, they played a large role in conflict mitigation by directing the scheduling of all 3 of the projects within the area | - (1)Streetcar Rails and Pavement Failures - Scope was 3" Mill/Fill and 5” rut in travel lane and large alligator cracking at US22 and Cameron Ave Intersection… discovered that most of them were due to the existing subgrade containing retired streetcar rails. - Performed a GPR on the rails to determine their location and depth. This yielded accurate results we could use to decide on how to proceed with the work. Total of 4 different runs of tracks present under the road. Total of 4 different runs of tracks present under the road and rails sat 1/2” into milling depths. '- (2) Adjacent Projects - One was a watermain reconstruction project that took place in mainline US22, the other was a safety improvement/sidewalk widening project. These projects in total encompassed roughly half of the length of our project, and due to the nature of the work being done on both, they needed to be substantially completed prior to any work. - It was determined that all 3 projects could be completed in the calendar year if good communication and partnering efforts were made. - Used Mr. Manhole technique which involved saving the casting adjustments until the road was already paved, then coming back with a core attachment on a skid steer to cut a hole in the pavement in which the casting would be adjusted to flush in, then encased in concrete with a steel cage. | - Measures such as resequencing the work with the Mr. Manhole technique and completing the GPR scans of the rails helped mitigate the potential for a dispute between the state and the contractor. | - N/A | - Without partnering the project would have not been able to be completed in the desired timeline. When the project was originally presented it was a possibility that all the streetcar rails would have had to been removed prior to the paving of the road. - Would have been extremely significant force account work item in the range of multiple millions of dollars if the problems were handled this way. Through partnering and good planning this was an outcome that was avoided and a product was delivered that satisfied all parties involved. | - No Facilitator - 0 Lost Time Accidents - 1 Early Written Notices (DSC - Rails) - Project was used as an example for a district wide class on ADA Curb Ramps. This class covered the different parts of a ramp, their tolerances, how the data is collected and recorded, and discussed instances when a, ADA waiver can be used - Partnering Meeting Minutes attached
1D | 24-0458 | ATH-682-6.07 | DGM | Matt Idleman | Adam Bapst | ATH 682-6.07 to 6.41, ATH 33-8.88 Includes the EB and WB US 33 Ramp Intersections from controlled stop to modern roundabouts. | - The primary goal was to maintain traffic safely while providing access to the adjacent property owners. These were achieved by regular communication daily as well as collective discussions at the monthly progress meetings to plan for upcoming traffic phase changes. | - The project did not initially address the relocation of the waterline and forced main sewer line that ran through the middle of the project. - It was decided that for the long-term benefit of the roadway facility, the water line and sanitary sewer line would be relocated outside of the roadway limits once the new embankment was constructed. Finding a subcontractor willing to perform that work on short notice was essential in getting this utility relocation completed without delaying the project completion. | - The project experienced a very wet spring, and everyone understood that this project had to be completed by Thanksgiving when the asphalt plants closed for the season. - Overcoming a lost two weeks during advertising b/c of a quantity bust and dealing with a short construction window. - Design Issues - Issues discovered with drainage structures, the MOT phasing, and obstructions that had not been accounted for. The MOT phasing was one of the most challenging obstacles. The plans showed the phasing tie-ins on the overhead plan view but did not adequately address the vertical differences between the existing and proposed roadway The design team provided some guidance, but most of these issues ended up being solved by the project team. | - key players on the project became comfortable having open and honest conversations with each other. - While there were no “dispute notices” provided, the team understood that there were errors in the plan set that would require coordination between the owner and the contractors. By being upfront regarding these errors, the project team was able to work together to discuss the impacts and work towards solutions as issues were discovered. - | N/A | - The project was ultimately completed before the asphalt plants closed for the season which was the primary goal. - The local feed store expressed their gratitude that we added a truck apron to allow their delivery drivers access to ATH-682 NB now that there was a splitter island in the median. | - No Partnering Facilitator - No lost time accidents - 0 Early Written Notices - Lessons Learned: Ensure each specialist gets a chance to thoroughly review the items of work related to their specialty during the design phase of the project.
1E | 24-0277 | MOT- Vandalia Bikeway Connector | Brumbaugh Construction Inc. | Julia Gourley, P.E. | Troy Myers | - This project provides a bicycle friendly connection from Old National Road Trail, which ends at National Road near Interstate 75, to the Great Miami Recreational Trail and other destinations. Access to the Great Miami Recreational Trail is through Taylorsville Metro Park which is part of Five Rivers MetroParks. | - Honest Counication: Many stakeholders were invited and they attended the progress meetings to provide their feedback - Respond in a timely manner: The remarkable speed and level of effort put forth by engineers from ODOT’s Project Management Team, ODOT’s Office of Geotechnical Engineering, District 7’s structural and geotechnical team, Miami Conservancy District (MCD), ODNR and the designers at LJB, Inc. led to the quick resolution of complex issues. - Safety: Project was completed with zero loss time injuries. The contractor phased work to have minimal impact on the travelling public, including park users, thus reducing the potential for incidents. By constructing, cofferdams and several fall protection fencing configurations, the site was safer for both Contractor and ODOT staff - Complete Project Ahead of Time: Brumbaugh was able to overcome the delays, opening the entire project to traffic by November 17, 2025, ahead of the revised contract completion date of November 26, 2025. - Agree to quantities on every pay estimate: Partial items were paid for when supporting documentation was provided. - Keep City notified on any issues, so their PIO/staff is knowledgeable prior to social media notifications: At each monthly progress meeting, the City of Vandalia, Five Rivers MetroParks, and Miami Conservancy District had representatives present. | - 17 Subcontractors - Stakeholder contributions to project successes began with their commitment to participate in meetings both on-site and monthly progress meetings. Funding for extra work and delays on the project was provided by the City and Parks so that the final product could be delivered as scoped. Their personnel could often be found on the project site and were available as needed to discuss project issues and decisions were quickly made so as not to delay the project. - Security Fence steadily built two traffic signals and removed old signals so walk work could be completed in advance of paving work. - CSX’s project management team often takes blame for delays, however, on this project, after the initial RR flagger delay, they offered alternatives to flaggers to keep construction on schedule. They allowed all work that was located more than 25 feet laterally from the edge of tracks to proceed without any railroad supervision. Only the most critical activities over the railroad were completed when the flagger was on site. CSX also proactively made calls to verify project progress so they could keep this project on their active project scheduling | - Authority: ODNR and MCD had authority which superseded ODOT where MSE wall Construction was scoped on the Taylorsville Dam. MCD also owned part of the land, which was operated by Five Rivers MetroParks, so items such as tree removal had to be approved by both agencies where both had jurisdiction. CSX had authority which exceeded ODOT’s authority near the railroad tracks . While all communication was supposed to go between the Contactor and ODOT’s project management team, permits required direct communication with other agencies. - Vibration Monitoring Submittal: The MCD submittal review transformed into a design review for ODNR. Soil assumptions and analysis methods had to be resolved before vibration monitoring proposal review would be completion raised concerns about construction sequencing which removed the weighted berm at the bottom of the dam, prior to cofferdam construction. Work was halted again. The entire MCD/ODNR review related delay extended the original contract completion date by 57 days. - Survey Monitoring of Slopes after Sheet Pile for excavation bracing of MSE Wall #2. A soil boring showed gravel/stone with sand for about 5.5’, followed by 3’ of silt clay to the bottom of the bore in the area - CSX: CSX Railroad Flagger delays were encountered as soon as Brumbaugh was ready to erect the prefabricated bridge. The RR Flagger Delay #1 lasted nearly six weeks. - VPF conformance issues and further RR delays, differing x-slopes for mill/fill operations, insufficient MSE Wall Length | - Project Engineer quickly reached out to subject matter experts upon notice of complex problems and the SMEs immediately engaged in discussions to resolve issues quickly. - Numerous internal meetings between the Department and DOR as well as additional conversations that included the contractor and remaining stakeholders (i.e. MCD, ODNR, Five Rivers MetroParks, and/or the City). | N/A | - ODOT project staff made efforts to connect with the Brumbaugh’s on-site project team on a more personal level. From the superintendent to operators to laborers, ODOT strived to include everyone in the partnering process. Also, the Taylorsville Park was the site of the 2024 ODOT District 7 Construction Kickoff event. Furthermore, the City of Vandalia invited ODOT to speak at the bikeway’s ribbon cutting, where Brumbaugh and other key stakeholders also attended, celebrating the major success - Project experienced 2-3 additional delays (e.g. Slope Stability, RR Flagger #1, and RR Flagger #2) that were never fully calculated in accordance with PN 107 – Critical Path Method Progress Schedule. Because of Brumbaugh’s ability to expediate completion despite compounded time impacts, both ODOT and Brumbaugh agreed that the effort spent to develop multiple delay analyses was not necessary. - ODOT project, District, and Central Office staff worked together, contacting the RR representative directly, to help Brumbaugh in the procurement of the missing information. | - No Partnering Facilitator - Federal Grant paid for 54% of Project - Dealt with CSX Railroad - Partnering Meeting Minutes - Slightly beyond budget/time (Excusable/Compensable) - 0 Lost Time Accidents - Big Ribbon Cutting Event w/ all Stakeholders - CSX, MSD, and ODNR had higher authority through portions of the Project which made - Number of Verbal's, 1 Early Written Notice - The project opened to traffic 30 days after the original completion date, yet prior to the revised contract completion date. - With concurrence from the City, Brumbaugh and Barrett Paving worked with both ODOT and Five Rivers MetroPark to ensure that all haul road related damage was repaired - Lessons Learned: Due to the significant delays created by this oversight, future projects should require an ODNR approval as part of the design review process
1F | 24-3001 | WOO-US23 Roundabout | Kokosing MBI | Tyler Vaughn | Craig Wing | - Construction of a single-lane roundabout at the intersection of US 23 and SR 105 in Wood County and Sandusky County utilizing the Progressive Design Build (PDB) contract delivery method. The roundabout was a digital delivery pilot project for ODOT; the first of its kind within ODOT to be fully designed and constructed using only Building Information Modeling (BIM) technology. | - Utilize BIM Technology and deliver Project w/out Paper Plans - Establish working platform for future BIM projects - Improve traffic flow (Top 150 Dangerous Intersection) - Maximize Project Scope - This kept the project budget within reason while providing the best product for the traveling public within our right-of-way footprint. The utilization of a risk register in the PDB contract allow to mitigate risk out of bid items receiving a better value overall. - Maximize Environmental Scope - Created solutions to mitigate and minimize impacts to the environment. Establishing an initial SWPPP plan that was further adjusted during phase 2 and installing long term BMPs. - Construction Schedule - Collaboration with ODOT allowed for a reasonable construction window to be developed for phase 2. The risk register included a premium time for weekend work to allow the contractor to meet the open-to-traffic milestone date. Project was completed on time | - 7 Subcontractors - MBI: Michael Baker was instrumental in leading the digital design process. They had invaluable experience delivering digitally designed projects utilizing the same modeling software used on this project and ensuring that field personnel were confident extracting information from the model to build the project. | - 3D Model Learning: A unique challenge to the project was ensuring subcontractors had sufficient information to perform their work with the lack of conventional “paper” construction plans - BIM Technology: Multiple training events, purchasing of proper hardware and software helped mitigate the implementation. - Progressive Design Build Process: Navigating Open Book Pricing, Risk Register, R/W, Environmental, "Bid Opening", and funding codes. | - ODOTs Team: The Project Manager was John Erford (Design) and Project Engineer Tyler Vaughan (Construction). Both were involved with the project from “cradle to grave.” This allowed for a dynamic team that paired up nicely with the DBT that further developed a partnering mindset with the contractor and designer. - There was no need for a formal dispute resolution process on the project and by its nature, a PDB contract is collaborative and was quite effective in mitigating risk and disputes. - Initially planned as a two-phase project where the roundabout would be built in halves, the MOT was modified to allow for a full intersection closure so the project could be complete in a single construction season. Not only did this provide schedule benefits by shortening duration, it also provided a better-quality product with the elimination of phase line joints and a safer working environment for project staff with the absence of adjacent traffic. | N/A - Value Engineering was in essence performed throughout design and preconstruction via collaboration between ODOT, the DBT, and key stakeholders. Negotiating the MOTin Phase 1 was a prime example of a valued change. Originally the project was to be constructed in two phases. | - Building Information Modeling (BIM) is simply a smart 3D blueprint for a building or infrastructure project. It’s not just a picture—it’s a digital model that includes all the details about the project: •Dimensions •Materials •Costs •Schedules (phasing) •Even how systems fit together / clash detection It’s like having a virtual project that you can walk through and check before you build the real thing. If something doesn’t fit, you catch it early. - The DBT was instrumental in working with ODOT Real estate and R/W. These processes of acquiring R/W and easements are still rooted in a paper plan set. The DBT provided information early and often to allow these parties to perform their work on a strict timeline | - Progressive Design Build (Phase 1A - Proof of Concept, Phase 1B Design, Phase 2 Construction) - No Facilitator - 0 Safety Incidents - 0 Early Written Notices - High-trust environment was created where both ODOT and Kokosing appreciated the goals and needs of each other. Decisions were made quickly and collaboratively to obtain necessary approvals and guidance that could have otherwise added cost or time to the project. - Awards/Presentations: ACEC Engineering Excellence Award submitted (Ohio and National) Presented at: OTEC 2024, OTEC 2025, OCA Winter Conf. 2025
1G

## Category 2 ($5M-$20M)
Nomination | Project Number | C-R-S | Contractor | ODOT P.E. | Project Description | Goals Established & Achieved | Key Stakeholders/ Relationships Managed | Challenges / Obstacles | Mitigation Efforts | VECP's | How did Partnering add Value | Additional Information
2A | 24-0488 | CUY-IR 480 17.87WN/17.90ES Decks | Great Lakes | Richard Hulick | - Project consists of replacing the decks of the IR-480 EB & WB ramp bridges to IR-77 over mainline IR-480 in the City of Independence, Cuyahoga County. Additional work also includes approach slabs, expansion joints, full depth pavement and resurfacing ramps ES and WN for an approximate length of 5,550 Feet. | - Keep the ramp closures to 124 consecutive days (or less): Unfortunately, this goal was not met. Due to weather and excusable delays (51 days) related to the installation of lateral bracing, a revised open-to-traffic date of 10/25/25 was established. The bridges were opened on 10/18/25. - Keep the safety of the motoring public, and construction personnel at the forefront of all decision making: Maintenance of traffic was always a topic of conversation. Due to the ODOT’s project staff familiarity with the I-480 traffic below, we were able to implement some lessons learned from previous projects. | - 18 Subcontractors - Armstrong Steel Erectors: One of the project’s biggest hurdles was the installation of the lateral bracing. Due to a plan error, the lateral bracing was unable to be installed as per plan. Armstrong prioritized this work to keep the project moving. - Flatrock LLC:327,850 Lbs. of reinforcing steel was installed on the project over the course of 35 Days. Flat Rock worked through inclement weather to keep deck pours as scheduled - JADCO Construction Services: Due to a significant amount of unanticipated delaminated concrete on the top surface of the existing pier caps. As a result, it was necessary to pour the pier caps back in two pours as opposed to one as originally intended. | - Posted detour routes for the two heavily travelled I-480 / I-77 Interchange ramps: The detours significantly increased traffic on the Transportation Blvd Exit (Garfield Heights), SR 17 Exit (Village of Brooklyn Heights) and Grant Ave. (Cuyahoga Heights). The municipalities were accepting that the first few weeks of the closures would be chaotic and were great partners to the project throughout its construction - Access to the Work: The ramp bridges were located below the heavily traveled I-77 and above the heavily traveled I-480 - Demolition of Decks: The existing decks and parapets were badly deteriorated - Lowering of Structure Vertical Clearance: During the review of the jacking plan submittal, the designer stated that the structures were being lowered by 2”. The lower final elevation of the girders was intended to improve the vertical clearance to the structures above, but this was not apparent in the plans - Lateral Bracing: The plans showed the lateral bracing members being bolted to the bottom flange of each girder. However, superelevation prevented this from being achievable in the field - Expansion Joints: Three of the four expansion joints were not fabricated correctly. ODOT permitted the contractor to modify them in the field to minimize the duration of the ramp closures. | - A number of potential project issues were brought to everyone’s attention well before they impacted the project schedule. This allowed us time to resolve, if necessary, without impacts to the schedule | N/A | - There were ODOT or Contractor issues; however, all issues were perceived as project issues. This resulted in everyone taking an active role in pursuing solutions and using all available resources. | - No Partnering Facilitator - 0 Safety Incidents - 4 Verbal's; 2 Early Written Notices - Team has won Lakefront W 73 before - Project was A+B and ramps were bid to be completed in 129 days but incurred a 45 excusable delay - Partnering held Partnering/ Progress Meetings
2B | 24-9006 | HAM-471-0.00 | Great Lakes | Chris Tuminello | - On November 1, 2024, an arson-induced fire beneath the southbound approach span of the Daniel Carter Beard “Big Mac” Bridge caused severe damage to seven steel plate girders and approximately 7,600 square feet of deck - ODOT immediately engaged The Great Lakes Construction Co. and E.L. Robinson Engineering to stabilize, demolish, redesign, fabricate, and reconstruct the structure at unprecedented speed. Through a design-assist partnering model, the project team jointly selected available materials, optimized girder design, simplified fabrication details, and executed winter demolition and reconstruction activities | - Reopen SB IR771 Safely and Timely (Opened in 100 Days) - Perform demo, stabilization, fabrication, erection, and deck replacement safely in harsh conditions (0 Lost time incidents) - Build Public Trust (Twice Weekly PIO Meetings and daily progress briefings, onsite media days, coordinated press conferences, etc.) - Deliver High Quality Work under Accelerated Schedule (rigorous QC during cold weather concrete pours and optimized girder details) | - 13 Subcontractors - Stupp: Began fabrication before receiving a formal PO, based solely on trust. Delivered all seven girders between January 12–15, ahead of schedule - Nucor & Cleveland-Cliffs: Pre-rolled plate steel in anticipation of national emergency needs - ELR: Collaborated daily with ODOT and Great Lakes on design refinements - Demolition & Shoring Design, Electrical: Pads within the first week. Worked through winter conditions to support steel erection - Communications: Cincinnati Reds organization publicly honored the project team with a ceremonial first pitch, recognizing | - Structural Instability & Unknown Damage: Warped, detached girders created collapse risks - Public & Political Pressure: Bridge closure caused significant congestion and frustration. City of Cincinnati Councilman Seth Walsh publicly admonished D8 Deputy Director, Tammy Campbell, for not working fast enough - Maintaining Schedule Under Emergency Pace: Real time engineering, shop drawing approvals, and field decisions were enabled by daily alignment and shared priorities. - Traditional lead times of 10-12 Months for Steel Availability - Absence of Plans: Original 1976 plans lacked sufficient detail. - Winter Weather Impacts | - Daily issue resolution prevented formal disputes from materializing. - Design-assist eliminated most causes of disputes (i.e. scope gaps, design omissions, ambiguity, etc.). - Early problem elevation ensured field crews were never delayed by administrative issues. - Public messaging coordination mitigated political and community pressure. - Vendor partnering mitigated submittal review delays. |  | - Partnering reduced schedule risk, eliminated claims, minimized cost growth, improved public sentiment, and delivered a 3-year project in 100 days - Shop drawings were reviewed “over-the-shoulder” to eliminate months of processing time. - Vendor partners operated on trust, beginning fabrication before formal paperwork - Lessons Learned: Design-Assist Emergency Delivery accelerated structural repairs dramatically and should be considered for future emergency declarations and other schedule driven projects. This feature mitigated disputes which ordinarily occur on DB or DBB projects Winter Concrete Innovations Heated enclosures, accelerated mixes, and strategic sequencing enabled high-quality pours despite freezing conditions. Transparent Public Messaging Taking the public “on the journey” through media events and updates transformed public sentiment and minimized frustration. | - 0 Lost Time Accidents - Not conducive to Partnering Facilitator - First Pitch Cincy Reds Game - LaRosa's Pizza Truck showed up during milestone events - Joint Field Office - Fabrication Shop Media Day - 0 Early Written Notices
2C | 22-3000 | GUE-209-8.56 | Ruhlin | Cheyann Moore | - Improve GUE-209-8.56 in Guernsey county, Ohio, in accordance with plans and specifications by replacing the existing bridge using the design build process. | - Project Safely, - On schedule, - Within budget, - All while meeting necessary requirements and specifications - The project team held an initial partnering meeting with all stakeholders and community members at a local Cambridge, OH restaurant. - Mission Battement, ‘Thoughtfully steward an on-time, to-spec, in-budget, injury-free bridge project that becomes a tangible source of pride and conversation for the Design Build Team, stakeholders, and the City of Cambridge | - 26 Subcontractors - Ruhlin Company, Burgess & Niple, and the City of Cambridge as main stakeholders | - Structure Demo: This project was originally designed and sold as a rehabilitation; however, the contract was terminated due to the complexity of the existing structure and the analysis required for demolition. - The structure itself was a complex design and construction as the bridge was superelevated and on a curve with radial skew. - Site Access: The bridge spanned over a railroad as well as a creek. While railroad coordination was less complex, Wills Creek posed multiple obstacles when a tremendous rainy season caused not one but two major floods to the construction site. | - OHWM: Ruhlin requested five weather days to make repairs from flooding and reschedule cranes needed for beam erection.Ruhlin provided the department with historical precipitation records that showed a traditional causeway would have been flooded 14 days where their design was only flooded 5 days. The flood levels were also 6 feet above OHWM. | N/A | - The project team was able to demonstrate partnering added value to the project by solving problems internally at the project level, eliminating delays in work and additional costs associated with escalations | - Partnering Facilitator: Tom Hyland - 0 Safety Incidents - Large opening ceremony that was well attended by the community and even televised - Presented Project at OTE C 2024 and Conaway 2025 - 1 Verbal Notice, I Early Written Notice - Project remained on schedule and meant milestone dates for completing design, demolition, and reconstruction - 2024 Association for Bridge Construction and Design - New Medium Span Bridge Category Award Winner - Partnering Meeting Minutes
2D | 24-0511 | CUY-271-8.28 / 9.73 | Shelly Company | Alec Pack | - Part 1 of the project consisted of switching the two crossover locations between the I-271 NB Express and NB Local lanes, extending the existing auxiliary lane and adding an additional auxiliary lane for the NB Cedar / Brainard Rd. exit Project also included drainage system adjustments, added a traffic island between the I-271 NB exit ramp and Cedar Rd, and updated the NB traffic control along the corridor. Part 2 included resurfacing the NB and SB Local lanes from Fairmount to the Mayfield Heights Corp. limit | - Safety of the project staff and motoring public Reduced closure period of Cedar Rd off Ramp. Revised maintenance of traffic scheme resulted in more consisted work zones and reduced the number of phases. - Completion on-time / ahead of schedule Goal to complete a two-construction season project in a single season. Project substantially completed 10 months ahead of completion date - Highly visible project Maintain work site and maintain strong work presence Contractor worked both day and night shifts to complete the project. Project received positive feedback from public | - 27 Subcontractors -Cities of Lyndhurst, Pepper Pike, Mayfield Heights and Beachwood The project and its alternate MOT scheme received full support from our local partners -Bunn The underdrain subcontractor performed work in awork zone, with quick responses to Shelly’s requested needs | -Maintenance of Traffic; A high volume of daily traffic and restrictive lane closure hours, especially for mainline resurfacing The project focused on a well maintained work zone, and worked concurrent Day & Night shifts as necessary - Material supplier issues Multiple plant failures impacted asphalt production, and failed samples led to mid-day production stoppages Out of date JMFs led to a last minute material supplier switch in order to keep work progressing - Narrow/confined work area The work zone was a median (between local and express lane traffic) appx. 48 feet wide and 9400’ long Work scheduling and truck paths had to be carefully considered as to not impede progress or damage previously constructed work - Differing Site Conditions, drainage. Much of the drainage work consisted of tying into the existing interstate sewer system. Issues encountered included differing conduit size or material, unknown appurtenances in abandoned locations, and downstream drainage blockages resulting in structure flooding The Department was able to call upon the county manager and maintenance forces to bring a vac- | - Shelly proposed a modification to the planned MOT in which we closed both express lane entrance / exit ramps concurrently which greatly reduced the overall construction duration. The project asked all affected municipalities to weigh in on the proposal, and all were very pleased with the reduced construction duration. | -N/A | - The Engineer and Superintendent performed as many activities jointly as time and schedule would allow. These included initial project layout, pavement inspection and partial depth repair marking, and job trailer meetings in advance of and maintenance of traffic phase changes. - Without partnering the project would have been completed over the course of two construction seasons as opposed to one. The Department and Shelly sat down to discuss the proposed MOT changes which facilitated the accelerated schedule | - No Partnering Facilitator - 0 Safety Incidents - 8 Verbal's; 0 Early Written Notices - The project was able to substantially complete all work 10 months ahead of the original project completion date. Effectively reducing the project to a single season.
2E | 22-0625 | CLE-CR-171 | JRJ | Josh Bradford | - reconstructing and widening roadway, constructing waterline and drainage, installing traffic signals and lighting, and related work Historical Background This project was part of an 8 phase larger scale project that improved the 32 corridor in Clermont County between IR-275 and Stonelick Olive Branch. This project built the intersection of Old 74 and Bach Buxton Road which tied into an adjacent project, CLE103954. Getting this intersection built was critical to open the bridge that was built on CLE103954. | - Communicate openly and honestly - Build a project that is safe for the workforce and the travelling public - Treat all stakeholders with respect. Remain open to all viewpoints Talked with Holman Motors and they requested a temporary fence during construction so that their property could be secured; Clermont Engineer’s Office was involved in all the MOT phase changes - Focus on the project first with attitudes of success and fairness - ODOT is committed to prompt payment to contractors - Create a positive team culture in the administration of the project - Commit to mitigate the impact of issues as they arise - Resolve issues on projects respectfully utilizing the Dispute Resolution process. - Build a quality project for which we are proud Project opened to traffic ahead of schedule in December of 2023. Only work that was done in 2024 was permanent signals, permanent striping, punch list, and some force accounts that cropped up. | - 10 Subcontractors - Clermont County: Early on in the life of the project we discussed with them modify the first MOT phase which allowed for a full closure of Old 74 for approximately 70% of the project limits. - CCEO also helped with all the concerns that were brought to them by the impacted businesses and property owners - Clermont County Water Resources Division: During the storm sewer work they provided a map showing locations of where the sanitary laterals came across the road. This information was not shown on the plans - Elex: Elex Worked to get everything to install a temporary signal at the intersection of Old 74 and Bach Buxton for the time being so that the adjacent project could go into the next phase - Elite Sports Complex: close Elick Lane for 2 weeks and during this time they allowed us to build a temporary drive so they were able to accommodate the large traffic flows that they had on weekends -Holman Motors: requested we put up a temporary fence during construction when we did as a security measure | - Duke Gas Occupying Site/Gas Line Placement: Gas main that was to be relocated. Duke did not get in to do that work until April of 2023 - Storm Sewer Modifications: Sanitary laterals were interfering with the storm sewer. Had to make modifications to 6 runs of storm sewer so that the storm pipe was over the sanitary laterals. - Adjacent Project CLE103954 The adjacent project CLE103954 (Bach Buxton Interchange) had MOT phases that required the intersection of Old 74 and Bach Buxton to be built - Mail Service to Residents along Old 74 Build a frame with several mail boxes on it and place them at the end of the project where mail trucks could easy access them. The contractor built these and we put the mailboxes for the houses on the east of the closure on one frame on the east end of the project, and the western house mail boxes on a frame on the western end of the project. - Concerns of Performing Cement Stabilization Cut the subgrade 6” lower than the plan elevation, proof roll, prescribe undercuts were required, and add an additional 6” of 304 b/c tiller teeth was close to gas lines - Elite Sports Complex Elite Sports Complex had installed drainage that conflicted with out plans, and raise up the surrounding grade approximately 3-4’ and built parking on this raised area. | - The project completion date was 6/1/2024, but the big date to hit for the project was to have the intersection of Old 74 and Bach Buxton open by October 1st 2023 set by the adjacent project CLE103954. Our modified initial phase allowed for us to meet this date. Project was up and fulling functioning by 12-20-2023. In 2024 the permanent striping was done and the permanent signal was installed. | -N/A | - The project completion date was 6/1/2024, but the big date to hit for the project was to have the intersection of Old 74 and Bach Buxton open by October 1st 2023 set by the adjacent project CLE103954. Our modified initial phase allowed for us to meet this date. Project was up and fulling functioning by 12-20-2023. In 2024 the permanent striping was done and the permanent signal was installed. - Partnering played a huge success in this project. ODOT, Jurgensen, and Clermont County Engineer’s Office held to the following partnering goals that were established early on in the project. | - On Time/ On Budget - No Facilitator - Informal Partnering Agreement Attached - 0 Safety Accidents - 1 Early Written Notice - Field offices were right next to each other so a face to face conversation dealing with the project was very easy and in my experience a lot better than an email, text, or phone call. As with most things in life the old school way works for a reason - Held weekly work plan meetings that allowed ODOT to know the plan for the upcoming week and make sure the project was on schedule.
2F | 22-0394 | CUY-480-22.41 | J.D. Williamson Construction Company | Adam Delfs | - Improvement of I-480 over Lee Road (CUY-480-22.41) including replacement of the bridge deck, substructure rehabilitation and replacement of the approach slabs and approach pavement. This also included improvements to the sidewalks and curbs under the structure on CR 8, Lee Road, in the City of Cleveland, Ohio. | - Complete the project without any disputes. Many of the issues that arose in the field, as the project was being built were able to be resolved on the site at the project level - Keep project on schedule by providing the contractor with requested information as timely as possible. JDW proposed two important MOT changes early in the project to expedite the schedule and provide cost savings to ODOT - Deliver the project within reasonable variance of the original estimated cost. Change orders were written to compensate the contractor as outlined in the contract documents for changes to the contract and for damage to maintenance of traffic items damaged by the traveling public. The original contract amount is $10,182,150.00 and the final completion amount is $11,552,586.46, resulting in an approximate increase in cost of 13.5%. - Create a positive team culture in the development, construction, and administration of ODOT’s construction program. The Department was promptly notified of issues that arose during construction, and JDW’s team consistently thought ahead and kept ODOT informed of anticipated issues for forthcoming operations. Frequent meetings were held to further this open line of communication. | - 18 Subcontractors -A&A:A & A Safety performed the MOT for the project. This section of 480 is one of the busiest highway sections in District 12. The zones are long and complex with all the ramps involved. The project appreciates A&A’s diligence to provide a safe work zone - X&J Steel: X&J Steel Construction - The reinforcing steel on the project had its share of issues and X&J was very proactive in identifying potential problems and getting it resolved - Lake Erie Construction: Lake Erie Construction - We lost count of the number of attenuator and guardrail repairs on this project, and they were able to get the repairs made in a timely manner | - 33 RFIs: Deck elevation discrepancy, the Department issued new deck elevation tables and a revised haunch design. Regarding the pier bar installation, the Department added additional quantity to ensure that enough steel was present in these critical areas of the deck. - Delay to an adjacent Project: The delay to the adjacent project made the implementation of the phase 1 maintenance of traffic for this project infeasible JDW made the Department aware of the situation and negotiations on potential solutions began. The Department requested the designer of record, IBI, to produce revised maintenance of traffic drawings - Maintenance of the existing deck before and during construction. This work was included in the contract, but it became evident early on that the items included in the contract would not last. The Project team worked through inclement weather, weekends and nights to make the required repairs. The project team worked together so that the repairs could be made as quickly and efficiently | - The project team worked diligently to resolve all issues that arose in the field verbally or through the RFI process. All verbal and/or early written notices were issued by the Contractor, answered by the Department and resolved immediately, resulting in the project having no disputes or claims - The District proactively included both concrete and asphalt patching items and a related itemized MOT line item in the plans |  | - The safety record for this project was very good. No major injuries were incurred by anyone on the project and/or contracting team. The section of I-480 where this project occurred is one of the busiest highways in the state, servicing approximately 180,000 vehicles per day | - No Partnering Facilitator - 3 Verbal's; 3 Early Written Notices - Jack Ford DRA - The project finished in close conformance with the original milestone of May 31, 2025. The project was extended to August 31, 2025. This was caused by material issues during the 2025 resurfacing that was part of this project - The project has been submitted to the National Asphalt Paving Association (NAPA) for a Quality in Construction Award. Awaiting the results in January 2026. - The project will be submitted to the American Society of Highway Engineers (ASHE) for the 2025 Outstanding Transportation Project Award. Awaiting the results in February 2026.
2G | 22-0442 | LUC-US 24-15.61 | Shelly Company | Brandon Grieve | - IMPROVING VARIOUS SECTIONS IN THE CITY OF MAUMEE, OF LUCAS COUNTY, OHIO, IN ACCORDANCE WITH PLANS AND SPECIFICATIONS BY RESURFACING A 3.58 MILE PORTION OF US 24 FROM JUST WEST OF MONCLOVA ROAD TO THE OHIO TURNPIKE OVERPASS | - Open line of communication between the City of Maumee, The Contractor, The Designer, and ODOT: This goal was achieved by having biweekly progress meetings throughout the project that all parties regularly attended. The Parties also held several onsite meetings to work through any obstacles that arose during the project. | - 16 Subcontractors - The Key Stakeholder, The City of Maumee, contributed to the success of the project by having an open line of communication with the project staff. A City Inspector was available at all times to ensure the City’s desires were communicated to the Department’s staff. Also, decisions were made onsite to address field conditions. | - Staff Changes - City of Maumee - Planted Trees/MUP - Drainage Alignment - Unmarked Waterlines - Traffic understanding the lights at the Conant St. intersection - Unmarked utilities interrupted the installation of storm drainage - Type 2 Curb Conflict - Depth of Fiber Duct Bank - SiteManager vs AWP - Taller Poles - Banner Arms being struck by Traffic - Thermo on Concrete - Light Pole Foundation Placement - No connection between Maumee MUP and Toledo MUP | - Special meetings were also held at the City of Maumee Administrator’s office to resolve issues with the different outlooks held between the City and ODOT. These meetings were held on an as needed basis and were scheduled within 48 hours of a significant disagreement. - Meetings were held internally within ODOT with the Executive Management, including Kacey Young, CPA, and Patrick McColley, DDD, Julie Fahy, PM in Design, Chris Waterfield, TE4 Planning, and the Area Engineer to define the Department’s role as far as ultimate decision making compared to the City of Maumee in relation to issues that could not be agreed upon by the two parties. - Unmarked waterline was hit by the contractor, ODOT had the project first mentality and offered the idea to keep the road way closed(these were only scheduled for nightly closures originally) so that the repair could take place and the contractor could finish the storm crossover. This saved time and money by not filling in the trench the following morning just to be dug out again later that night. | - N/A | - All three teams worked together throughout the project with open, honest dialogue to ensure that the project’s success overshadowed the issues presented during the construction process - Lessons learned from the project are to make sure that each party is looking months ahead towards the next step of the project to ensure that everything will come together appropriately and to head off project delaying issues | - No Partnering Facilitator - 0 Safety Incidents (2 WZ Crashes where drivers ended up behind barrels; incident of a manhole lid that popped off after traffic drove over it. This was property damage only) - 2 Disputes (18" Curb and Spalling Concrete) - Disputes with Maumee (Embankment Material in median, Trees, Type 2 Curb to Type 6, light poles placement with gas lines, banner arms getting struck) - Project was overall delayed due to plan errors, field conditions and tree establishment periods - District 2 also has a best practice of holding a very thorough and in-depth pre-construction meeting where all involved stakeholders, including the consultant designers are invited to participate and each internal (ODOT departments – ex. Survey, PIO, Real Estate, Safety, Maintenance, Materials/Testing, etc.) stakeholder has a slide/opportunity to present to the Contractor/external stakeholders - Kirk Bostelman nominated by District for Individual Award

## Category 3 ($20M+)
Nomination | Project Number | C-R-S | Contractor | ODOT P.E. | Project Description | Goals Established & Achieved | Key Stakeholders/ Relationships Managed | Challenges / Obstacles | Mitigation Efforts | VECP's | How did Partnering add Value | Additional Information
3A | 24-0001 | LAK-US 20-24.99 | Great Lakes | Nate Sheehan | - Major rehabilitation of approximately 3 miles of US20 (North Ridge Road) consisting of roadway widening, new sidewalk, curb and gutter, drainage, new asphalt pavement, and traffic signal improvement. The project began in early spring of 2024 and was substantially complete at the end of the 2025 construction season. MOT patterns consisted of 4 phases including designated short term side street and drive closures to facilitate reconstruction of those areas. | - Safety - Zero Reportable Accidents from Contractor/ODOT - Contractor submitting paperwork timely (material submittals, 611 plan, driveway access plan, shop drawings, work erection plans, and RFIs) - Quality - Less than 15 Engineer’s punchlist items - ODOT reviewing contractor submittals timely - Meeting initial project milestones Development of an accurate CPM baseline schedule, Multiple float paths were generated with each submitted schedule to indicate the float path of the next interim milestone, ODOT reviewing CPM schedules quicker than the PN 107 required - Contractor being proactive in notifying ODOT of all plan work - Completing the project on or under budget - Reduce the number of construction claims and associated cost savings - Complete projects on or before the contract completion date Lookahead schedules and daily crew lists distributed by Contractor to keep ODOT informed of upcoming work | '- 25 Subs, 9 Material Suppliers - Key stakeholders included Madison Township officials, various utility companies, local businesses, and residential property owners - Madison Township officials attended the bi-weekly progress meeting to be informed of upcoming work and to address any concerns the township had. Although the various utilities did not clear their obstructions via the 4A proposal note, they met various times with the project staff and the D12 Utility Coordinator to ensure they were focusing on the critical relocation work to avoid delaying the project. | - Utilities that were not relocated - Utilities that were mismarked or absent from the contract documents - Additional work at Hubbard Road was significant from a schedule and cost perspective and included locating existing utility to verify conflict with proposed storm sewer, including exploratory excavation - A plan error was found within the cross sections and corresponding end area calculations regarding excavation and embankment quantities. (Escrow Bid Docs) - After excavating the existing pavement for Phase 1 Hubbard Road work, a drop-off exceeding 1 foot was realized (Stone wedge placed) - The trench for widening and overnight trench closing indicated a maximum 5” drop-off below the existing pavement (to avoid the installation of barrier wall in these sections, and RFI was submitted and approved to slightly relocate the phaseline which increased the distance to adjacent traveled lane and subsequently achieved compliance with MT101-90 without barrier wall.) - Utility company was required to support existing poles during proposed drainage construction | - All disputes were resolved within the Step 1 process. As issues were being resolved the Dispute Resolution Board was notified and kept abreast of the issues in case an advisory opinion or formal dispute process was going to be needed. - Regarding the excavation/temp excavation quantity issue an RFI was submitted to clarify quantity calculation methodology. The RFI led to ongoing discussions regarding designer calculations and interpretation of the contract documents. - The willingness of both sides to open escrow and the constant and ongoing communication regarding this issue led to an agreement on quantities prior to a DRB Advisory or Step 2 claim. | N/A | The project team demonstrated that partnering works by completing the project on time, having zero claims, completing project for nearly the bid price ($13,111.80 overage), and having a great professional rapport with all involved stakeholder - An initial partnering session was held after the preconstruction meeting, resulting in the generation of a partnering charter that memorialized goals, responsibilities, chain of command, and expectations from both ODOT and the contractor. - Providing an accurate baseline and timely updates including time impact analyses allowed the project team to have a precise way to track the project and see if it was on time. | - No Partnering Facilitator - Returning Champion in Great Lakes/ Matt DeSapri - Barely into Category #3 at $24,794,727.39 - End of the year cookouts were held as an informal post construction meeting to discuss the successes and challenges the project experienced. - No reportable safety issues - 3 Verbal's; 1 Early Written Notice - PN420 positive pay adjustments have been made for the asphalt pavement - Partnering Meetings Minutes Attached
3B | 203000 | HAM-74-18.01 | Great Lakes (ELR) DBT | Chris Tuminello | - The HAM-74 Mill Creek Expressway Phase 5B project (PID 104668) is a complex urban Design-Build interchange reconstruction located at the I-74 / I-75 system interchange in Cincinnati, Ohio. The project is two miles long and includes construction of a nine-span curved steel flyover bridge crossing five CSX and Norfolk Southern railroad tracks and a U.S. Army Corps of Engineers (USACE) flood control channel, one mile of third lane widening primarily supported by MSE wall, rehabilitation and/or reconstruction of nine bridges, extensive roadway reconstruction, and maintenance of traffic through one of the most heavily traveled corridors in Ohio. | - Goal: Completion Date of 2025 - Goal: Hit Major Phase Switch Milestone Dates - Goal: Zero Recordable and Zero Lost Time Incidents - Goal: Innovation (ATCs/VECPS) - Goal: Minimal Rework/Quality Work - Goal: Fair profit - Goal: Workforce Development - Goal: Positive Environment | - 48 Subcontractors - CSX and Norfolk Southern: Through joint workshops and iterative reviews, the team secured approvals for VECP 3000-S-051 (Railroad Splice Elimination), reducing erection complexity over live tracks and lowering flagging risk. There were ZERO delays to the project related to railroads. - Utilities: Duke Energy (Power and Gas), Cincinnati Bell, Spectrum, Charter, Qwest/CenturyLink, Sprint, MSD, Verizon, GCWW, T-Mobile, and the City of Cincinnati. Through collaborative design revisions (ODOT + Great Lakes + E.L. Robinson + utility owners) and a shared Utility Conflict Matrix, three relocations (Duke Power, Duke Gas, and T-Mobile) were avoided. There were ZERO schedule delays to the project due to utilities. - City of Cincinnati and local stakeholders - USACE: The Design-Build contract uniquely required the contractor to lead USACE Section 408 and 404 permitting. Ultimately, this 18-month process was completed in less than 12 months resulting in ZERO delays to the project. | - Complex MOT sequencing in a constrained urban interchange with high traffic volumes The team reduced risk by pursuing a Texas Turnaround strategy and by converting planned intermittent impacts into defined closure windows with enforceable constraints - Five railroad tracks (CSX and Norfolk Southern) below a new bridge requiring design and construction. The team minimized railroad exposure through BU sequencing, early railroad engagement, and VECP 3000-S-051, which eliminated a splice over live tracks and simplified erection and approvals. - 27 Utility Conflicts - Contractor-led USACE 408/404 permitting on the critical path and FHWA (IMS Revisions).With collaboration from the Designer, GLC, ODOT, and the USACE, the project was able to get through the permitting process very quickly avoiding any delays. - Schedule Risk due to COVID Supply Chain Volatility, Railroads, USACE, FHWA, and Utility conflict risk. The Beekman detour and Montana Avenue Texas Turnaround decoupled traffic operations from structure construction, allowing the team to mitigate risks associated with third-party review durations and fabrication challenges. This change eliminated MOT phases and added six months of float to all critical path activities. - Adjacent Projects, Field Conditions (Full Depth Rigid Pavement Removal), Concrete Median Caps, AWP Conversion, Barrier Concrete Sealing on MSE Walls and Slab Barrier Walls, Surveying and GLC Mill and Fill | -RFI 058 – Roadway Barrier and Concrete Cap Scope is a clear example of effective partnering in action. Differing interpretations of Design-Build contract requirements created the potential for a formal dispute with cost and schedule exposure - Rather than escalating the issue, ODOT, Great Lakes, and E.L. Robinson worked collaboratively to document intent, review technical details, and reach an agreement. -Early alignment submittals (e.g., BU #1A conceptual MOT) to secure concurrence before full design. -BU strategy (35 BUs) to isolate risk and prevent third-party reviews from blocking unrelated work. - Over-the-shoulder design reviews to reduce formal rejections and minimize rework cycles. | - VECP 3000-S-051 (Railroad Splice Elimination): Final approved submission documents total guaranteed savings of $132,551.72 and reduced railroad erection risk and flagging exposure - VECP 3000-S-020R1 (Beekman Closures / Montana Avenue Texas Turnaround). This VECP was originally submitted with $150,000 of guaranteed savings. - ATC 3.1. Eliminated multiple MSE walls and a bridge over five railroad tracks. This saved the project several million dollars. | - Initial facilitated partnering workshop (Lair Learning Alliance). Partnering Reconnects were held on February 15, 2024, and March 22, 2023. See attached Meeting Agendas/Minutes. HAM-74-1909 flyover bridge ribbon cutting with GLC/ODOT/Omnipro team prior to opening to traffic. Joint MOT planning / conceptual alignment activities (BU #1A conceptual MOT submittal). Joint design workshops and over-the-shoulder review sessions between ODOT, Great Lakes, and E.L. Robinson. Recurring stakeholder coordination meetings (railroads, utilities, City, USACE). - Most valuable asset for the Team was the onsite cooperative attitudes of the project management staff and workforce personnel to move the project forward by collaboratively solving problems in real time. This Team took great pride in knowing that the end result of a quality project was well worth the effort. | - Partnering Facilitator - Mike Lair - 0 Lost Time Work Incidents - DRB: Tom Hyland, P.E., Don Gregory, and Jack Ford - 36 Verbal's, 15 Early Written, 0 Step 2s (Backwall Construction Joint Locations, Pavement Joint Lapping, Bridge Punch List Work, and Soldier Pile Lagging Wall 13)
3C | 24-0042 | PAU/DEF-US 24-12.30/0.00 | Miller Bros. | Ryan Wisniewski | - For Part 1 this project consisted of the rehabilitation of 10.61 miles of US 24 pavement and the ramps at the US 127 and Baltimore St. Interchanges, by crack and seating the existing concrete and placing 7.25” of asphalt concrete pavement and 3” overlay of waterproofing asphalt on the mainline bridge decks. - For Part 2, we performed two slide repairs by reconstruction and benching the embankment along US 127, at the eastbound entrance ramp to US 24 (Ramp D), and along US 24 eastbound | - Any existing Concrete Pavement that was cracked needed to be paved up to intermediate before winter shutdown. MBC really had to schedule out how far they could go in one year to follow this plan note. Which is when they propose to do three sections at different times, not just one whole 11-mile-long work zone. By splitting the project work area into three separate sections this allowed the contractor to achieve this goal and at the same time have less impact on the traveling public. This also basically completed roughly 7 miles of US 24 in both directions up to the intermediate asphalt course. Quality work and product Good communication Complete project on time or within reason Complete project within budget Overcome a new construction challenge, i.e. Crack and Seat. First project of its kind for District 1 as well as MBC Have adequate safe traffic zones Manage sub-contractors’ activities and their schedules Communicate with ODOT Defiance and Paulding Counties | - 21 Subcontractors - Gerken Paving was a key subcontractor that drove the schedule on this project. With out the long 4,000-ton production days this project could of really went past the original work completion date. - Aggregate availability for the over 143,000 CY of asphalt on this project was something Gerken and MBC had to work through throughout the entire project. MBC & Gerken worked on schedules constantly with the local quarries and plants to stay on schedule | - MOT, the traveling public speed, distracted drivers - Existing Gas Lines running underneath road - Existing poor sub-grade conditions - Poor existing Concrete Pavement Conditions - Several small slope failures throughout existing US24 - Larger existing slope failure & existing damaged lighting - This was the first Crack & Seat project to be sold within District 1 - Projects proximity to aggregate quarries and asphalt plants. - Limited temporary right-of-way at the two slide repair projects - Approximately 11-mile construction zones on EB & WB US24 | - A high level of informal partnering and respect was established early on in the project. If there was a problem ODOT & MBC always handled it at the lowest level. It’s one of those projects that every team member & stakeholder can be proud of. - Formal partnering meetings were not held, but we held biweekly and then monthly progress meetings | - N/A | - Team Building: At the end of the 2024 season when MBC was completed with the two slide repairs on the project, MBC held a celebration event at the borrow site for the dirt import on the slide repairs. MBC had added on to an existing pond, so MBC invited ODOT to watch the dike excavated between the two ponds. Both parties took guesses on how much the existing water elevation would drop. - A high level of informal partnering and respect was established early on in the project. If there was a problem ODOT & MBC always handled it at the lowest level. It’s one of those projects that every team member & stakeholder can be proud of. | - No Partnering Facilitator - On Budget/ On Time - No Safety Incidents - 0 Early Written Notices, ) Verbal's - Project received a $385,236.47 PN420 Smoothness Adjustment and a combined Mat/Joint 447 Density Adjustment of $252962.70. - MBC Project Manager went into labor and had a baby boy on the day of the pre-construction meeting for this project! - Lessons Learned: contracted work may not take as long as anticipated but always keep in mind the availability of materials on large scale projects
3D | 21-3000 | SUM-76-8.24/9.74/8-0.00 | RSS JV | Raymond Fridley | - Part 1 - Full depth pavement replacement on the IR-76 and IR-77 mainline and ramps for the entire project length with the exception that the ramps at the Northwest Interchange (IR-76/IR-77) where they are being resurfaced. All shoulders will be replaced with the same composition and build-up as the mainline pavement. In addition, SR-8 will be resurfaced within the Project Limits, capacity improvements will occur on the southbound side between Carroll Street on-ramp and Beacon Street - Part 2, which is the Akron Central Interchange includes reconstruction of IR-76 EB/WB pavement | - Build a project that is safe for the workforce and the traveling public Construct the project so that it will last and serve the public interest Safety First — No Lost Time Accidents Complete the project on time and on budget Treat the environment with respect Resolve issues respectfully and timely Resolve issues at the levels closest to the project consistent with levels of authority Seriously consider all alternative viewpoints Partner with all stakeholders, including the public, local government, utilities, and the bus/transit system Trust and respect each other and all the partners on the project Focus on the "project first," with an attitude of success and fairness Responsibly mitigate the impact of issues as they arise Manage the project so it is fully transparent and meets all real and perceived legal standards Build a quality project of which we are proud Communicate openly and effectively Empower our people to use and enforce these principles | - 25 Subcontractors - The Project had approximately 25 Subcontractors working on The Project at some point in time. Most of the time several Subcontractors were working in the same area as project phasing allowed. - The City of Akron and Akron METRO Regional Transit Authority were heavily involved in the maintenance of traffic efforts to ensure the traveling public navigated throughout the City of Akron effortlessly. Weekly Maintenance of Traffic emails were sent throughout the Project duration, and the stakeholders had the opportunity to review and ask questions about the upcoming work zones. For larger traffic impacts The Project held meetings with both the City of Akron and Akron METRO for their opportunity to review and comment as needed. Adjustments would be made accordingly to limit the impacts as best as possible - The Project held three Traffic Incident Management (TIM) Program meetings with all stakeholders involved who wanted to take part in the meeting and provide their thoughts, comments, and questions. | - 2022 Epoxy Shortage Impacts/ Labor & Worker Shortage - East Avenue, SUM-76-0876, Pier Replacement – September 2021 - I-76 Westbound/Northbound Asphalt Failures on Lakeshore, Bowery, and Manchester Bridge Decks and Roadway – January 2022 – April 2022 - Ex Asphalt Pavement Failures along I-76 EB from East Avenue Bridge to Princeton Street Bridge – Dec 2021 – Feb 2022 - I-76 Westbound Bridge Deck Failures over Inman Street, SUM-76-1179R - Working 23 Hours a Day 6 Days a Week. No Winters off. Phasing Changes throughout the year. - Stolen Skid Steer and Wire Theft - Maintenance of Traffic Zones; 80 Attenuators Replaced - Local Ramp Closures and working near houses and businesses - Utility Conflicts - East Avenue Acceleration Ramp to I-76 Eastbound Redesign - SUM-76-1151L - Beam Seat Reconstruction - 77 Southbound Deceleration Ramp to Waterloo Road - Underground Storage Tanks Uncovered and Removal - Transitioned from Site Manager to AASHTOWARE Project on 7/11/2024 | - Project staff continued to host both informal and formal meetings to mitigate the risk and notify all parties involved of The Projects intent of work to be performed. All levels of the Project met to discuss mitigative efforts amongst themselves and other field staff to ensure correct measures were taken for The Projects continued success. In the event an issue was raised, a Request for Information was generated, an email populated, or a conversation was had to ensure proper protocols were fulfilled to mitigate impacts. | - Value Engineering 001: 63” Pipe Lining vs. Replacement Cost Savings Split Between ODOT and RSS = $465,455.45 Value Engineering 002: Wall 12/Sewer Conflict: Cost Savings Split Between ODOT and RSS = $592,276.61 - A good example of partnering are the VECP’s that were approved and the East Avenue Redesign that we had mentioned in the challenges section of this nomination. The Department approached The Contractor to modify our current approved ramp L design to accommodate a future Project | - Throughout the duration of the project, the Ruhlin / Shelly & Sands JV team employed a Site Safety Specialist to lead and direct a positive safety culture among the project staff. This individual managed safety training for all staff, ensured staff had the proper safety supplies for the work at hand and provided valuable insight for planning work at weekly project coordination meetings - Partnering during design added value to not hold any thoughts, comments, and/or ideas back to save both time and money. The Design Build Team and The Department worked in unison together and understood the tight timelines involved and kept the Project moving forward - | - Partnering Facilitator: Scott Slack - Parsons Design Lead - Fernando Rodriguez - Nearly 1 Year ahead of Schedule - See "Mission Statement" Page 6 - Akron Beltway Project hosted a Partnering Golf Outing at Turkeyfoot Lake Golk Links in Akron, Ohio. This gave the project staff the opportunity to meet each other outside of the office environment to get to know one another; Ruhlin/ Shelly and Sands hosted a luncheon at the Field Office Garage; Ruhlin/Shelly and Sands rented a taco food truck at their work yard for everyone on The Project to come and enjoy - 1 Verbal; 2 Early Written Notices - Official Partnering Meetings - The Project was unique as it was both a Design Build Project and Design, Bid, Build Project in one, some like to refer to it as a hybrid project - 55,000 CY in concrete poured, 280,000 SY of cement stabilization performed, 200,000 Ton of 304 aggregate base, 320,000 Ton of asphalt, 45 Bridges maintained, 3 new bridges.
3E | 220256 | LUC-475-1.85 | Kokosing | Mike Benton/Dan Kelsey | - New interchange at IR475/USR20A, the removal and replacement of IR475 and the addition of a third lane between The Maumee River and Airport Hwy. - Bridge work included a new structure for USR20A over IR475 and a rebuilt structure for IR475 over the CSX railroad - Collector-distributor lane was constructed for the combination of the new USR20A interchange and the existing Salisbury Rd./Dussel Dr. interchange. - New drainage, new highway lighting, sound barriers and associated safety items were also constructed as part of the project | - Formal goals were not established but the project team agreed early in the project that a ‘solutions first’ approach would be taken. This meant that the team would work together to solve problems and not dwell on assessing blame. | - 37 Subcontractors - Subcontractors and key stakeholders complemented each other and supported the team concept rather than working independently - Lake Erie Construction expressed an interest in adopting a new approach to installing cable rail post foundations and no mow strip. This process required significant coordination between Lake Erie and Kokosing, but that collaboration resulted in a higher-quality product installed with greater efficiency | - The phasing of the two proposed structures at U.S. 20A over I-475 conflicted with the proposed I-475 MOT scheme and the alignment of the existing structure. (Decided to build parts of the WB U.S. 20A structure out of phase to maintain traffic on U.S. 20A as long as possible and minimize the impact to the local communities and traveling public) - The proposed SB I-475 construction phase included the closure of two ramps from U.S.24 to I-475 for the duration of the phase (Utilizing additional temporary pavement, the project team members were able to redesign the phasing closing each of the four US 24 ramps for short durations and eliminated the need for full duration closures as per plan.) - The ramps of the Dussel Dr. interchange and the Airport Hwy. interchange remained open the majority of project. The MOT scheme tried to allow for the completion of all the proposed work but unfortunately there were several areas of work that could not be performed without redesigning the phasing and/or geometry of the temporary ramps. (The project and the contractor worked together to solve these problems. Solutions included layout changes, phasing changes, short-term closures with focused work and work type changes.) - Industry Wide Cement Shortage (critical for the project to complete the temporary/permanent pavement on SB I475 so traffic could be placed in a bi-directional scheme and bridge work could begin over the winter months... See Mitigation Efforts) | - Cement Shortage The issue surfaced on August 31, 2022 The team explored multiple stabilization options: 1.Cement Stabilization: Proposed but ruled out due to cement shortage. 2.Lime Stabilization: Tested but found ineffective in improving soil strength. 3.Cement-Lime Mix: Rejected due to lack of testing and precedent concerns. 4.Global Undercut: Proposed with a cost increase of $335,000. 5. Modified Pavement Section: Ultimately accepted, additional excavation of 7” of subgrade, proof rolling, and adding 7” of 304 aggregate base. ODOT District 2 personnel worked with Kokosing Construction and the Office of Pavement Engineering to evaluate alternatives, share test results, and align on a solution. The team coordinated field visits, adjusted schedules and maintained open communications across departments. | - VECP #1:Change temporary pavement to permanent pavement. GMS = $1,948,472.96 Time Savings = 28 days with a value of $86,800 VECP #2:Change LUC-475-0093 L/R from the proposed 3-span structure to a single span. GMS = $620,662.86 Time Savings = 0 days but mitigated potential delays by minimizing interaction with the railroad and utilities located on railroad R/W. | - Cleaning out the existing No. 4 Inlets - Crux of the issue came from the size of the maintenance door and the location of the outlet in need of jetting. The equipment used to clean the inlets could not turn twice, essentially creating a ‘U’, to reach the outlet located under the access door. - To solve this problem an extension to the inlet box was fabricated and attached to allow access to the outlet pipe. The extension was pre-cast and attached with through bolts. The extension basically mimics a No. 3 Inlet - To minimize the cost and complexity of the work the project team essentially designed the modifications on a “bar napkin”. Marked up Standard Construction Drawings were provided to the contractor and then he worked with the pre-cast supplier to come up with drawings used to fabricate the “boxes” added to the existing inlets - The initial estimate of cost for modifying 9 median inlets was $625,000. The actual cost ended up being $160,500 | - No Partnering Facilitator - Safety: Total number of Recordable Injuries = 3 Total Recordable Incident Rate = 2.38 Days Away Restricted Transfer (Lost Time) = 1.59 - 0 Early Written Notices - Partnering Approach: "The Project probably took a more old school approach in that all members of the team focused on a solution first approach. We communicated openly and maintained respect for other members and their viewpoints. Partnering is not rocket science. It’s just communication. Listen to learn rather than listening to respond."
3F | 21-0591 | CLE-32-3.50 | John R Jurgensen | Josh Bradford and Jason Haus | - Constructing a new interchange at SR-32 and Bach Buxton Road: which includes constructing a new bridge, realigning and widening roadway, paving, applying pavement markings, upgrading signs, signals, and lighting, and performing all related work along SR-32 and nearby streets. -This project was part of an 8 phase project to improve the corridor of EB and WB 32 Between IR-275 and Stonelick Olive Branch Road. The 8 phases were constructed out of sequence which caused issues with the MOT of this project. - Bach Buxton Road, which is a road maintained by Clermont County, was realigned to now be the bridge that goes over SR 32, whereas previously it intersected with SR 32. | - Develop a work environment that promotes mutual respect - Maintain a safe project work site - Build the project on time and within budget - Minimize inconvenience to the traveling public - Maximize public value and contractor profitability - Keep the project first while solving issues - Seek opportunies for VECP - Elevate safety discussions - Every project successful, including adjacent projects - Be proud of the finished project -Be a quality product | - 23 Subcontractors - The Clermont County Engineer’s Office was a critical partner in the successful delivery of this project. They worked collaboratively with ODOT and the contractor through all major maintenance of traffic (MOT) phase changes. - The County further supported partnering efforts by hosting multiple coordination meetings at their Batavia office - The District 08 Public Information Office (PIO), in coordination with ODOT construction staff, played a key role in supporting project partnering by proactively communicating all maintenance of traffic (MOT) changes to the public. - Scott Kraus worked collaboratively with the contractor and ODOT construction staff to develop and refine MOT phasing required due to surrounding infrastructure not yet being in place. Through a workshop-style approach, alternative concepts were evaluated and implemented to maintain traffic flow while accommodating changing field conditions - Marc Grake , District Traffic Engineer, supported project partnering by modifying impacted traffic signal operations during MOT phase changes to optimize traffic flow - The Ohio Department of Natural Resources (ODNR) partnered with the project team to address initial concerns related to the Glen Willow Lake dam being undersized. - The Union Township Fire Department worked closely with the project team throughout multiple MOT phase changes and roadway closures over the three construction seasons. - Holman Motors and Jeff Wyler Auto Mall, Tractor Supply, Eastgate Woods Apartment Complex | - Existing Grade Elevation Busts & Survey Challenges: Throughout the project, significant and recurring survey discrepancies were encountered. Existing pavement elevation was 3 to 6 inches lower than indicated in the contract plans, with isolated locations deviating by up to 10 inches. Approximately 2,000 cubic yards of asphalt beyond the original estimates. J - MOT Phasing and Multi-Part Plan sets The SR 32 corridor included several projects that overlapped with or were adjacent to ODOT Project 210591. This project was advertised as a three-part project because it combined three separately designed projects into a single contract. These parts were not explicitly linked by a defined construction sequence. Adjacent projects also significantly contributed to conflicts, particularly related to MOT. For example, the MOT plans assumed the intersection of Bach Buxton Road and Old SR 74 had already been constructed - AWP Migration - Adjacent Projects: ODOT, JRJ, and the adjacent project team worked collaboratively to modify phasing strategies and minimize impacts to the traveling public. - Survey Asbestos Delay: On January 12, 2022, JRJ submitted an RFI regarding asbestos surveys that were not included in the contract documents. This RFI resulted in a schedule delay due to the need to abate asbestos from several properties located within the footprint. JRJ submitted a Time Impact Analysis requesting a 58-day time extension along with delay compensation - 48" Pipe Failure: JRJ installed a 48-inch storm sewer pipe that exhibited deflection and sag beyond the allowable specification. The pipe, located approximately 20 to 25 feet below grade and several hundred feet north of the Bach Buxton Bridge. The DRB provided a verbal recommendation that the issue should be shared. | - All major disputes were discussed verbally before an email was written. Many of these discussions were face to face at a weekly work plan meeting or by just walking over to the JRJ/ODOT field offices that were next door to each other. - The level of communication between the contractor and ODOT on this project was the best experienced on any ODOT project. This success can largely be attributed to the clear goals established during the initial partnering meeting. Having the ODOT and contractor field offices located next to each other fostered a strong working relationship. - Field offices were right next to each other so a face to face conversation dealing with the project was very easy and in my experience a lot better than an email, text, or phone call. As with most things in life the old school way works for a reason. | - N/A | - On April 7, 2022, ODOT hosted a project kickoff meeting with local stakeholders at the jobsite near the future Bach Buxton forward abutment. - On August 8, 2023, ODOT and JRJ jointly hosted a local stakeholders meeting to inform the public and respond to questions regarding upcoming roadway openings and closures. - JRJ hosted a Pull Planning session on March 9, 2023, bringing together project leadership to collaboratively plan the 2023 construction season. A Pull Planning meeting is a collaborative scheduling exercise in which the team works backward from key milestones to define activity sequencing and durations - Throughout the construction season, weekly work plan meetings were held every Wednesday to review planned activities for the upcoming two weeks | - No Facilitator; Chris Kunz and Jason Haus facilitated a formal partnering meeting at the Clermont County Engineer’s Office - Partnering Meeting Minutes and Project Specific Goals; Partnering Recap Meetings - 0 Work site safety incidents - 6 Verbal's; 6 Early Written - Field Office located close together
3G | 22-0366 | MOT-75-06.86 | Barrett Paving Materials | Jackie Nicol | - Reconstructs 2.68 miles of Interstate 75 south of Dayton in Montgomery Co. with improvements including new pavement, storm sewers, lighting, median barrier wall replacement, median inlets, guardrail, and minor bridge repairs. | - Safety: Goal Zero – No loss time injuries to contractor or inspection staff; redesign of maintenance of traffic (MOT) patterns by Barrett eliminated a plan traffic split, thus reducing motorist confusion and potential resulting accidents. - Quality: No Rework; Barrett achieved the Item 447 asphalt density bonus with the potential to earn the PN 420 smoothness bonus as well - Schedule: On-time; Timely closeout - Budget At or under budget...At time of application, projected final costs are absolutely anticipated to be within the 2% of original contract amount; Contractor profitable | - 25 Subcontractors - Contractor held weekly work plan meetings with major subcontractors willingly participating. The group scheduled for the short term (i.e. 1-3 weeks ahead) and long term (i.e. entire phase), and often anticipated material needs per phase - Law enforcement blitzes helped to improve safety with periodic speed enforcement with participation from multiple agencies - Subcontractor- Security Fence welcomed the weekly standing single lane closures on Thursday nights to perform non-emergency accident repairs throughout the work zone - Multiple stakeholders participated in discussions about upcoming maintenance of traffic pattern changes | - Managing a 5-mile-long contraflow lane in a corridor carrying 117,000 vehicles daily: Installed emergency access gate… District 7 proactively closed I-75 S to Dryden Rd off-ramp four weeks into the project due to concerns with reduced deceleration lane width and length before entering the circle ramp... Painted WZ Air Speed Markings at the request of the Ohio State Patrol... Placed temporary thermoplastic rumble strips to notify and ideally slow down traffic...Erected additional truck lane use signs...Participated in the research project to observe motorist behavior where haul trucks enter/exit the work zone... etc. - Conflicting projects: Although the Coordination of Adjacent Projects plan note only mentioned two projects to be aware of, in the end 7 projects were in conflict with the zone throughout the life of the project... Projects including Highway Lighting Optimization (22-431), Bridge scouring at structure MOT-75-6.86 (23-463), SR 741 ramp resurfacing (25-306), and ITS camera replacements (25-030) ... The northern I-75 Dayton rehab (23-0039) project was located within pavement markings on 22-366, the 23-0039 traffic queue extended into 22-366 work zone, resulting in work hour adjustments to avoid conflicts - An overestimation of Item 519 deck patching quantities resulted in $1.6M of non-performed DBE work—3% of the project’s 8% DBE goal - A vehicle accident damaged the median bridge parapet over railroad tracks, requiring Norfolk Southern involvement and delaying repairs for five months due to submittal approvals, flagger availability, and completion of Phase 5 MOT. - Phase 1 Profile adjustment, Surface asphalt material production, joint failures, over 250 traffic accidents, AWP transition, underdrain plans, NATO Summit in May 2025 & LEOs, ITS conduit Extra Work | - Annual Partnering Reconnect Sessions… April 17, 2024: The team enjoyed a casual lunch featuring Chick-fil-A and cupcakes from Pastries by George, a local Cincinnati favorite...April 9, 2025: Following a progress meeting and discussion of the anticipated final paving schedule, the team celebrated with pizza and homemade treats - Collaborative Safety and Communication Meetings The Project Team fostered strong partnerships and proactive communication through Traffic Incident Management (TIM) and After Action Review (AAR) meetings. These sessions brought together all levels of project management, local government agencies, and key community stakeholders - Phase 1–2 Profile Adjustment at Existing Median Wall A virtual meeting was convened with the Designer of Record (DOR), ODOT District 7 Design, ODOT project management, and Barrett. This inclusive session allowed decisionmakers to review images and clarify the issue in real time - ITS Microduct Shrinkage - collaborative attacked by the Project Team | - No official Value Engineering (VE) Change Proposals were submitted for this project. While revising the MOT plan, the team determined that pursuing an official VE process under Supplement 1113 would have delayed the Phase 1 traffic switch. To avoid schedule impacts and ensure timely progress, ODOT and the contractor collaboratively agreed to implement Barrett’s revised MOT plans and compensate for the work as installed. This approach prioritized project efficiency and minimized potential delays, even though it did not generate formal VE savings. | - Instrumental MOT Phase Revision: Barrett proposed revising the original MOT plan, and the Department expedited review to implement the change - Early Commitment to Partnering: The very first change order established the missing line items for PN 108 – Dispute Resolution Board Process and PLN 111 – Facilitated - Streamlined Issue Resolution: Before the pre-construction meeting, Barrett proactively submitted 12 RFIs to address design and constructability concerns early - Joint Decision for Safer, Cost-Effective Design - Collaborative Safety Enhancements - Shared Efforts to Mitigate Delays and Accelerate Work - Proactive Design Adjustments for Safety - Cost Savings Through Cooperative Design Revisions - Joint Recognition and Continuous Improvement - Open Scheduling and Transparency | - Facilitator: Jack Ford - On time; On budget - Zero loss-time injuries among the prime construction crew covering more than 75,000 work hours (Three fatalities occurred within project limits; however, they were not related to the work zone or construction activities.) - 2 Early Written Notices - Best Practices/ Lessons Learned Dedicated Repair Windows Added Crossover Design Improved Surface Rideability Proactive Quantity Management User-Centric Perspective Streamlined Cost Tracking: Developed specific cost codes for each force account item, referenced in ODOT change orders for quick, transparent tracking Improved Surface Rideability: Addressed natural phased construction crown challenges by adding extra asphalt surface mix for consistent placement of the final course and using a multiplex mill to profile lanes
3H | 230244 | TRU-46/82-DDI | A.P. O’Horo Company | Kurtis Brzyscz | - Construction of Diverging Diamond Interchange (DDI) at the State Route 46 and State Route 82 interchange in Trumbull County, Ohio. Project also includes the replacement of the SR82 Structure (SFN# 7804652) over State Route 46. | - The primary project goal was to place the Diverging Diamond Interchange into its final traffic configuration prior to the 2025 Christmas shopping season to minimize impacts to one of the region’s highest-volume retail corridors. This goal was successfully achieved when the interchange was opened to full, final traffic on October 10, 2025, more than nine months ahead of the original July 31, 2026 completion date. - A secondary goal was to minimize construction impacts to adjacent businesses and stakeholders. This was achieved through proactive coordination with the Eastwood Mall Development, Howland Township, Trumbull County, and individual business owners, ensuring access was maintained and communication remained consistent throughout construction. | - Key stakeholders, including the Eastwood Mall Complex, Howland Township, and the Trumbull County Sanitary Engineer, also contributed significantly to project success Subcontractors: As project phasing was re-evaluated and revised, subcontractors were actively engaged to assess feasibility, sequencing impacts, and resource availability. Their willingness to adjust schedules, re-sequence work, and commit resources under evolving conditions was instrumental in achieving the project’s early traffic milestones | - Stormwater Maintenance and Design Revisions: During early construction phases, the Contractor identified concerns regarding the ability to maintain adequate drainage while implementing the proposed storm sewer system and maintaining complex traffic patterns. ODOT promptly acknowledged these concerns and worked collaboratively with A.P. O’Horo and HDR Engineering to modify project phasing, drainage design elements, and maintenance-of-traffic concepts. - Construction Phasing and Re-Sequencing: As construction progressed, the original phasing plan was found to significantly impact traffic movements serving the Eastwood Mall Complex during peak holiday shopping periods. Recognizing the magnitude of this impact, ODOT and A.P. O’Horo jointly discontinued the affected traffic restriction and immediately began developing an alternative phasing strategy. - Structure Demolition and Safety: Prior to demolition of the existing SR82 structure over SR46, the Contractor raised serious safety concerns related to maintaining live traffic beneath demolition operations. Rather than proceeding under the original maintenance-of-traffic assumptions, ODOT and A.P. O’Horo collaboratively explored safer alternatives. The project team implemented a short-duration full closure of SR46, allowing demolition activities to be completed safely and efficiently - Utility Coordination: Utility relocations—including gas, water, electric, and communications—presented recurring challenges throughout construction. Relocation efforts extended from pre-construction through final project phases and periodically impacted the critical path. ODOT and A.P. O’Horo maintained continuous coordination with utility owners to resolve conflicts, re-sequence work, and mitigate delays | - ODOT and A.P. O’Horo emphasized early and continuous communication as a primary mitigation strategy. - Potential issues were discussed openly as they arose, allowing the project team to jointly evaluate impacts and implement solutions before they developed into claims or disputes - Project conducted regular progress meetings between ODOT and the Contractor, which served as a useful tool for identifying/discussing issues from both party’s perspective. The Engineer and the Superintendent also made efforts to routinely communicate various project matters to keep underlying/potential issues from festering into major issues later. | - None | - Partnering was fundamental to the success of this project. The complexity of the interchange, the high-volume traffic environment, and the number of significant challenges encountered would have made achieving the original completion date difficult under traditional project delivery dynamics. - The team also learned that empowering field-level staff to raise concerns and propose solutions—particularly related to safety—leads to better outcomes than strict adherence to original plans | - No Facilitators - Original Bid: $20,442,000.00 (Just ove $20M from category #2) - No Early Written Notices - PN 109 but Advisor not uitlized - Regular Progress Meetings - The diverging diamond interchange was opened to fully functioning traffic nine (9) months ahead of schedule.