CLE - SR 32 - 03.50 (Part 1, 2, 3 )

ODOT PROJECT 21-0591

ODOT -  JR Jurgensen Company

DRB INITIAL MEETING AGENDA

Date:     07/19/22					Meeting Number:    001

Original Completion Date:    08/01/24   		Revised:     None

Original Contract Amount:   $42,465,290.87		Revised Amount:  $42,642,266.56

Amount Earned To Date:   $4,838,540.45		% Complete By $:   11.39%

% Complete By Time: (148/893) = 16.5%

- Introduction

- Name, Affiliation, Role

- Sign-Up Sheet

- ODOT and JRJ Point of Contact with email

ODOT:___________________________________

JRJ:_______________________________

- Overview of DRB Process:

- Quarterly Meetings

- Meetings Informal

- DRB Purpose

- No Ex-Parte discussions of issues

- DRB Operating and Hearing Procedures –  Comments

- DRB Monthly Information Packets

- Information to be Included:

- Forwarded to DRB in a Timely Manner

- Use of ODOT SHPT

- ODOT - Project Overview

- Scope

- Significant Project Details

- Critical Activities, Specifications

- Milestone Dates

- Risk Registry developed?

- Issues and Challenges

- JRJ -  Project Overview

- Scope

- Planning and Sequencing

- Phasing

- Detours

- Structures

- MSE Walls

- Noisewalls

- Fills / Soil Conditions

- Roadway Items

- Maint. of Traffic

- Other

- Issues and Challenges

- Utilities

- Right-of-Way

  - Reg. Material mitigation

- 3rd Party coordination

- Other

- Current Project Status ( JRJ with ODOT Comments)

- Progress-to-Date

- Any Technical Issues

- Any Delays

- Project Schedule (JRJ with ODOT Comments)

- Approved Schedule status

- Key Milestones to note

- Critical Path Delays:

- Non-Critical Path Delays

- Three Month Look-Ahead

- Time Extensions, If Any

- Status of Key Submittals (JRJ with ODOT Comments)

- Issues, If Any

- Status of RFIs (ODOT with JRJ Comments)

- Quality Issues or Kudos,   (ODOT with JRJ Comments)

- Change Order Status (All)

- Amount Approved To Date

- Amount Pending

- Potential Disputes  (All)

- Safety Issues (All)

- Project Personnel

- Traveling Public

- Public Complaints/Comments (All)

- Any Other Topics

- Invoicing Point of Contact:____________________

- Set Next Two DRB Meeting Dates

- Joint Site Tour w/ at least 1 ODOT and 1 JRJ party accompanying

- Adjourn