21-0591 Partnering Session 3-24-22

Phase coordination w/ Complete General (ODOT project 22-0039 (PHASE 10))

- ODOT is modifying both projects in order to resolve the conflicts

  - 22-0039

    - non-perform the small section that requires Glen Este Withamsville  to be closed.

    - Any traffic signal work should fall under this contract

  - 21-0591

    - Non-perform the right turn only exit from 32 EB to Glen Este SB

    - Instead perform a complete closure and install cul-de-sac turn around

    - Eventually will open up the ramp from 22-0039 project

21-0591, MOT conflicts from the multiple Parts (1, 2, & 3)

- Fire Department concern with closing SR 74 and Marian Dr.

  - To resolve this, we have agreed to install emergency access to Marian Drive for authorized vehicles only

  - JRJ will build a construction entrance and barricades in order to not allow public travelers access but allow emergency vehicles a location to access the apartment complex.

- Apartment Complex action items

  - The sign within the limits of the MSE wall needs electric disconnected. JRJ will perform sign removal and retaining wall removal.

  - Perform the traffic reconfiguration of the north parking lot on 3/31/22, from 8am to 5pm.

    - ODOT to notifying Apartment complex of scheduled work

    - All vehicles in the area needs to be gone in order to perform the work

      - Vehicles still remaining at 8am will be towed

    - JRJ to waterblast existing parking lines, paint new parking lines, install PCB and necessary signage

- JRJ to take care of Elick property repairs as well as electric disconnect to garage. Electric disconnect work being done via FA.

- Traffic Detours for Part 1.

  - The detour plan sheet notes say to maintain existing detours for the permanent road closures through out each phase of the project.

  - JRJ and ODOT agreed that this could cause confusion to the traveling public

  - JRJ will remove the previous phase detour prior to installing the subsequent phase.