## WWP Template
|  | TWO WEEK LOOK-AHEAD | JRJ Project # | 10571 | [7 empty] | Week's Planning Accuracy
|  |  | DOT # | 210591 | Previous Week PPC | [6 empty] | Total Activities Planned | [7 empty] | 0
|  |  | Job Name | Clermont 32 | Week of | 2024-07-31 | [5 empty] | Activities Completed | [7 empty] | 0
|  |  | Date | 2024-08-07 | [7 empty] | Percent Planned Complete | [7 empty] | #DIV/0! |  | (tentative)
[5 empty] | Project Average: | #DIV/0! | [5 empty] | Week Of: |  | 2024-08-12 | [7 empty] | Week Of: |  | 2024-08-19
| Phase | Operation | Foreman | Material Qty | Resources |  | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-17 | 2024-08-18 | DONE? |  | Category | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25
|  |  |  | Notes | Select from Drop-down |  | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | YES | NO |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Clermont 32, ODOT 210591, JRJ 10571 | Part 2 SR 32 Median Work | bar: Thu to Fri
|  | Underdrain | Zorb | bar: Wed to Fri
304 agg base
Zorb | bar: Fri; Mon to Tue
|  | Asphalt Base & Int | Troy | bar: Wed to Fri
|  | Asphalt cul-de-sacs | Stacey
|  | Median Wall Hand Work | KOKO | starting at paved section near fayard | bar: Wed to Fri; Mon to Tue
end anchors, lightpoles, inlets
|  | set light poles | ELEX | spread footers design from ODOT | [17 empty] | x | x | x
|  | set anchor bolts | Security | bar: Thu
|  | Pulling wall | Zorb | bar: Tue to Wed
|  | Traffic Switch | A&A | 2024-08-15
x
OLD 74, 220625 | bar: Thu to Fri
| NOTES: |  |  |  |  | Day | Mon: M; Tue: T; Wed: W; Thu: H; Fri: F; Sat: S; Sun: S
Day Trucks
Night Trucks
Total Trucks

## Average PPC
AVG | #DIV/0!
2015-03-30 |  | #DIV/0!
2015-04-06 |  | #DIV/0!
2015-04-13 |  | #DIV/0!
2015-04-20 |  | #DIV/0!
2015-04-27 |  | #DIV/0!
2015-05-04 |  | #DIV/0!
2015-05-11 |  | #DIV/0!
2015-05-18 |  | #DIV/0!
2015-05-25 |  | #DIV/0!
2015-06-01 |  | #DIV/0!
2015-06-08 |  | #DIV/0!
2015-06-15 |  | #DIV/0!
2015-06-22 |  | #DIV/0!
2015-06-29 |  | #DIV/0!
2015-07-06 |  | #DIV/0!
2015-07-13 |  | #DIV/0!
2015-07-20 |  | #DIV/0!
2015-07-27 |  | #DIV/0!
2015-08-03 |  | #DIV/0!
2015-08-10 |  | #DIV/0!
2015-08-17 |  | #DIV/0!
2015-08-24 |  | #DIV/0!
2015-08-31 |  | #DIV/0!
2015-09-07 |  | #DIV/0!
2015-09-14 |  | #DIV/0!
2015-09-21 |  | #DIV/0!
2015-09-28 |  | #DIV/0!
2015-10-05 |  | #DIV/0!
2015-10-12 |  | #DIV/0!
2015-10-19 |  | #DIV/0!
2015-10-26 |  | #DIV/0!
2015-11-02 |  | #DIV/0!
2015-11-09 |  | #DIV/0!
2015-11-16 |  | #DIV/0!
2015-11-23 |  | #DIV/0!
2015-11-30 |  | #DIV/0!
2015-12-07 |  | #DIV/0!
2015-12-14 |  | #DIV/0!

## Category Tracking
[17 empty] | SUM | [16 empty] | Average
Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 1-Weather | 2-Labor | 3-Equipment | 4-Material | 5-Subcontract | 6-Owner | 7-Site Condition | 8-RFI | 9-Contract CO | 10-Plant | 11-Accident | 12-Trucking | 13-Low Production | 14-High Production | 15-Operations Decision | 16-Other
2015-03-30 | [16 empty] | 2015-03-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-04-06 | [16 empty] | 2015-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-04-13 | [16 empty] | 2015-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-04-20 | [16 empty] | 2015-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-04-27 | [16 empty] | 2015-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-04 | [16 empty] | 2015-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-11 | [16 empty] | 2015-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-18 | [16 empty] | 2015-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-25 | [16 empty] | 2015-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-01 | [16 empty] | 2015-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-08 | [16 empty] | 2015-06-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-15 | [16 empty] | 2015-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-22 | [16 empty] | 2015-06-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-29 | [16 empty] | 2015-06-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-07-06 | [16 empty] | 2015-07-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-07-13 | [16 empty] | 2015-07-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-07-20 | [16 empty] | 2015-07-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-07-27 | [16 empty] | 2015-07-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-08-03 | [16 empty] | 2015-08-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-08-10 | [16 empty] | 2015-08-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-08-17 | [16 empty] | 2015-08-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-08-24 | [16 empty] | 2015-08-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-08-31 | [16 empty] | 2015-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-09-07 | [16 empty] | 2015-09-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-09-14 | [16 empty] | 2015-09-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-09-21 | [16 empty] | 2015-09-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-09-28 | [16 empty] | 2015-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-10-05 | [16 empty] | 2015-10-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-10-12 | [16 empty] | 2015-10-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-10-19 | [16 empty] | 2015-10-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-10-26 | [16 empty] | 2015-10-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-11-02 | [16 empty] | 2015-11-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-11-09 | [16 empty] | 2015-11-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-11-16 | [16 empty] | 2015-11-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-11-23 | [16 empty] | 2015-11-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-11-30 | [16 empty] | 2015-11-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-12-07 | [16 empty] | 2015-12-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-12-14 | [16 empty] | 2015-12-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## LISTS
RESOURCES
JRJ Paint
Mill
Rubber-tire hoe
Security - Rail
Security - Sign
Stabilization
Survey
UD Trencher
Waterblaster
1 | Weather | 1 - Weather
2 | Labor | 2 - Labor
3 | Equipment | 3 - Equipment
4 | Material | 4 - Material
5 | Subcontract | 5 - Subcontract
6 | Owner | 6 - Owner
7 | Site Conditions | 7 - Site Conditions
8 | RFI's | 8 - RFI's
9 | Contract CO | 9 - Contract CO
10 | Plant Error | 10 - Plant Error
11 | Accident | 11 - Accident
12 | Trucking | 12 - Trucking
13 | Low Production | 13 - Low Production
14 | High Production | 14 - High Production
15 | Operations Decision | 15 - Operations Decision
16 | Other | 16 - Other