## Slide 2
Construction Administration Clint Bishop

## Slide 3: TOPICS
Spec Updates
  104.02.D Significant Changes
  105.20 As Per Plan Designation
  107.15 & 622.08 Damaged Traffic Control Equipment
  107.21 Prompt Payment
  108.02 Dispute Resolution
  108.095 Partial Severability
Proposal Note Updates
  PN 151 Railroad Flagging Service
  PN 153 -Indefinite Delivery Indefinite Quantity IDIQ
  PN 525 Steel Price Adjustment
Buy America Updates
  Proposal Note 133 Products Made in the United States
Manual of Procedures
  107.15 Contractor’s Responsibility for Work

## Slide 4: 104.02.D Significant Changes
On smaller projects, Contract Limits increased from $25k to $50k
Revision to ORC 5525.14 during Transportation Budget Bill submission
Effective July 1, 2025

## Slide 5: 105.20 As Per Plan Designation
105.20 As Per Plan Designation.
  “As Per Plan” designation may be added to some item descriptions in the proposal to assist in identifying Work with project specific requirements.
  The absence of an “As Per Plan” designation on item descriptions in the proposal having clear and controlling plan notes does not relieve the Contractors of the responsibility to read, bid and construct those particular items in accordance with the governing plan notes.
Language moved from Proposal Note 33 to C&MS.

## Slide 6: 107.15 & 622.08 Damaged Traffic Control Equipment
In the event that the Engineer determines that damage to completed permanent items of Work results from traffic using a substantially completed section of Roadway, the Department may compensate the Contractor for repair of the damage as authorized by Change Order. Additionally, if traffic permanently damages beyond use and of the following temporary maintenance of traffic items, the Department may compensate the Contractor for replacement of the item as authorized by Change Order:
Arrow board,
Work zone signal, pole, or controller,
Lighting unit or pole,
Changeable message sign,
Work Zone Impact Attenuator,
Truck Mounted Impact Attenuator,
Digital Speed Limit Sign Assembly,
Portable Barrier.

## Slide 7: 107.21 Prompt Payment
Retainage cannot exceed eight percent of the estimates paid until fifty percent of the work has been satisfactorily completed, then the amount retained cannot exceed four percent. Progressively and proportionately release any retainage held, as set forth in any subcontractor or supplier agreement, 30 days after the work is satisfactorily completed. For the purposes of this section, a subcontractor’s work is satisfactorily completed when payment forall the tasks called for in the subcontract have been accomplished and documented payment for a subcontractor’s work or supplier’s material has been made by the Department. No subcontract provision shall permit the Contractor to delay subcontractor’s retainage payments until the Project’s final payment.
Notes: Developed by Construction Administration and SBED
• Delete the 30-day provision because that seems to cause confusion with the 10-day requirement above it.
• Payment for the work is made after the tasks called for in the subcontract have been accomplished and documented

## Slide 8: 108.02 Dispute Resolution
  Step 1 added language: Informal discussions with the DCE are permissible during the Step 1 review
  Shortened Step 1 Determination: The Engineer will issue a written Step 1 decision within seven (was 14) calendar days of the meeting.
  Shortened Step 3 Notice: Submit a written Notice of Intent to File a Claim to the Dispute Resolution Coordinator … within seven (was 14) calendar days of receipt of the Step 2 decision.
Notes: Dispute Resolution Task Force
Goal to shorten the process
DCE can be involved in Step 1 decisions that may later escalate to Step 2 where the DCE is on the board. Effort to better resolve issues at Step 1.

## Slide 9: 108.02 Dispute Resolution
  Revised language on interest for claims:
    Interest on Claims. The Department will pay interest in accordance with ORC Section 5703.47 on any amount ultimately found due on a claim which is not paid within 30 days of the Dispute Resolution Coordinator's Receipt of the Certified Claim expenditure of funds by the Contractor in accordance with ORC 126.30 when all Work related to the Claim is complete. However, interest will not be paid on the amount of any agreed settlement unless specifically itemized and included in the total settlement prior to agreement

## Slide 10: 108.095 Partial Severability
108.095 Partial Severability Due to Legal Revisions. If any term of the Contract is to any extent illegal, otherwise invalid, or incapable of being legally enforced, such term shall be excluded to the extent of such invalidity or unenforceability; all other requirements hereof shall remain in full force and effect.
Notes: Common contractual clause
The Severability Clause, also sometimes called a partial invalidity clause, is a nearly universal miscellaneous clause in a contract agreement that addresses how the remainder of the agreement is to be interpreted in the event that a court finds that one or more terms are invalid, illegal or unenforceable.

## Slide 11: Proposal Note 151 Railroad Flagging Service
Necessary due to a labor shortage with respect to Norfolk Southern Railroad. They are no longer providing Norfolk Southern personnel for railroad flagging during construction on their right-of-way.
Norfolk Southern has certified two companies to provide flagging services during construction on their right-of-way.
    Revision deletes Railroad Consultants (out of business) and adds R&R Consulting Team.
This specification will allow the contractor to hire one of the two certified companies for railroad flagging services and be reimbursed in a contract line item.

## Slide 12: Proposal Note 153 Indefinite Quantity/Indefinite Delivery (ID/IQ) Projects
This project will be delivered utilizing the Indefinite Quantity/Indefinite Delivery (ID/IQ) contracting method authorized by Ohio Revised Code Section 5517.012.
This Proposal Note replaces all sections of the 2023 Construction and Material Specifications 100 GENERAL PROVISIONS sections (C&MS 100 Series Specifications).

## Slide 13: Proposal Note 153 Indefinite Quantity/Indefinite Delivery (ID/IQ) Projects
Key Provisions:
Contract Value
  Max $2 million per project.
  May increase by $200,000 or 10%, whichever is less.
Contract Duration
  Max 2 years
  May extend up to 1 additional year if determined necessary.
Project Geography
  Contracts may not cross Districts; no more than one ODOT district.
Work Types
  Limited: Guardrail, highway lighting, and traffic signal maintenance.
Concurrent Contracts
  Each district can have up to two active contracts at any time.
Notes: Revisions made to ORC 5517.012 when submitting the Transportation Budget Bill.

## Slide 14: Proposal Note 525 Steel Price Adjustment
Added Language to Opt-out of the Steel Price Adjustment:
  To elect to not participate in the Steel Price Adjustment, advance notification must be submitted to the Department. The apparent low bidder is required to submit the Steel Price Adjustment Opt-out form via email to steeloptions@dot.ohio.gov by 3:00 pm prevailing local time within 7 calendar days after the bid opening. When the seventh calendar day after the bid opening falls on a day Department offices are closed, submit the Steel Escalation Price Adjustment Opt-out form by 3:00 pm prevailing local time on the next business day. If a properly completed Steel Price Adjustment Opt-out form is not provided by the apparent low bidder within the time specified, the Department will consider the option to not participate in these price adjustment provisions on the project to be declined. The Steel Price Adjustment Opt-out form is located on the Department’s website here: Pages - Price Indexes (state.oh.us).

## Slide 15: Buy America Updates
Proposal Note 133 Products Made in the United States
New Buy America webpage: Buy America Information & Exceptions | Ohio Department of Transportation
  Proposal Note 133
  Recent updates
  OMM list of material codes separated into Steel/Iron, Construction Materials, Manufactured Products
  Exception Form for de minimis quantities

## Slide 16: Buy America Updates
  FHWA has rescinded an existing waiver that states Manufactured Products are not required to be made domestically.
  FHWA has updated language that would require Manufactured Products to be manufactured in the United States “final assembly requirement” and made domestically 55% by cost “55 percent requirement.”
  Manufactured products that receive Federal authorization on or after October 1, 2025 must meet the final assembly requirement. Manufactured products that receive Federal authorization on or after October 1, 2026.must meet the final assembly requirement and the 55 percent requirement.

## Slide 17: Buy America Updates
Precast concrete products that are classified as manufactured products must have their predominantly iron or steel components meet the above requirements for iron and steel.
The cabinets or other enclosures of intelligent transportation systems (ITS) and other electronic hardware systems that are installed in the highway right of way and classified as manufactured products must comply with the above requirements for iron and steel if the cabinet or enclosure is predominately iron or steel.
Notes: Items emphasized in the Final Rule for Manufactured Products.
Predominately iron or steel or a combination of both means the total cost of the iron and steel content exceeds 50 percent of the total cost of all its components.

## Slide 18: Manual of Procedures 107.15 Contractor’s Responsibility for Work
If the Contractor follows the CMS 107.15 process and does not receive a response from the motorist or the insurance company, the following process will govern:
The Project Engineer shall process a change order to compensate the contractor for the damage. Use change order reason code #37.
The Project Engineer will forward the accident report and other documentation the contractor used to make good faith efforts to collect compensation to their District Accounts Receivable contact person to generate an invoice.
If the invoice is not paid within 90 calendar days, the District Accounts Receivable system will automatically send a certified invoice to the Ohio Attorney General’s Office for collection.
Notes: This section will provide guidance to the project engineer when the Contractor is following the process to receive compensation for damage to permanent items of Work or temporary maintenance of traffic items listed in this section of the Construction and Materials Specifications.

## Slide 19: Manual of Procedures 107.15 Contractor’s Responsibility for Work
If the Contractor follows the CMS 107.15 process and the insurance company is offering less than the total cost for any reason, the following process will govern:
1. The Contractor nor the Department should accept any offer less than the actual cost initially.
2. The District shall forward all pertinent information to the Department’s Chief Legal Counsel

## Slide 20: Manual of Procedures 107.15 Contractor’s Responsibility for Work
3. Chief Legal Counsel will review the information and decide on the next step likely consisting of one of the following two scenarios.
  a. Reject in whole the reduced offer from the insurance company. ODOT (project level) would then immediately process a change order for the total
  cost of the repair to fully compensate the Contractor. Chief Legal Counsel will coordinate with the Attorney General’s Office to determine the next step.
  b. Accept the reduced offeror from the insurance company. The partial reduced offer payment shall be made directly from the insurance company to the Contractor. The Department (project level) will issue a change order for the difference between the reduced offer and agreed value. Chief Legal Counsel will coordinate with the Attorney General’s Office if needed.

## Slide 21: Questions
Clint Bishop, P.E.
Staff Specialist,
Office of Construction Administration and Innovative Delivery
1980 West Broad Street
Columbus, Ohio 43223
D: 614.387.1164
clint.bishop@dot.ohio.gov

## Slide 22
Thank You Attendees & Sponsors