# PN 127 –1/16/2026 - Lane Value Contract:

The Contractor shall be assessed Disincentives as designated in the Lane Value Contract Table for each unit of time the described Critical Lane/Ramp is restricted from full use by the traveling public within the restricted time period. The Lane Value Contract Table is located in the Plan General Notes. The Disincentives will be assessed for all restrictions of the critical work.

Critical work is shown in the Lane Value Contract Table.

Critical work is defined as having the designated sections open to unrestricted traffic as shown in the table, or the entire project if not otherwise listed.

Unrestricted traffic is defined as all traffic lanes being available for use with specified striping and safety features in place.

For any Contractor restrictions initiated prior the start of the Lane Value Contract Table’s restricted time period, the Contractor will be assessed the maximum Disincentives. Disincentives for restrictions that continue within the first hour after the Lane Value Contract Table’s restricted time period starts will be prorated. Those prorates will be as follows:

| Minutes after restricted time period, T* | Prorate applied to maximum Disincentive, P* |
| --- | --- |
| 0 - 30 | 0.25 |
| 31 - 60 | 0.75 |
| 61 + | 1.00 |
| *The maximum Disincentive is determined by the Lane Value Contract Table located in the Plan General Notes. Only one prorate will be applied per event. For a single event, the total disincentive will be calculated as such: TD=P×T×LV×L Where: TD=Total Disincentive, $ T=duration of time after the start of the restricted time period, min LV=lane value maximum Disincentive, $/min/lane L=number of lanes restricted, lane |  |

Disincentives will not be assessed for delays outside the Contractor's control or responsibility, such as private motorist accidents, on-site equipment breakdowns, civil disturbances, or Engineer-ordered revisions to the Work. The Department reserves the right to assess the maximum Disincentive without proration if there have been three or more events on the project including, but not limited to, three or more equipment breakdowns or other incidents which the contractor's inactions/actions contributed to the event. Such other actions could be early lane restrictions without prior Engineer approval.

# Prior to assessing any single Disincentive amount exceeding $50,000, the restriction event and the proposed Disincentive will be evaluated by the Maintenance of Traffic Executive Committee (MOTEC) to confirm applicability, calculation, and justification of the assessment.

# Designer Notes

For use with the 2019 C&MS. These Designer Notes are for information and direction to the Designer. Information within Designer Notes are not to be considered binding nor included within the Contract.

## Purpose and Benefits

A Lane Value Contract establishes a Disincentive that is assessed to the Contractor for each time interval that a critical lane or ramp is restricted. The Disincentive amounts do not have to be the same amount for each lane or ramp configuration. It allows the Department to allocate road user costs based on dense traffic or other high value areas. The Disincentives are assessed for each time period the specific lane / ramp is restricted. The Contractor will pass on the minimum assessments they feel are required to get the high priority lane or ramp open. This encourages the Contractor to focus work on highest priority lanes.

Time Savings: If used properly the construction time for specific areas will be decreased.

Congestion: Lane Value Contracts allow the Department to minimize the lane closure duration in order to lessen the congestion time. Also, lane closures can be held to a minimum, this is the most restrictive note the Department currently uses and allocates road user costs based on delays to a very large number of traveling public as the Disincentives.

## Criteria for Selection

- This project is of a complex nature and has high traffic volume

- All projects within work limits located on highway segments listed in the Permitted Lane Closure System shall include Proposal Note 127 – Lane Value Contract.

## Project Types

Complex and high traffic volume projects- A construction project with areas that are critically important to remain unrestricted.Note to be included in the Plan General Notes (with sample language):

Lane Value Contract Table

| Description of Critical Lane/Ramp to be maintained | Restricted Time period | Time Unit | Disincentive $ per minute per lane |
| --- | --- | --- | --- |
| 2 Lanes of FRA IR 71 from MM99 to MM101 | 06:00 – 19:00 | Each Minute per Lane | $10,000 |
| Ramp from IR 270 NB to SR 161 EB | 06:00 – 19:00 | Each Minute per Lane | $1,000 |