## Sheet1
Description of Critial Work | Calendar Days to Complete | Disincentive $ per Day | Work Window
|  |  | Start | End
All Roadway, Pavement, Traffic Control, and Structures work | 90 | $2,000 per day | 2026-04-01 | 2026-10-01
All work on project (including work listed above) | 180 | Per C&MS 108.07 | Contract Execution Date | Project Completion Date