## Sheet1
OUPS 1-800-362-2764 |  | Project Number |  | AUG-SR198501-INTERSECTIONS | [5 empty] | Last Updated By: | BMW
PM: | 0 |  | OUPS Ticket: | B328500124-00B - BS32850010152-00B | [5 empty] | On: | 2025-02-10
Utility Company | Telephone | Contact | Project Notification and Request for Plans | Received Utility Plans or Positive Response | Sent Stage 1 (35%) Plans | Received Comments | Sent Stage 2 (80%) Plans | Received Comments | Sent Stage 3 (95%) Plans | Received Comments | Remarks
Name and Address | No. | Name
AEP - OHIO (WESTERN) | ? | PAUL T PAXTON | 2024-01-15 | 1-15-24 - Paul Paxton responded with statement he sees no conflicts. COEC asks for further | 2024-03-29 | 3-29-24: Paul Paxton stated Clarke Saunders is now in charge of the region | 2024-07-29
209 N. WOOD STREET |  | ptpaxton@aep.com |  | clarification of what AEP owns within project limits.
FOSTORIA, OHIO 44830 | [5 empty] | 4-1-24: Clarke stating no faciliites within project limits.
|  | CLARKE SAUNDERS |  | 1-16-24 - Paxton states AEP distribution has no faciliites in the area
cmsaunders@aep.com
CHARTER COMMUNICATIONS | 937-396-8611 | JUSTIN TEGTMEYER | 2024-01-15 |  | 2024-03-29 |  | 2024-07-29 | 7-29-24 - keith jones auto repsonse out of office
3691 TURNER ROAD |  | justin.tegtmeyer@charter.com |  |  |  |  | 2024-08-01 | 8/1/2024 - Keith Jones will confirm the clearances and coordinate with Levi
DAYTON, OHIO 45415 | [7 empty] | 8/13/24 - Keith confirmed that they have the clearance for the signal supports.
MARY EVANS
mary.evans@charter.com
810 N MAIN STREET | 419-584-5183 | KEITH JONES |  | 1-16-24 - keith jones stated everything is aerial in the area on City of Wapak poles.
CELINA, OHIO 45822 |  | keith.jones@charter.com |  | if a pole need moved, he will work with Levi at the City to get his things moved.
TELEPHONE SERVICE COMPANY | 419-739-2241 | RANDY HEINL | 2024-01-15 | 1-16-24 - Randy Heinl stating TSC has no facilities within the area. | 2024-03-29 |  | 2024-07-29 | 2-7-25 - Chris Hardy coordinating a new fiber optic that is coming through the interseciton.
2 WILLIPIE STREET |  | Randy@telserco.com | [5 empty] | 2-10-25 - COEC agreed no poles are being relocated and to coordinate with the City on installing lines at elevations that will not
P.O. BOX 408 | [7 empty] | conflict with the future mast arms.
WAPAKONETA, OHIO 45895 | 419-739-2560 | Chris Hardy | [5 empty] | 2-10-25 - Chris Hardy believes they are good to go with their project and our project coordinations
chris.hardy@telserco.com
DOMINION ENERGY OF OHIO | 419-226-4829 | W. Michael North | 2024-01-15 | 1-25-24 - Michael stated the only area of concern is the CB along Lincoln Avenue. | 2024-03-29 |  | 2024-07-29
150 S. JACKSON STREET |  | w.michael.north@dominionenergy.com |  | The invert seem fine, but the basin itself is very close to the existing line.
LIMA, OHIO 45801 |  |  |  | COEC responded with answers to questions and asked if 6" to 8" of clearance is okay.
RELOCATIONS
|  | relocation@dom.com |  | 1-25-24 - michael agreed a plan note regarding the close proximity will suffice
CITY OF WAPAKONETA - WATER | 419-738-7439 | BRENT J HAMEL | 2024-01-15 | 2-16-24: Called Brent and sent email regarding the water lines not being marked. | 2024-03-29 |  | 2024-07-29
203 E. HARRISON STREET |  | bhamel@wapakoneta.net |  | 2-16-24: Wapak stating they will get water lines marked
P.O. BOX 269
WAPAKONETA, OHIO 45895
CITY OF WAPAKONETA - ELECTRIC | 419-738-7713 | LEVI CECIL | 2024-01-15 | 1-22-24 - levi cecil saying everything in the plans looks accurate to him | 2024-03-29 |  | 2024-07-29 | 7-29-24 - Levi auto reply stating out of office
251 INDUSTRIAL DRIVE |  | lcecil@wapakoneta.net | [5 empty] | 3/27/2025 - Levi confirmed the temporary pole and guy pole to be installed by the City and the contractor will utilize in the temporary signal support.
P.O. BOX 269
WAPAKONETA, OHIO 45895

## Sheet2
Utility | Utility Owners Name | Utility Companies Representatives Name | Utility Companies Representatives Address | Utility Companies Representatives Telephone Numbers | Utility Companies Representatives Email Address | Remarks
Telephone
Electric (Transmission)
Electric (Distribution)
Storm Sewer
Cable
Gas (Transmission)
Gas (Distribution)
Water & Sanitary