## FINAL QUANTITIES
By: JSE |  |  |  |  | 2025-12-17
Checked: WER |  |  |  |  | 2025-12-17
ESTIMATED QUANTITIES
ITEM | EXTENSION | TOTAL | UNIT | DESCRIPTION | SHEET REF.
202 | 11203 | LS |  | PORTIONS OF STRUCTURE REMOVED, OVER 20 FOOT SPAN, AS PER PLAN | P.10, P.14
SPECIAL | 51267400 | 4055.04 | SF | WATERPROOFING: TIMBER BOARDWALK | P.10
518 | 21200 | 8.0157 | CY | POROUS BACKFILL WITH GEOTEXTILE FABRIC
519 | 11101 | 16.6 | SF | PATCHING CONCRETE STRUCTURE, AS PER PLAN | P.10
SPECIAL | 53000600 | 600 | SF | STRUCTURES: TIMBER BOARDWALK | P.10
601 | 20011 | 7 | CY | CRUSHED AGGREGATE SLOPE PROTECTION, AS PER PLAN | P.10, P.11
SPECIAL | 69098400 | LS |  | ASBESTOS CONTAINING MATERIALS | P.4
870 | 10001 | 78 | SF | PREFABRICATED MODULAR RETAINING WALL, AS PER PLAN | P.10, P.12
870 | 11000 | 29.5148 | CY | WALL EXCAVATION
870 | 11100 | 2.5 | CY | NATURAL SOIL
870 | 12000 | 13 | FT | 6" DRAINAGE PIPE, PERFORATED
870 | 12100 | 20 | FT | 6" DRAINAGE PIPE, NON-PERFORATED
870 | 14000 | 2 | DAY | ON-SITE ASSISTANCE
878 | 25000 | LS |  | INSPECTION AND COMPACTION TESTING OF UNBOUND MATERIALS

## 202E11203
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 202E11203
CALCULATIONS |  |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 1
PID NO. |  | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME |  | PORTIONS OF STRUCTURE REMOVED, OVER 20 FOOT SPAN, AS PER PLAN | [6 empty] | PAY UNIT | LS
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
LUMP SUM ITEM
TOTAL | [8 empty] | 0 | LS

## 512E67400
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 512E67400
CALCULATIONS |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 3
PID NO. | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME | SPECIAL - WATERPROOFING: TIMBER BOARDWALK | [6 empty] | PAY UNIT | SF
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
| BRIDGE LENGTH | 337.92 | FT
| BRIDGE WIDTH | 12 | FT
| TOTAL | 4055.04 | SF |  |  |  |  | 4055.04
TOTAL | [7 empty] | 4055.04 | 4055.04

## 518E21200
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 518E21200
CALCULATIONS |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 4
PID NO. | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME | POROUS BACKFILL WITH GEOTEXTILE FABRIC | [6 empty] | PAY UNIT | CY
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
| AREA | 16.648 | SF
| LENGTH | 13 | FT
| TOTAL | 216.424 | CF
| TOTAL | 8.0157 | CY |  |  |  |  | 8.0157
TOTAL | [7 empty] | 8.0157 | 8.0157

## 519E11101
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 519E11101
CALCULATIONS |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 5
PID NO. | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME | PATCHING CONCRETE STRUCTURE, AS PER PLAN | [6 empty] | PAY UNIT | SF
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
| REAR ABUTMENT | 8.8 | SF
| FORWARD ABUTMENT | 7.8 | SF
| TOTAL | 16.6 | SF |  |  |  |  | 16.6
TOTAL | [7 empty] | 16.6 | 16.6

## 530E00600
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 530E00600
CALCULATIONS |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 6
PID NO. | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME | SPECIAL - STRUCTURES: TIMBER BOARDWALK | [6 empty] | PAY UNIT | SF
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
| BRIDGE AREA | 4055.04 | SF
| 15% AREA | 608.256 | SF
| USE | 600 | SF |  |  |  |  | 600
TOTAL | [7 empty] | 600 | 600

## 601E20011
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 601E20011
CALCULATIONS |  |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 7
PID NO. |  | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME |  | CRUSHED AGGREGATE SLOPE PROTECTION, AS PER PLAN | [6 empty] | PAY UNIT | CY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
MEASURED BY COMPUTER
|  | TOTAL | 7 | CY |  |  |  |  | 7
TOTAL | [8 empty] | 7 | 7

## 690E98400
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 690E98400
CALCULATIONS |  |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 8
PID NO. |  | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME |  | SPECIAL - MISC.: WORK INVOLVING ASBESTOS CONTAINING MATERIALS | [6 empty] | PAY UNIT | LS
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
LUMP SUM ITEM
TOTAL | [8 empty] | 0 | LS

## 870E10001
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 870E10001
CALCULATIONS |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 9
PID NO. | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME | PREFABRICATED MODULAR RETAINING WALL, AS PER PLAN | [6 empty] | PAY UNIT | SF
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
| LENGTH | 13 | FT
| HEIGHT | 6 | FT
| TOTAL | 78 | SF |  |  |  |  | 78
TOTAL | [7 empty] | 78 | 78

## 870E11000
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 870E11000
CALCULATIONS |  |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 10
PID NO. |  | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME |  | WALL EXCAVATION | [6 empty] | PAY UNIT | CY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
| LENGTH ALONG WALL (FT) |  | AREA (SF) | VOLUME (CF)
| 0 |  | 49.1
| 2.6 |  | 52.9 | 132.6
| 5.2 |  | 57.5 | 143.52
| 7.8 |  | 63.4 | 157.17
| 10.4 |  | 70.2 | 173.68
| 13 |  | 75.9 | 189.93
|  |  | TOTAL | 796.9 |  | CF
|  |  | TOTAL | 29.5148 |  | CY |  |  | 29.5148
TOTAL | [8 empty] | 29.5148 | 29.5148

## 870E11100
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 870E11100
CALCULATIONS |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 11
PID NO. | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME | NATURAL SOIL | [6 empty] | PAY UNIT | CY
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
| LENGTH | 13 | FT
| AREA | 4.4 | SF
| TOTAL | 57.2 | CF
| TOTAL | 2.1185 | CY |  |  |  |  | 2.5
TOTAL | [7 empty] | 2.5 | 2.5

## 870E12000
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 870E12000
CALCULATIONS |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 12
PID NO. | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME | 6" DRAINAGE PIPE, PERFORATED | [6 empty] | PAY UNIT | FT
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
| LENGTH | 13 | FT |  |  |  |  | 13
TOTAL | [7 empty] | 13 | 13

## 870E12100
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 870E12100
CALCULATIONS |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 13
PID NO. | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME | 6" DRAINAGE PIPE, NON-PERFORATED | [6 empty] | PAY UNIT | FT
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
| LENGTH | 20 | FT |  |  |  |  | 20
TOTAL | [7 empty] | 20 | 20

## 870E14000
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 870E14000
CALCULATIONS |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 14
PID NO. | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME | ON-SITE ASSISTANCE | [6 empty] | PAY UNIT | DAY
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
|  | 2 | DAYS |  |  |  |  | 2
TOTAL | [7 empty] | 2 | 2

## 878E25000
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 878E25000
CALCULATIONS |  |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 15
PID NO. |  | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME |  | INSPECTION AND COMPACTION TESTING OF UNBOUND MATERIALS | [6 empty] | PAY UNIT | LS
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
LUMP SUM ITEM
TOTAL | [8 empty] | 0 | LS

## 512E10100
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-12-17 | ITEM NUMBER: | 512E10100
CALCULATIONS |  | CHECKED BY: | WER | DATE: | 2025-12-17 | PAGE NUMBER: | 2
PID NO. | 124268 |  | PROJECT | BEL-National Road |  | STRUCTURE | SFN 0701114
ITEM NAME | SEALING OF CONCRETE SURFACES (EPOXY-URETHANE) | [6 empty] | PAY UNIT | SY
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
| WALL LENGTH | 13 | FT
| WALL THICKNESS | 28 | IN.
| EXPOSED WALL HEIGHT | 4 | FT
| TOTAL | 101 | SF
| TOTAL | 11.2222 | SY |  |  |  |  | 11.2222
TOTAL | [7 empty] | 11.2222 | 11.2222