## Disincentives
CRITICAL WORK | CALENDAR DAYS TO COMPLETE | DISINCENTIVE ($ PER DAY)
ALL WORK | 60 | 1500

## Holidays
NEW YEAR'S (OBSERVED) | GENERAL ELECTION DAY
MEMORIAL DAY | THANKSGIVING
FOURTH OF JULY (OBSERVED) | CHRISTMAS (OBSERVED)
LABOR DAY | OTHER HOLIDAY OR EVENT

## Schedule
DAY OF HOLIDAY OR SPECIAL EVENT | TIME ALL LANES MUST BE OPEN TO TRAFFIC
SUNDAY | 12:00N FRIDAY THROUGH 6:00AM MONDAY
MONDAY | 12:00N FRIDAY THROUGH 6:00AM TUESDAY
TUESDAY | 12:00N MONDAY THROUGH 6:00AM WEDNESDAY
TUESDAY (GEN. ELECTION) | 5:00AM TUESDAY THROUGH 12:00AM WEDNESDAY
WEDNESDAY | 12:00N TUESDAY THROUGH 6:00AM THURSDAY
THURSDAY | 12:00N WEDNESDAY THROUGH 6:00AM FRIDAY
FRIDAY | 12:00N THURSDAY THROUGH 6:00AM MONDAY
SATURDAY | 12:00N THURSDAY THROUGH 6:00AM MONDAY

## LaneValue
LANE VALUE CONTRACT TABLE
DESCRIPTION OF CRITICAL LANE | TIME UNIT | DISINCENTIVE $ PER TIME UNIT
ALL LANES EB & WB OF BRO US 50 FROM SLM 0.00-5.27 | EACH MINUTE | 55

## Notifications
NOTIFICATION OF TRAFFIC RESTRICTION TIME TABLE
ITEM | DURATION OF CLOSURE | NOTICE DUE TO PERMITS & PIO
RAMP & ROAD CLOSURES | >= 2 WEEKS | 21 CALENDAR DAYS PRIOR TO CLOSURE
| >12 HOURS & < 2 WEEKS | 14 CALENDAR DAYS PRIOR TO CLOSURE
| <= 12 HOURS | 4 CALENDAR DAYS PRIOR TO CLOUSRE
LANE CLOSURES & RESTRICTIONS | >= 2 WEEKS | 14 CALENDAR DAYS PRIOR TO CLOSURE
| < 2 WEEKS | 5 BUSINESS DAYS PRIOR TO CLOSURE
START OF CONST. & TRAFFIC PATTERN CHANGES | N/A | 14 CALENDAR DAYS PRIOR TO IMPLEMENTATION