## Interim
SCHEDULE OF DAILY DISINCENTIVES FOR FAILURE TO MEET THE INTERIM COMPLETION REQUIREMENTS
ORIGINAL CONTRACT AMOUNT (TOTAL AMOUNT AT THE TIME OF BIDDING) |  | DAILY DISINCENTIVE FOR EACH FULL OR PARTIAL CALENDAR DAY OF TIME OVERRUN BEYOND THE PLAN INTERIM COMPLETION DATE
FROM MORE THAN | TO AND INCLUDING
0 | 500000 | 800
500000 | 1000000 | 1200
1000000 | 5000000 | 2500
5000000 | 10000000 | 3500
10000000 | 50000000 | 5000
OVER $50,000,000 |  | 7500

## Window
DESCRIPTION OF CRITICAL WORK | CALENDAR DAYS TO COMPLETE | DISINCENTIVE $ PER DAY | WORK WINDOW
|  |  | START | END
ALL WORK AT PRE-122-7.24 | 30 | $800 PER DAY | 2023-04-01 | 2023-05-26