## Sheet1
DESCRIPTION OF CRITICAL WORK | CALENDAR DAYS TO COMPLETE | DISINCENTIVE $ PER DAY | WORK WINDOW
|  |  | START | END
ALL PART 2 WORK REQUIRING SIGNALIZED LANE CLOSURE | 75 DAYS | $3,600 PER DAY | 2024-04-15 | BEFORE PART 1 START
PART 1 RESURFACING INCLUDING PAVEMENT REPAIRS (DOES NOT INCLUDE CURB RAMPS) | 90 DAYS | $3,600 PER DAY | AFTER PART 2 COMPLETION | PROJECT COMPLETION DATE